## VMS -Effort estimation
EFFORT ESTIMATION (man-day)
| Activity Description | Dio (PM) | Peishan (QM) | Thida (BAL) | Hazel (BA) | Zaw (TL) | Feng Yan (DL) | Jifa (TSL)
1 | Project Planning
1.1. | Produce Project Plan | 4
1.2. | Review Project Plan | 1.5 | 1.5
1.3. | Produce Quality Plan |  | 4
1.4. | Review Quality Plans | 1 | 1
1.5. | Prepare first Audit & Presentation | 2 | 2 | 1 | 1 | 1 | 1 | 1
2 | Requirement Analysis
2.1. | Research Requirements | 2.5 |  | 5.5 | 5.5
2.2. | Produce User Requirements Specifications |  |  | 3 | 2.5
2.3. | Review User Requirement Specifications | 1.5 | 1.5 | 1.5
3 | Analysis Modeling
3.1. | Identify Analysis Objects/Ops/Attributes |  |  | 5 | 5 | 5 | 5
3.2. | Produce Class/Collaboration Diagrams |  |  | 5 | 5 | 5 | 5
3.3. | Produce User Case Model Survey (Analysis) |  |  | 5 | 5 | 5 | 5
3.4. | Write Use Case Realization Report (Analysis) |  |  | 2.5 | 2.5 | 2.5 | 2.5
3.5. | Review & Finalize Use Case Realization Reports (Analysis) | 2 | 2 | 2 |  | 2
3.6. | Produce UI Specification |  |  |  |  | 3 | 3
3.7. | Review UI Specifications (3 rounds) | 2 | 2 | 2
3.8. | Produce Prototype UI | [5 empty] | 5 | 5
3.9. | Review Prototype UI (3 rounds) | 1.5 | 1.5
3.10. | Produce Prototyping Study Report |  |  | 1.5 |  | 1.5 | 1.5
3.11. | Produce FS based on UCRR and Prototype UI |  |  |  |  | 5 | 5 | 5
3.12. | Review FS | 2.5 | 2.5
3.13. | Produce High-level DS |  |  |  |  | 2.5 | 2.5
3.14. | Review High-level DS | 2 | 1 |  |  | 0.5
3.15. | Prepare second Audit & Presentation | 2 | 2 | 1 | 1 | 1 | 1 | 1
4 | Design Modeling
4.1. | Adjust objects to implementation architecture |  |  |  |  | 3 | 3
4.2. | Define Object Associations |  |  | 2 | 2 |  |  | 2
4.3. | Produce Sequence Diagrams | 3 | 3 | 3 | 3 |  |  | 3
4.4. | Specify Object Attributes/Operations |  |  | 4 | 4 | 4.5 | 4 | 4
4.5. | Structure Object Model for Implementation |  |  |  |  | 1.5 | 1.5
4.6. | Produce detailed DS |  |  | 2.5 | 2.5 | 5 | 5 | 2.5
4.7. | Review & finalize detailed DS | 1 | 1 |  |  | 1
5 | Programming
5.1. | Implement Code Components | 10 | 10 | 10 | 10 | 10 | 10 | 10
5.2. | Peer Review and Unit Test | 5 | 5 | 5 | 5 | 5 | 5 | 5
5.3. | Integrate System Modules | 2.5 | 5 | 5 | 2.5 | 5 | 5 | 5
6 | Integration System Test
6.1. | Identify Integration Test Approach and Test Plan | 1 |  |  |  | 1 |  | 1
6.2. | Review & finalize Integration and Test Plan | 1 | 1 |  |  |  |  | 1
6.3. | Identify Test Cases based on Use Cases, prepare test script |  |  | 2.5 | 2.5 |  |  | 5
6.4. | Implement Test Environment |  |  |  |  | 2 | 2 | 2
6.5. | Prepare test data | 1 | 1 | 3 | 3
6.6. | Perform System Test | 2.5 | 2.5 |  |  | 1 |  | 2.5
6.7. | Additional Testing: stress test, performance test | 1 | 1 | 1 |  |  |  | 1
6.8. | Analyze Results and Correct Defects | 1 | 1 |  | 5 | 5 | 5 | 5
7 | User Acceptance Testing
7.1. | Prepare UAT environment |  |  |  |  | 2 | 2 | 2
7.2. | Prepare UAT data |  |  | 2.5 | 2.5
7.3. | Conduct UAT | 2.5 | 2.5 |  |  | 1 |  | 2.5
7.4. | Review Test Results/ Corrective Action | 1 | 1 |  | 5 | 5 | 5 | 5
8 | Project Report and Closure
8.1. | Produce Final Project report | 4 | 4
8.2. | Produce User Guide |  |  |  |  | 1 | 1
8.3. | Review User Guide | 1 | 1 |  |  | 1
8.4. | Produce Project Presentation & Audit | 2 | 2 | 1 | 1 | 1 | 1 | 1
| Individual total | 64 | 62 | 76.5 | 75.5 | 89 | 86 | 71.5
| Project Total | 524.5

## Project Milestones
PROJECT MILESTONES
Activity Description
1 | Project Planning
1.1. | Produce Project Plan
1.2. | Review Project Plan
1.3. | Produce Quality Plan
1.4. | Review Quality Plans
1.5. | Prepare first Audit & Presentation
2 | Requirement Analysis
2.1. | Research Requirements
2.2. | Produce User Requirements Specifications
2.3. | Review User Requirement Specifications
3 | Analysis Modeling
3.1. | Identify Analysis Objects/Ops/Attributes
3.2. | Produce Class/Collaboration Diagrams
3.3. | Produce User Case Model Survey (Analysis)
3.4. | Write Use Case Realization Report (Analysis)
3.5. | Review & Finalize Use Case Realization Reports (Analysis)
3.6. | Produce UI Specification
3.7. | Review UI Specifications (3 rounds)
3.8. | Produce Prototype UI
3.9. | Review Prototype UI (3 rounds)
3.10. | Produce Prototyping Study Report
3.11. | Produce FS based on UCRR and Prototype UI
3.12. | Review FS
3.13. | Produce High-level DS
3.14. | Review High-level DS
3.15. | Prepare second Audit & Presentation
4 | Design Modeling
4.1. | Adjust objects to implementation architecture
4.2. | Define Object Associations
4.3. | Produce Sequence Diagrams
4.4. | Specify Object Attributes/Operations
4.5. | Structure Object Model for Implementation
4.6. | Produce detailed DS
4.7. | Review & finalize detailed DS
5 | Programming
5.1. | Implement Code Components
5.2. | Peer Review and Unit Test
5.3. | Integrate System Modules
6 | Integration System Test
6.1. | Identify Integration Test Approach and Test Plan
6.2. | Review & finalize Integration and Test Plan
6.3. | Identify Test Cases based on Use Cases, prepare test script
6.4. | Implement Test Environment
6.5. | Prepare test data
6.6. | Perform System Test
6.7. | Additional Testing: stress test, performance test
6.8. | Analyze Results and Correct Defects
7 | User Acceptance Testing
7.1. | Prepare UAT environment
7.2. | Prepare UAT data
7.3. | Conduct UAT
7.4. | Review Test Results/ Corrective Action
8 | Project Report and Closure
8.1. | Produce Final Project report
8.2. | Produce User Guide
8.3. | Review User Guide
8.4. | Produce Project Presentation & Audit

## Sheet1
210