## Task
Project: MTECH SE18 TEAM8S Server: team8s.myvnc.com\DefaultCollection Query: All tasks List type: Flat
ID | Work Item Type | Iteration Path | Area Path | Title | Assigned To | Start Date | Finish Date | State | Resolved By | Priority | Original Estimate | Remaining Work | Completed Work | Closed By | Closed Date
23 | Task | \Phase 3 | \80 Project Management | Development tasks break down - to use case level | dio | 2011-08-13 00:41 | 2011-08-19 00:41 | In progress |  | 1 | 12 | 8 | 4
28 | Task | \Phase 3 | \80 Project Management | To prepare Implementation Plan - down to use case level , include SIT | dio | 2011-08-13 00:41 | 2011-08-20 | In progress |  | 2 | 16 | 14 | 2
49 | Task | \Phase 3 | \80 Project Management | To configure email sent out for TFS, to notice team member upon changes/new assignment | dio | 2011-08-21 16:04 | 2011-08-21 16:04 | In progress |  | 2 | 8 | 8 | 0
29 | Task | \Phase 3 | \80 Project Management | To produce tasks assignment for Detailed Design Document - involved all team members | dio | 2011-08-13 17:53 | 2011-08-25 17:53 | In progress |  | 1 | 8 | 8 | 0
5 | Task | \Phase 2 | \80 Project Management | Review WBS to reflect latest change | dio | 2011-06-01 08:00 | 2011-09-01 17:00 | In progress |  | 1 | 8 | 7 | 1
35 | Task | \ | \80 Project Management | Looking for User | dio | 2011-01-01 00:41 | 2012-01-01 | Assigned |  | 4 | 8 | 8 | 0
21 | Task | \Phase 2 | \80 Project Management | To explore how to use SVN Bug tracker, and how to generate project reports from SVN | fengyan | 2011-08-13 00:41 | 2011-08-20 | In progress |  | 2 | 12 | 12
4 | Task | \Phase 2 | \30 Prototype\31 UI Prototype | To create User Interface Prototype draft 1 | hazel | 2011-06-05 08:00 | 2011-06-16 17:00 | In progress |  | 1 | 16 | 6 | 10
30 | Task | \Phase 3 | \60 Test | Produce Test Plan | jifa | 2011-08-13 00:41 | 2011-08-20 | In progress |  | 2 | 8 | 8 | 0
31 | Task | \Phase 3 | \60 Test | Produce Test Script | jifa | 2011-08-13 00:41 | 2011-08-20 | In progress |  | 2 | 8 | 8 | 0
32 | Task | \Phase 3 | \90 Quality Management | Create Review Form for all outstanding deliverables (High level Architecture Design, Prototype Study Report, Transition Strategy) | jifa | 2011-08-13 00:41 | 2011-08-20 | In progress |  | 2 | 8 | 8 | 0
39 | Task | \Phase 2 | \70 Report\72 Presentation Phase 2 | High level Design (Prepare for technical Question) Prototype (Technical Issue/Risk/learned….) | peishan | 2011-08-13 00:41 | 2011-08-20 | Resolved | peishan | 2 | 8 | 8 | 0
25 | Task | \Phase 3 | \90 Quality Management | Separate Internal Meeting Minutes and Quality Audit Meeting Minutes | peishan | 2011-08-13 00:41 | 2011-08-20 | In progress |  | 2 | 8 | 8 | 0
34 | Task | \Phase 3 | \90 Quality Management | Put the indexing file to some specific required folder(E.g Analysis) | peishan | 2011-08-13 00:41 | 2011-08-20 | In progress |  | 2 | 8 | 8 | 0
19 | Task | \Phase 2 | \80 Project Management | Get familiar with Team Foundation Server | se18team8s | 2011-08-13 00:41 | 2011-08-20 | In progress |  | 2 | 8 | 8 | 0
26 | Task | \Phase 3 | \90 Quality Management | Update the document reference to the document header beside the system name (the coming deliverables) | se18team8s | 2011-08-13 00:41 | 2011-08-20 | In progress |  | 2 | 8 | 8 | 0
33 | Task | \Phase 3 | \90 Quality Management | Update and Review all the UCRR | thida | 2011-08-13 00:41 | 2011-08-20 | In progress |  | 2 | 8 | 8 | 0
50 | Task | \Phase 3 | \30 Prototype | To complete prototype - get at least 1 use case working end-to-end (include AJAX-DWR) | zaw | 2011-08-21 | 2011-08-28 | Assigned |  | 2 | 50 | 50 | 0
1 | Task | \Phase 1 | \80 Project Management | Finish server setup | admin | 2011-05-21 08:00 | 2011-06-01 17:00 | Closed |  | 1 | 8 | 64 | 8 | admin | 2011-05-21 15:08
2 | Task | \Phase 2 | \80 Project Management | Test out the SQL and TFS server | admin | 2011-05-21 08:00 | 2011-06-08 17:00 | Closed |  | 2 | 0 | 0 | 112 | admin | 2011-05-28 23:35
3 | Task | \Phase 2 | \80 Project Management | To check with Zaw for MySQL setup | admin | 2011-05-21 08:00 | 2011-08-26 17:00 | Closed |  | 2 | 0 | 112 | 0 | dio | 2011-06-01 23:15
6 | Task | \Phase 2 | \30 Prototype\33 Prototype Study Report | To compare AJAX Framework for Prototype study report | zaw | 2011-08-13 00:41 | 2011-08-20 | Closed |  | 2 | 8 | 0 | 8 | dio | 2011-08-21 17:38
7 | Task | \Phase 2 | \30 Prototype\33 Prototype Study Report | To compare UI AJAX Prototype | peishan | 2011-06-01 08:00 | 2011-08-20 | Closed |  | 2 | 8 | 8 |  | dio | 2011-06-01 23:15
8 | Task | \Phase 2 | \30 Prototype\33 Prototype Study Report | To compare Framework Prototype for Prototype Study Report | zaw | 2011-06-01 08:00 | 2011-08-20 | Closed | zaw | 2 | 8 | 8 | 0 | dio | 2011-08-21 18:28
9 | Task | \Phase 2 | \30 Prototype\32 Architecture Prototye | To produce Data Access Layer Prototype | zaw | 2011-06-01 08:00 | 2011-06-14 17:00 | Closed |  | 2 | 16 | 0 | 16 | dio | 2011-08-21 17:23
10 | Task | \Phase 2 | \30 Prototype\33 Prototype Study Report | To compare Reporting Tool Prototype | dio | 2011-06-01 08:00 | 2011-08-20 | Closed | thida | 2 | 8 | 0 | 8 | dio | 2011-08-21 18:25
11 | Task | \Phase 2 | \30 Prototype\33 Prototype Study Report | To compare Database system for Prototype study report | jifa | 2011-08-13 00:41 | 2011-08-20 | Closed | jifa | 2 | 8 | 0 | 8 | dio | 2011-08-13 16:18
12 | Task | \Phase 2 | \30 Prototype | to produce End to end Prototype draft 1 | zaw | 2011-06-01 08:00 | 2011-06-14 17:00 | Closed |  | 1 | 16 | 0 | 16 | dio | 2011-08-21 17:23
13 | Task | \Phase 2 | \30 Prototype\33 Prototype Study Report | To consolidate all parts to produce prototype study report | peishan | 2011-06-01 08:00 | 2011-08-20 | Closed |  | 2 | 16 | 0 | 16 | dio | 2011-08-21 17:23
14 | Task | \Phase 2 | \30 Prototype\31 UI Prototype | To review UI draft 1 from Jifa | dio | 2011-06-01 08:00 | 2011-06-14 17:00 | Closed |  | 2 | 8 | 0 | 8 | dio | 2011-08-14 17:57
15 | Task | \Phase 2 | \80 Project Management | To start WBS tasks breakdown , split tasks among team | dio | 2011-07-01 18:56 | 2011-08-30 18:56 | Closed |  | 1 | 0 | 0 | 12 | dio | 2011-08-14 17:57
17 | Task | \Phase 2 | \30 Prototype\32 Architecture Prototye | To review Database system for Prototype study report from Jifa | dio | 2011-06-01 17:47 | 2011-07-07 17:47 | Closed | dio | 2 | 4 | 4 | 0 | dio | 2011-08-13 17:48
18 | Task | \Phase 2 | \30 Prototype | Testing review my report tool | dio | 2011-08-14 00:24 | 2011-08-14 00:24 | Closed | thida | 1 | 8 | 0 | 8 | dio | 2011-06-11 16:48
20 | Task | \Phase 2 | \80 Project Management | To explorer TFS template, modify the project template to match ISS and project context | dio | 2011-08-13 00:23 | 2011-08-14 00:23 | Closed |  | 2 | 8 | 0 | 8 | dio | 2011-08-14 17:57
22 | Task | \Phase 2 | \20 Analysis\22 Use Case Realization Report (Analysis) | Produce UCRR - Analysis | se18team8s | 2011-08-13 00:41 | 2011-08-20 | Closed |  | 1 | 24 | 0 | 24 | dio | 2011-08-21 17:42
24 | Task | \Phase 2 | \20 Analysis | Combine UCMS, UCRR into 1 document | thida | 2011-08-13 00:41 | 2011-08-20 | Closed | dio | 2 | 8 | 0 | 8 | dio | 2011-08-21 18:14
27 | Task | \Phase 2 | \80 Project Management | For the task tracking, use the TFS to generate the progress report and check in to the SVN | dio | 2011-08-13 16:31 | 2011-08-20 16:31 | Closed |  | 2 | 8 | 0 | 8 | dio | 2011-08-21 17:34
36 | Task | \Phase 2 | \70 Report\72 Presentation Phase 2 | Presentation - Project Background (2 Slides) | dio | 2011-08-13 00:41 | 2011-08-20 | Closed |  | 2 | 8 | 0 | 8 | dio | 2011-08-21 17:34
37 | Task | \Phase 2 | \70 Report\72 Presentation Phase 2 | Presentation - Global Use Case Modelling Picture | dio | 2011-08-13 00:41 | 2011-08-20 | Closed |  | 2 | 8 | 0 | 8 | dio | 2011-08-21 17:34
38 | Task | \Phase 2 | \70 Report\72 Presentation Phase 2 | Select Two use case for Demo Decompose / Explain for chosen use cases | dio | 2011-08-13 00:41 | 2011-08-20 | Closed |  | 2 | 8 | 8 | 0 | dio | 2011-08-21 17:34
40 | Task | \Phase 2 | \70 Report\72 Presentation Phase 2 | Progress (Which task takes longer… Implementation Plan (what u r going to finish….) | dio | 2011-08-13 00:41 | 2011-08-20 | Closed |  | 2 | 8 | 8 | 0 | dio | 2011-08-21 17:34
42 | Task | \Phase 1 | \80 Project Management | To modify TFS Template to match MTECH workflow | dio | 2011-08-13 19:01 | 2011-08-14 19:01 | Closed |  | 1 | 4 | 0 | 4 | dio | 2011-08-21 17:06

## VSTS_ValidationWS_1 (hidden)
value doesn't matter | value doesn't matter | value doesn't matter | value doesn't matter | admin | admin | admin | admin | admin | admin | admin | admin | admin | admin | admin | Active | 1 | admin | Active | 1 | admin | Active | 1 | admin | Active | 1 | admin | Active | admin | Active | 1 | admin | Active | 1 | admin | Assigned | 1 | admin | Closed | 1 | Bug | admin | Active | 1 | \ | \ | admin | Assigned | 1 | admin | admin | admin | admin | admin | admin | admin | admin | Closed | Closed | Assigned
readOnlyTestRange_@ | readOnlyTestRange_0 | readOnlyTestRange_dd-MMM-yy h:mm AM/PM | readOnlyTestRange_General | dio | dio | dio | dio | dio | dio | dio | dio | dio | dio | dio | Closed | 2 | dio | Closed | 2 | dio | Closed | 2 | dio | Closed | 2 | dio | Closed | dio | Closed | 2 | dio | Closed | 2 | dio | Closed | 2 | dio | Design | 2 | Change Request | dio | Closed | 2 | \10 Requirements | \Phase 1 | dio | Closed | 2 | dio | dio | dio | dio | dio | dio | dio | dio | In progress | In progress | Closed
|  |  |  | fengyan | fengyan | fengyan | fengyan | fengyan | fengyan | fengyan | fengyan | fengyan | fengyan | fengyan | Proposed | 3 | fengyan | Proposed | 3 | fengyan | Proposed | 3 | fengyan | Proposed | 3 | fengyan | Resolved | fengyan | Proposed | 3 | fengyan | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Shared Steps_System.State | 3 | fengyan | In progress | 3 | fengyan | Ready | 3 | Issue | fengyan | Proposed | 3 | \20 Analysis | \Phase 2 | fengyan | In progress | 3 | fengyan | fengyan | fengyan | fengyan | fengyan | fengyan | fengyan | fengyan | Resolved | VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_50-5B-D0-C6-4D-02-A8-6F-40-65-26-EB-25-5E-77-D6-47-52-6D-6C | In progress
|  |  |  | hazel | hazel | hazel | hazel | hazel | hazel | hazel | hazel | hazel | hazel | hazel | Resolved | 4 | hazel | Resolved | 4 | hazel | Resolved | 4 | hazel | Resolved | 4 | hazel | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Review_System.State | hazel | Resolved | 4 | hazel |  | 4 | hazel | Resolved | 4 | hazel | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Test Case_System.State | 4 | Requirement | hazel | Resolved | 4 | \20 Analysis\21 Use Case Model Survey | \Phase 3 | hazel | Resolved | 4 | hazel | hazel | hazel | hazel | hazel | hazel | hazel | hazel | VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_6F-C6-D8-EB-43-26-13-F5-A3-D3-8B-09-48-94-22-7A-77-AF-E5-C2 |  | VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_8B-D1-53-A2-A6-FB-4F-03-24-65-B4-29-73-CC-D1-C9-B6-3C-6A-90
|  |  |  | jifa | jifa | jifa | jifa | jifa | jifa | jifa | jifa | jifa | jifa | jifa | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Bug_System.State | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Bug_Microsoft.VSTS.Common.Priority | jifa | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Change Request_System.State | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Change Request_Microsoft.VSTS.Common.Priority | jifa | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Issue_System.State | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Issue_Microsoft.VSTS.Common.Priority | jifa | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Requirement_System.State | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Requirement_Microsoft.VSTS.Common.Priority | jifa |  | jifa | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Risk_System.State | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Risk_Microsoft.VSTS.Common.Priority | jifa |  | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Shared Steps_Microsoft.VSTS.Common.Priority | jifa | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Task_System.State | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Task_Microsoft.VSTS.Common.Priority | jifa |  | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Test Case_Microsoft.VSTS.Common.Priority | Review | jifa | Assigned | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Microsoft.VSTS.Common.Priority | \20 Analysis\22 Use Case Realization Report (Analysis) | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_System.IterationPath | jifa | VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_9F-F6-0F-1C-08-6A-BA-DC-02-F0-E1-1F-9D-C4-DD-F3-E1-46-6F-4A | VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_A9-74-3C-60-20-83-BF-D2-70-44-DA-6E-AF-8C-55-96-9A-24-CE-B3 | jifa | jifa | jifa | jifa | jifa | jifa | jifa | jifa
|  |  |  | LOCAL SERVICE | LOCAL SERVICE | LOCAL SERVICE | LOCAL SERVICE | LOCAL SERVICE | LOCAL SERVICE | LOCAL SERVICE | LOCAL SERVICE | LOCAL SERVICE | LOCAL SERVICE | LOCAL SERVICE |  |  | LOCAL SERVICE |  |  | LOCAL SERVICE |  |  | LOCAL SERVICE |  |  | LOCAL SERVICE |  | LOCAL SERVICE |  |  | LOCAL SERVICE |  |  | LOCAL SERVICE |  |  | LOCAL SERVICE |  |  | Risk | LOCAL SERVICE | In progress |  | \30 Prototype |  | LOCAL SERVICE |  |  | LOCAL SERVICE | LOCAL SERVICE | LOCAL SERVICE | LOCAL SERVICE | LOCAL SERVICE | LOCAL SERVICE | LOCAL SERVICE | LOCAL SERVICE
|  |  |  | peishan | peishan | peishan | peishan | peishan | peishan | peishan | peishan | peishan | peishan | peishan |  |  | peishan |  |  | peishan |  |  | peishan |  |  | peishan |  | peishan |  |  | peishan |  |  | peishan |  |  | peishan |  |  | Shared Steps | peishan | Design |  | \30 Prototype\31 UI Prototype |  | peishan |  |  | peishan | peishan | peishan | peishan | peishan | peishan | peishan | peishan
|  |  |  | se18team8s | se18team8s | se18team8s | se18team8s | se18team8s | se18team8s | se18team8s | se18team8s | se18team8s | se18team8s | se18team8s |  |  | se18team8s |  |  | se18team8s |  |  | se18team8s |  |  | se18team8s |  | se18team8s |  |  | se18team8s |  |  | se18team8s |  |  | se18team8s |  |  | Task | se18team8s | Ready |  | \30 Prototype\32 Architecture Prototye |  | se18team8s |  |  | se18team8s | se18team8s | se18team8s | se18team8s | se18team8s | se18team8s | se18team8s | se18team8s
|  |  |  | thida | thida | thida | thida | thida | thida | thida | thida | thida | thida | thida |  |  | thida |  |  | thida |  |  | thida |  |  | thida |  | thida |  |  | thida |  |  | thida |  |  | thida |  |  | Test Case | thida | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_System.State |  | \30 Prototype\33 Prototype Study Report |  | thida |  |  | thida | thida | thida | thida | thida | thida | thida | thida
|  |  |  | zaw | zaw | zaw | zaw | zaw | zaw | zaw | zaw | zaw | zaw | zaw |  |  | zaw |  |  | zaw |  |  | zaw |  |  | zaw |  | zaw |  |  | zaw |  |  | zaw |  |  | zaw |  |  | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_System.WorkItemType | zaw |  |  | \40 Design |  | zaw |  |  | zaw | zaw | zaw | zaw | zaw | zaw | zaw | zaw
|  |  |  | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Bug_Microsoft.VSTS.Common.ClosedBy | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Change Request_Microsoft.VSTS.Common.ClosedBy | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Issue_Microsoft.VSTS.Common.ClosedBy | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Requirement_Microsoft.VSTS.Common.ClosedBy | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Review_Microsoft.VSTS.Common.ClosedBy | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Risk_Microsoft.VSTS.Common.ClosedBy | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Shared Steps_Microsoft.VSTS.Common.ClosedBy | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Task_Microsoft.VSTS.Common.ClosedBy | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Test Case_Microsoft.VSTS.Common.ClosedBy | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Microsoft.VSTS.Common.ClosedBy | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Bug_System.AssignedTo |  |  | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Change Request_System.AssignedTo |  |  | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Issue_System.AssignedTo |  |  | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Requirement_System.AssignedTo |  |  | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Review_System.AssignedTo |  | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Risk_System.AssignedTo |  |  | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Shared Steps_System.AssignedTo |  |  | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Task_System.AssignedTo |  |  | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Test Case_System.AssignedTo |  |  |  | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_System.AssignedTo |  |  | \40 Design\41 High level architecture |  | VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_63-3D-6E-FD-05-A5-E3-0A-3D-3B-27-25-0E-09-89-A2-24-50-7D-FA |  |  | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Bug_Microsoft.VSTS.Common.ResolvedBy | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Change Request_Microsoft.VSTS.Common.ResolvedBy | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Issue_Microsoft.VSTS.Common.ResolvedBy | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Requirement_Microsoft.VSTS.Common.ResolvedBy | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Review_Microsoft.VSTS.Common.ResolvedBy | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Risk_Microsoft.VSTS.Common.ResolvedBy | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Task_Microsoft.VSTS.Common.ResolvedBy | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Microsoft.VSTS.Common.ResolvedBy
\40 Design\42 Detailed Design Specficiations
\50 Build
\50 Build\51 Security and Admin
\50 Build\52 Volunteer Management
\50 Build\53 Staff Management
\50 Build\54 Project Management
\50 Build\55 Itinerary Management
\50 Build\56 Reporting
\60 Test
\60 Test\61 Unit test
\60 Test\62 SIT
\60 Test\63 UAT
\70 Report
\70 Report\71 Presentation Phase 1
\70 Report\72 Presentation Phase 2
\70 Report\73 Presentation Phase 3
\70 Report\74 End project report
\80 Project Management
\90 Quality Management
all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_System.AreaPath