## 1.Task
Project: MTECH SE18 TEAM8S Server: team8s.myvnc.com\DefaultCollection Query: All tasks List type: Flat
ID | Iteration Path | Area Path | Work Item Type | Assigned To | Priority | Title | Description | State | History | Original Estimate | Completed Work | Blocked | Reason | Triage | Start Date | Finish Date | Resolved By | Resolved Date | Remaining Work
1 | \Phase 1 | \80 Project Management | Task | admin | 1 | Finish server setup | To finish TFS, (done) MS SQL, (done) MySQL, (done) Java (done) Tomcat (done) Jtrac setup (N/A) | Closed |  | 8 | 8 | No | Complete and Does Not Require Review/Test | Triaged | 2011-05-21 08:00 | 2011-06-01 17:00 |  |  | 64
2 | \Phase 2 | \50 Build\50 UI design | Task | admin | 2 | Test out the SQL and TFS server | Please try to test the function of TFS & SQL | Closed |  | 0 | 112 | No | Complete and Does Not Require Review/Test | Triaged | 2011-05-21 08:00 | 2011-06-08 17:00 |  |  | 0
3 | \Phase 2 | \80 Project Management | Task | admin | 2 | To check with Zaw for MySQL setup | To check with Zaw for MySQL setup | Closed |  | 0 | 0 | No | Complete and Does Not Require Review/Test | Pending | 2011-05-21 08:00 | 2011-08-26 17:00 |  |  | 112
23 | \Phase 3 | \80 Project Management | Task | dio | 1 | Development tasks break down - to use case level | Development tasks break down - to use case level (done - pending checked in SVN ) To review the draft WBS breakdown from Peishan (checked into SVN) (done) | In progress |  | 12 | 4 | No | Investigate | Pending | 2011-08-13 00:41 | 2011-08-19 00:41 |  |  | 8
28 | \Phase 3 | \80 Project Management | Task | dio | 1 | To prepare Implementation Plan - down to use case level , include SIT | Prepare Implementation Plan - in detailed Focus on : - prototype completed solution - integration phases - DWR usage ? OK or not ? | In progress |  | 16 | 2 | No | Investigate | Pending | 2011-08-13 00:41 | 2011-08-20 |  |  | 14
49 | \Phase 3 | \80 Project Management | Task | dio | 2 | To configure email sent out for TFS, to notice team member upon changes/new assignment | To configure email sent out for TFS for these items: - Task created - Bug update - Review request | In progress |  | 8 | 0 | No | Investigate | Pending | 2011-08-21 16:04 | 2011-08-21 16:04 |  |  | 8
29 | \Phase 3 | \80 Project Management | Task | dio | 1 | To produce tasks assignment for Detailed Design Document - involved all team members | To produce Detailed Design Document - all team members | In progress |  | 8 | 0 | No | Investigate | Pending | 2011-08-13 17:53 | 2011-08-25 17:53 |  |  | 8
5 | \Phase 2 | \80 Project Management | Task | dio | 1 | Review WBS to reflect latest change | To review WBS and Project plan to reflect latest status | In progress |  | 8 | 1 | No | Investigate | Pending | 2011-06-01 08:00 | 2011-09-01 17:00 |  |  | 7
35 | \ | \80 Project Management | Task | dio | 4 | Looking for User | To continue looking for potential user | Assigned |  | 8 | 0 | No | Investigation Complete | Pending | 2011-01-01 00:41 | 2012-01-01 |  |  | 8
10 | \Phase 2 | \30 Prototype\33 Prototype Study Report | Task | dio | 2 | To compare Reporting Tool Prototype | To compare Reporting Tool Prototype | Closed |  | 8 | 8 | No | Complete and Does Not Require Review/Test | Pending | 2011-06-01 08:00 | 2011-08-20 | thida |  | 0
14 | \Phase 2 | \30 Prototype\31 UI Prototype | Task | dio | 2 | To review UI draft 1 from Jifa | To review UI draft 1 from Jifa , in SVN - to suggest integrated view (all page with footer / header) - to suggest navigation - to suggest frame/ button/ layout / CSS usage | Closed |  | 8 | 8 | No | Complete and Does Not Require Review/Test | Triaged | 2011-06-01 08:00 | 2011-06-14 17:00 |  |  | 0
15 | \Phase 2 | \80 Project Management | Task | dio | 1 | To start WBS tasks breakdown , split tasks among team | To start WBS tasks breakdown , split tasks among team - Split UCRR tasks for all members - Split High level specs among Zaw, Feng Yan, Peishan and Thida - To get status update before 24 June 2011 | Closed |  | 0 | 12 | No | Complete and Does Not Require Review/Test | Triaged | 2011-07-01 18:56 | 2011-08-30 18:56 |  |  | 0
17 | \Phase 2 | \30 Prototype\32 Architecture Prototye | Task | dio | 2 | To review Database system for Prototype study report from Jifa | To review Database system for Prototype study report from Jifa | Closed |  | 4 | 0 | No | Review/Test Passed | Pending | 2011-06-01 17:47 | 2011-07-07 17:47 | dio | 2011-08-13 17:48 | 4
18 | \Phase 2 | \30 Prototype | Task | dio | 1 | Testing review my report tool | pls check for me | Closed |  | 8 | 8 | No | Review/Test Passed | Triaged | 2011-08-14 00:24 | 2011-08-14 00:24 | thida | 2011-06-11 16:48 | 0
20 | \Phase 2 | \80 Project Management | Task | dio | 2 | To explorer TFS template, modify the project template to match ISS and project context | To customize TFS template with task workflow, item workflow that match the ISS project waterfall model. For e.g: To add more discipline into Tasks | Closed |  | 8 | 8 | No | Complete and Does Not Require Review/Test | Pending | 2011-08-13 00:23 | 2011-08-14 00:23 |  |  | 0
27 | \Phase 2 | \80 Project Management | Task | dio | 2 | For the task tracking, use the TFS to generate the progress report and check in to the SVN | For the task tracking, use the TFS to generate the progress report and check in to the SVN | Closed |  | 8 | 8 | No | Complete and Does Not Require Review/Test | Pending | 2011-08-13 16:31 | 2011-08-20 16:31 |  |  | 0
36 | \Phase 2 | \70 Report\72 Presentation Phase 2 | Task | dio | 2 | Presentation - Project Background (2 Slides) | To prepare slides for presentation (project background) | Closed |  | 8 | 8 | No | Complete and Does Not Require Review/Test | Pending | 2011-08-13 00:41 | 2011-08-20 |  |  | 0
37 | \Phase 2 | \70 Report\72 Presentation Phase 2 | Task | dio | 2 | Presentation - Global Use Case Modelling Picture | To create UCMS for presentation | Closed |  | 8 | 8 | No | Complete and Does Not Require Review/Test | Pending | 2011-08-13 00:41 | 2011-08-20 |  |  | 0
38 | \Phase 2 | \70 Report\72 Presentation Phase 2 | Task | dio | 2 | Select Two use case for Demo Decompose / Explain for chosen use cases | To select 2 use cases for Phase 2 presentation | Closed |  | 8 | 0 | No | Complete and Does Not Require Review/Test | Pending | 2011-08-13 00:41 | 2011-08-20 |  |  | 8
40 | \Phase 2 | \70 Report\72 Presentation Phase 2 | Task | dio | 2 | Progress (Which task takes longer… Implementation Plan (what u r going to finish….) | To show the current progress of Phase 2 | Closed |  | 8 | 0 | No | Complete and Does Not Require Review/Test | Pending | 2011-08-13 00:41 | 2011-08-20 |  |  | 8
42 | \Phase 1 | \80 Project Management | Task | dio | 1 | To modify TFS Template to match MTECH workflow | - Created Phases & Iterations to match MTECH architecture | Closed |  | 4 | 4 | No | Rejected | Pending | 2011-08-13 19:01 | 2011-08-14 19:01 |  |  | 0
51 | \Phase 3 | \50 Build\50 UI design | Task | dio | 2 | To produce completed UI design of the whole system (include all pages) - prepare before development start | Requirements: - All UI design for all pages - Design for main page, home screen - Involve navigation and flow | Assigned |  | 30 | 0 | No | New | Pending | 2011-08-21 22:30 | 2011-08-28 22:30 |  |  | 30
21 | \Phase 2 | \80 Project Management | Task | fengyan | 2 | To explore how to use SVN Bug tracker, and how to generate project reports from SVN | - To explore how to use SVN Bug tracker, and how to generate project reports from SVN. For e.g: - How to integrate SVN bug tracker into Eclipse - How to generate report on active/closed/pending bugs - Generate report on code coverage during testing stage - Generate report on requirements coverage during testing stage | In progress |  | 12 | 1 | No | Investigate | Pending | 2011-08-13 00:41 | 2011-08-20 |  |  | 11
4 | \Phase 2 | \30 Prototype\31 UI Prototype | Task | hazel | 1 | To create User Interface Prototype draft 1 | To prepare User Interface Prototype for putative user to review, by 28th May 2011 | Closed |  | 16 | 10 | No | Complete and Does Not Require Review/Test | Triaged | 2011-06-05 08:00 | 2011-06-16 17:00 | hazel | 2011-08-21 22:30 | 6
30 | \Phase 3 | \60 Test | Task | jifa | 2 | Produce Test Plan | To produce detailed Test Plan (maybe based on Unit 7 materials) | In progress |  | 8 | 0 | No | Investigate | Pending | 2011-08-13 00:41 | 2011-08-20 |  |  | 8
31 | \Phase 3 | \60 Test | Task | jifa | 2 | To produce Full Test Script for all use cases | To produce Full Test Script for all use cases | In progress |  | 8 | 0 | No | Investigate | Pending | 2011-08-13 00:41 | 2011-08-20 |  |  | 8
32 | \Phase 3 | \90 Quality Management | Task | jifa | 2 | Create Review Form for all outstanding deliverables (High level Architecture Design, Prototype Study Report, Transition Strategy) | Create Review Form for all outstanding deliverables (High level Architecture Design, Prototype Study Report, Transition Strategy) | In progress |  | 8 | 0 | No | Investigate | Pending | 2011-08-13 00:41 | 2011-08-20 |  |  | 8
11 | \Phase 2 | \30 Prototype\33 Prototype Study Report | Task | jifa | 2 | To compare Database system for Prototype study report | To compare Database system for Prototype study report | Closed |  | 8 | 8 | No | Review/Test Passed | Triaged | 2011-08-13 00:41 | 2011-08-20 | jifa | 2011-06-10 08:59 | 0
39 | \Phase 2 | \70 Report\72 Presentation Phase 2 | Task | peishan | 2 | High level Design (Prepare for technical Question) Prototype (Technical Issue/Risk/learned….) | High level Design (Prepare for technical Question) Prototype (Technical Issue/Risk/learned….) | Resolved |  | 8 | 0 | No | Complete and Requires Review/Test | Pending | 2011-08-13 00:41 | 2011-08-20 | peishan | 2011-08-21 18:26 | 8
25 | \Phase 3 | \90 Quality Management | Task | peishan | 2 | Separate Internal Meeting Minutes and Quality Audit Meeting Minutes | Separate Internal Meeting Minutes and Quality Audit Meeting Minutes | In progress |  | 8 | 0 | No | Investigate | Pending | 2011-08-13 00:41 | 2011-08-20 |  |  | 8
34 | \Phase 3 | \90 Quality Management | Task | peishan | 3 | Put the indexing file to some specific required folder(E.g Analysis) | Put the indexing file to some specific required folder(E.g Analysis) | In progress |  | 8 | 0 | No | Investigate | Pending | 2011-08-13 00:41 | 2011-08-20 |  |  | 8
7 | \Phase 2 | \30 Prototype\33 Prototype Study Report | Task | peishan | 2 | To compare UI AJAX Prototype | To compare UI AJAX Prototype for Prototype Study Report | Closed |  | 8 |  | No | Cancelled | Triaged | 2011-06-01 08:00 | 2011-08-20 |  |  | 8
13 | \Phase 2 | \30 Prototype\33 Prototype Study Report | Task | peishan | 2 | To consolidate all parts to produce prototype study report | To consolidate all parts to product prototype study report | Closed |  | 16 | 16 | No | Complete and Does Not Require Review/Test | Pending | 2011-06-01 08:00 | 2011-08-20 |  |  | 0
19 | \Phase 2 | \80 Project Management | Task | se18team8s | 2 | Get familiar with Team Foundation Server - know how to manage task/bug/issue status | Get familiar with Team Foundation Server - Know how to create/update/close tasks - Know how to create/update/close requirement / assignment | In progress |  | 8 | 0 | No | Accepted | Pending | 2011-08-13 00:41 | 2011-08-20 |  |  | 8
26 | \Phase 3 | \90 Quality Management | Task | se18team8s | 2 | Update the document reference to the document header beside the system name (the coming deliverables) | Update the document reference to the document header beside the system name (the coming deliverables) | In progress |  | 8 | 0 | No | Investigate | Pending | 2011-08-13 00:41 | 2011-08-20 |  |  | 8
22 | \Phase 2 | \20 Analysis\22 Use Case Realization Report (Analysis) | Task | se18team8s | 1 | Produce UCRR - Analysis | Complete UCRR (analysis ) for these Use case : 1. Login / Logout 2. Change password 3. Forget password 4. Register User Account 5. Update Profile 7. Raise Project Interest 8. Proposa Project 9. Post Experience 10. Post Feedback 11. Request for Certificate | Closed |  | 24 | 24 | No | Complete and Does Not Require Review/Test | Triaged | 2011-08-13 00:41 | 2011-08-20 |  |  | 0
33 | \Phase 3 | \90 Quality Management | Task | thida | 1 | Update and Review all the UCRR (Analysis) | Update and Review all the UCRR (analysis) correctness | In progress |  | 8 | 0 | No | Investigate | Pending | 2011-08-13 00:41 | 2011-08-24 |  |  | 8
24 | \Phase 2 | \20 Analysis | Task | thida | 2 | Combine UCMS, UCRR into 1 document | Combine UCMS, UCRR into 1 document | Closed |  | 8 | 8 | No | Review/Test Passed | Pending | 2011-08-13 00:41 | 2011-08-20 | dio | 2011-08-21 18:14 | 0
50 | \Phase 3 | \30 Prototype | Task | zaw | 2 | To complete prototype - get at least 1 use case working end-to-end (include AJAX-DWR) | To complete prototype - get at least 1 use case working end-to-end (include AJAX-DWR) | In progress |  | 50 | 0 | No | Accepted | Pending | 2011-08-22 | 2011-08-29 |  |  | 50
6 | \Phase 2 | \30 Prototype\33 Prototype Study Report | Task | zaw | 2 | To compare AJAX Framework for Prototype study report | To compare AJAX Framework for Prototype study report To be use in Prototype study report | Closed |  | 8 | 8 | No | Complete and Does Not Require Review/Test | Pending | 2011-08-13 00:41 | 2011-08-20 |  |  | 0
8 | \Phase 2 | \30 Prototype\33 Prototype Study Report | Task | zaw | 2 | To compare Framework Prototype for Prototype Study Report | To compare Framework Prototype for Prototype Study Report | Closed |  | 8 | 0 | No | Review/Test Passed | Pending | 2011-06-01 08:00 | 2011-08-20 | zaw | 2011-08-21 18:27 | 8
9 | \Phase 2 | \30 Prototype\32 Architecture Prototye | Task | zaw | 2 | To produce Data Access Layer Prototype | To produce Data Access Layer Prototype | Closed |  | 16 | 16 | No | Complete and Does Not Require Review/Test | Pending | 2011-06-01 08:00 | 2011-06-14 17:00 |  |  | 0
12 | \Phase 2 | \30 Prototype | Task | zaw | 1 | to produce End to end Prototype draft 1 | to produce End to end Prototype draft 1 | Closed |  | 16 | 16 | No | Complete and Does Not Require Review/Test | Pending | 2011-06-01 08:00 | 2011-06-14 17:00 |  |  | 0

## 2.Bug
Project: MTECH SE18 TEAM8S Server: team8s.myvnc.com\DefaultCollection Query: All bugs List type: Flat
ID | Title | Area Path | Assigned To | State | Severity | Priority | Resolved By | Resolved Date | Activated By | Blocked | Iteration Path | Original Estimate | Reason | Symptom | Triage | Work Item Type
41 | TST - Not a bug | \50 Build | dio | Closed | 4 - Low | 4 | dio | 2011-08-22 14:35 | dio | No | \ |  | Verified | Testing creating a new bug | Triaged | Bug
43 | System cannot start | \50 Build | dio | Resolved | 4 - Low | 4 | dio | 2011-08-22 14:36 | dio | No | \ |  | Fixed | The system crashed ! | More Info | Bug

## VSTS_ValidationWS_1 (hidden)
value doesn't matter | value doesn't matter | 2011-08-22 14:35 | value doesn't matter | admin | admin | Active | admin | 1 | admin | admin | Active | admin | 1 | admin | admin | Active | admin | 1 | admin | admin | Active | admin | 1 | admin | admin | Active | admin | admin | admin | Active | admin | 1 | admin | admin | admin | admin | admin | Active | admin | Active | admin | Active | admin | Active | admin | Active | admin | Active | admin | Active | admin | Assigned | admin | Closed | admin | Active | Active | 1 | admin | admin | Assigned | admin | 1 | admin | admin | Closed | 1 | admin | admin | admin | Active | admin | 1 | \ | \ | admin | Assigned | 1 | Closed | Assigned | admin | admin | Active | \ | 1 - Critical | 1 - Critical | 1 - Critical | 1 - Critical | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | admin | admin | admin | admin | admin | admin | admin | admin | 1 - Critical | 1 | Active | Active | Closed | Bug | admin | admin | admin | admin | admin | admin | No | No | No | No | No | No | \ | Approved | Abandoned | Accepted | Abandoned | Accepted (as is) | Accepted (won't mitigate) | Deferred | Accepted | Completed | Approved | Info Received | Info Received | Info Received | Info Received | Info Received | Info Received | Bug | No | Info Received | No | No | No | No | No | No | Approved | Abandoned | Accepted | Abandoned | Accepted (as is) | Accepted (won't mitigate) | Deferred | Accepted | Completed | Approved | Info Received | Info Received | Info Received | Info Received | Info Received | Info Received | No | Info Received | Assigned | Bug | New | Accepted
readOnlyTestRange_@ | readOnlyTestRange_0 | readOnlyTestRange_dd-MMM-yy h:mm AM/PM | readOnlyTestRange_General | dio | dio | Closed | dio | 2 | dio | dio | Closed | dio | 2 | dio | dio | Closed | dio | 2 | dio | dio | Closed | dio | 2 | dio | dio | Closed | dio | dio | dio | Closed | dio | 2 | dio | dio | dio | dio | dio | Closed | dio | Closed | dio | Closed | dio | Closed | dio | Closed | dio | Closed | dio | Closed | dio | Closed | dio | Design | dio | Closed | Closed | 2 | dio | dio | Closed | dio | 2 | dio | dio | Design | 2 | dio | dio | dio | Closed | dio | 2 | \10 Requirements | \Phase 1 | dio | Closed | 2 | In progress | Closed | dio | dio | Closed | \10 Requirements | 2 - High | 2 - High | 2 - High | 2 - High | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | dio | dio | dio | dio | dio | dio | dio | dio | 2 - High | 2 | Proposed | Closed | In progress | Change Request | dio | dio | dio | dio | dio | dio | Yes | Yes | Yes | Yes | Yes | Yes | \Phase 1 | As Designed | Accepted | Closed in Error | Accepted | Accepted with Major Changes | Closed in Error | Duplicate | Cancelled | Deferred | As Designed | More Info | More Info | More Info | More Info | More Info | More Info | Change Request | Yes | More Info | Yes | Yes | Yes | Yes | Yes | Yes | As Designed | Accepted | Closed in Error | Accepted | Accepted with Major Changes | Closed in Error | Duplicate | Cancelled | Deferred | As Designed | More Info | More Info | More Info | More Info | More Info | More Info | Yes | More Info | VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_59-97-B9-3F-37-D5-23-8F-BD-31-44-27-81-8F-74-99-3A-32-51-FA | Change Request | VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_EC-0F-7A-13-B7-B8-F1-00-EB-63-A3-B5-07-10-E1-15-11-B0-2B-46 | Investigate
|  |  |  | fengyan | fengyan | Proposed | fengyan | 3 | fengyan | fengyan | Proposed | fengyan | 3 | fengyan | fengyan | Proposed | fengyan | 3 | fengyan | fengyan | Proposed | fengyan | 3 | fengyan | fengyan | Resolved | fengyan | fengyan | fengyan | Proposed | fengyan | 3 | fengyan | fengyan | fengyan | fengyan | fengyan | Proposed | fengyan | Proposed | fengyan | Proposed | fengyan | Proposed | fengyan | Resolved | fengyan | Proposed | fengyan | all_VSTS_d9cdb1c3_3b79_4351_91a7_e256f1cd916d_Shared Steps_System.State | fengyan | In progress | fengyan | Ready | fengyan | Proposed | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Shared Steps_System.State | 3 | fengyan | fengyan | In progress | fengyan | 3 | fengyan | fengyan | Ready | 3 | fengyan | fengyan | fengyan | Proposed | fengyan | 3 | \20 Analysis | \Phase 2 | fengyan | In progress | 3 | VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_50-5B-D0-C6-4D-02-A8-6F-40-65-26-EB-25-5E-77-D6-47-52-6D-6C | In progress | fengyan | fengyan | VSTS_d9cdb1c3_3b79_4351_91a7_e256f1cd916d_C0-8B-87-81-67-52-71-76-29-2A-B8-4D-FB-D4-D6-6F-1E-E5-D9-2A | \20 Analysis | 3 - Medium | 3 - Medium | 3 - Medium | 3 - Medium | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | fengyan | fengyan | fengyan | fengyan | fengyan | fengyan | fengyan | fengyan | 3 - Medium | 3 | Resolved | Resolved | Resolved | Issue | fengyan | fengyan | fengyan | fengyan | fengyan | fengyan | all_VSTS_d9cdb1c3_3b79_4351_91a7_e256f1cd916d_Bug_Microsoft.VSTS.CMMI.Blocked | all_VSTS_d9cdb1c3_3b79_4351_91a7_e256f1cd916d_Change Request_Microsoft.VSTS.CMMI.Blocked | all_VSTS_d9cdb1c3_3b79_4351_91a7_e256f1cd916d_Requirement_Microsoft.VSTS.CMMI.Blocked | all_VSTS_d9cdb1c3_3b79_4351_91a7_e256f1cd916d_Risk_Microsoft.VSTS.CMMI.Blocked | all_VSTS_d9cdb1c3_3b79_4351_91a7_e256f1cd916d_Task_Microsoft.VSTS.CMMI.Blocked | all_VSTS_d9cdb1c3_3b79_4351_91a7_e256f1cd916d_Microsoft.VSTS.CMMI.Blocked | \Phase 2 | Build Failure | Closed in Error | Investigate | Closed in Error | Accepted with Minor Changes | Eliminated | New | Closed in Error | Duplicate | Build Failure | Pending | Pending | Pending | Pending | Pending | Pending | Issue | VSTS_d9cdb1c3_3b79_4351_91a7_e256f1cd916d_20-B5-FF-1A-30-9C-85-1A-A5-5F-41-8C-5C-7D-57-1C-5E-01-21-9C | Pending | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Bug_Microsoft.VSTS.CMMI.Blocked | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Change Request_Microsoft.VSTS.CMMI.Blocked | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Requirement_Microsoft.VSTS.CMMI.Blocked | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Risk_Microsoft.VSTS.CMMI.Blocked | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Task_Microsoft.VSTS.CMMI.Blocked | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Microsoft.VSTS.CMMI.Blocked | Build Failure | Closed in Error | Investigate | Closed in Error | Accepted with Minor Changes | Eliminated | New | Closed in Error | Duplicate | Build Failure | Pending | Pending | Pending | Pending | Pending | Pending | VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_20-B5-FF-1A-30-9C-85-1A-A5-5F-41-8C-5C-7D-57-1C-5E-01-21-9C | Pending |  | Issue |  | VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_EA-55-57-01-F4-8D-44-13-1B-D3-F3-2D-ED-63-76-D2-FE-33-B2-DB
|  |  |  | hazel | hazel | Resolved | hazel | 4 | hazel | hazel | Resolved | hazel | 4 | hazel | hazel | Resolved | hazel | 4 | hazel | hazel | Resolved | hazel | 4 | hazel | hazel | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Review_System.State | hazel | hazel | hazel | Resolved | hazel | 4 | hazel | hazel | hazel | hazel | hazel | Resolved | hazel | Resolved | hazel | Resolved | hazel | Resolved | hazel | all_VSTS_d9cdb1c3_3b79_4351_91a7_e256f1cd916d_Review_System.State | hazel | Resolved | hazel |  | hazel | Resolved | hazel | all_VSTS_d9cdb1c3_3b79_4351_91a7_e256f1cd916d_Test Case_System.State | hazel | Resolved |  | 4 | hazel | hazel | Resolved | hazel | 4 | hazel | hazel | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Test Case_System.State | 4 | hazel | hazel | hazel | Resolved | hazel | 4 | \20 Analysis\21 Use Case Model Survey | \Phase 3 | hazel | Resolved | 4 |  | VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_8B-D1-53-A2-A6-FB-4F-03-24-65-B4-29-73-CC-D1-C9-B6-3C-6A-90 | hazel | hazel |  | \20 Analysis\21 Use Case Model Survey | 4 - Low | 4 - Low | 4 - Low | 4 - Low | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | hazel | hazel | hazel | hazel | hazel | hazel | hazel | hazel | 4 - Low | 4 | VSTS_d9cdb1c3_3b79_4351_91a7_e256f1cd916d_F6-86-31-A3-47-27-76-CB-57-28-49-17-32-EB-97-93-07-11-CC-4D | VSTS_d9cdb1c3_3b79_4351_91a7_e256f1cd916d_26-FF-DE-08-0D-C9-09-53-1F-05-FD-90-D7-AD-D4-D5-FF-6A-89-45 | VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_6F-C6-D8-EB-43-26-13-F5-A3-D3-8B-09-48-94-22-7A-77-AF-E5-C2 | Requirement | hazel | hazel | hazel | hazel | hazel | hazel | [6 empty] | \Phase 3 | Cannot Reproduce | Code Complete and System Tested | Investigation Complete | Code Complete and System Test Passed | Closed in Error | Mitigated | Obsolete | Complete and Does Not Require Review/Test | New | Cannot Reproduce | Triaged | Triaged | Triaged | Triaged | Triaged | Triaged | Requirement |  | Triaged | [6 empty] | Cannot Reproduce | Code Complete and System Tested | Investigation Complete | Code Complete and System Test Passed | Closed in Error | Mitigated | Obsolete | Complete and Does Not Require Review/Test | New | Cannot Reproduce | Triaged | Triaged | Triaged | Triaged | Triaged | Triaged |  | Triaged |  | Requirement
|  |  |  | jifa | jifa | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Bug_System.State | jifa | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Bug_Microsoft.VSTS.Common.Priority | jifa | jifa | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Change Request_System.State | jifa | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Change Request_Microsoft.VSTS.Common.Priority | jifa | jifa | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Issue_System.State | jifa | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Issue_Microsoft.VSTS.Common.Priority | jifa | jifa | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Requirement_System.State | jifa | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Requirement_Microsoft.VSTS.Common.Priority | jifa | jifa |  | jifa | jifa | jifa | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Risk_System.State | jifa | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Risk_Microsoft.VSTS.Common.Priority | jifa | jifa | jifa | jifa | jifa | all_VSTS_d9cdb1c3_3b79_4351_91a7_e256f1cd916d_Bug_System.State | jifa | all_VSTS_d9cdb1c3_3b79_4351_91a7_e256f1cd916d_Change Request_System.State | jifa | all_VSTS_d9cdb1c3_3b79_4351_91a7_e256f1cd916d_Issue_System.State | jifa | all_VSTS_d9cdb1c3_3b79_4351_91a7_e256f1cd916d_Requirement_System.State | jifa |  | jifa | all_VSTS_d9cdb1c3_3b79_4351_91a7_e256f1cd916d_Risk_System.State | jifa |  | jifa | all_VSTS_d9cdb1c3_3b79_4351_91a7_e256f1cd916d_Task_System.State | jifa |  | jifa | Assigned |  | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Shared Steps_Microsoft.VSTS.Common.Priority | jifa | jifa | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Task_System.State | jifa | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Task_Microsoft.VSTS.Common.Priority | jifa | jifa |  | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Test Case_Microsoft.VSTS.Common.Priority | jifa | jifa | jifa | Assigned | jifa | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Microsoft.VSTS.Common.Priority | \20 Analysis\22 Use Case Realization Report (Analysis) | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_System.IterationPath | jifa | VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_9F-F6-0F-1C-08-6A-BA-DC-02-F0-E1-1F-9D-C4-DD-F3-E1-46-6F-4A | VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_A9-74-3C-60-20-83-BF-D2-70-44-DA-6E-AF-8C-55-96-9A-24-CE-B3 |  |  | jifa | jifa |  | \20 Analysis\22 Use Case Realization Report (Analysis) | all_VSTS_d9cdb1c3_3b79_4351_91a7_e256f1cd916d_Bug_Microsoft.VSTS.Common.Severity | all_VSTS_d9cdb1c3_3b79_4351_91a7_e256f1cd916d_Issue_Microsoft.VSTS.Common.Severity | all_VSTS_d9cdb1c3_3b79_4351_91a7_e256f1cd916d_Risk_Microsoft.VSTS.Common.Severity | all_VSTS_d9cdb1c3_3b79_4351_91a7_e256f1cd916d_Microsoft.VSTS.Common.Severity | all_VSTS_d9cdb1c3_3b79_4351_91a7_e256f1cd916d_Bug_Microsoft.VSTS.Common.Priority | all_VSTS_d9cdb1c3_3b79_4351_91a7_e256f1cd916d_Change Request_Microsoft.VSTS.Common.Priority | all_VSTS_d9cdb1c3_3b79_4351_91a7_e256f1cd916d_Issue_Microsoft.VSTS.Common.Priority | all_VSTS_d9cdb1c3_3b79_4351_91a7_e256f1cd916d_Requirement_Microsoft.VSTS.Common.Priority | all_VSTS_d9cdb1c3_3b79_4351_91a7_e256f1cd916d_Risk_Microsoft.VSTS.Common.Priority | all_VSTS_d9cdb1c3_3b79_4351_91a7_e256f1cd916d_Shared Steps_Microsoft.VSTS.Common.Priority | all_VSTS_d9cdb1c3_3b79_4351_91a7_e256f1cd916d_Task_Microsoft.VSTS.Common.Priority | all_VSTS_d9cdb1c3_3b79_4351_91a7_e256f1cd916d_Test Case_Microsoft.VSTS.Common.Priority | all_VSTS_d9cdb1c3_3b79_4351_91a7_e256f1cd916d_Microsoft.VSTS.Common.Priority | jifa | jifa | jifa | jifa | jifa | jifa | jifa | jifa | VSTS_d9cdb1c3_3b79_4351_91a7_e256f1cd916d_45-F5-9C-27-95-2A-7B-65-33-77-4B-A9-8C-81-2F-7D-A7-A1-56-F2 | VSTS_d9cdb1c3_3b79_4351_91a7_e256f1cd916d_A9-74-3C-60-20-83-BF-D2-70-44-DA-6E-AF-8C-55-96-9A-24-CE-B3 |  |  |  | Review | jifa | jifa | jifa | jifa | jifa | jifa | [6 empty] | all_VSTS_d9cdb1c3_3b79_4351_91a7_e256f1cd916d_System.IterationPath | Closed in Error | Investigate | New | Investigate | Major Changes Complete | Mitigation Action Complete | Reactivated | Complete and Requires Review/Test | Obsolete | Closed in Error | all_VSTS_d9cdb1c3_3b79_4351_91a7_e256f1cd916d_Bug_Microsoft.VSTS.Common.Triage | all_VSTS_d9cdb1c3_3b79_4351_91a7_e256f1cd916d_Change Request_Microsoft.VSTS.Common.Triage | all_VSTS_d9cdb1c3_3b79_4351_91a7_e256f1cd916d_Issue_Microsoft.VSTS.Common.Triage | all_VSTS_d9cdb1c3_3b79_4351_91a7_e256f1cd916d_Requirement_Microsoft.VSTS.Common.Triage | all_VSTS_d9cdb1c3_3b79_4351_91a7_e256f1cd916d_Task_Microsoft.VSTS.Common.Triage | all_VSTS_d9cdb1c3_3b79_4351_91a7_e256f1cd916d_Microsoft.VSTS.Common.Triage | Review |  | VSTS_d9cdb1c3_3b79_4351_91a7_e256f1cd916d_94-53-34-EB-36-B9-44-D0-24-37-A0-62-B2-E1-13-E8-50-A4-DF-57 | [6 empty] | Closed in Error | Investigate | New | Investigate | Major Changes Complete | Mitigation Action Complete | Reactivated | Complete and Requires Review/Test | Obsolete | Closed in Error | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Bug_Microsoft.VSTS.Common.Triage | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Change Request_Microsoft.VSTS.Common.Triage | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Issue_Microsoft.VSTS.Common.Triage | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Requirement_Microsoft.VSTS.Common.Triage | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Task_Microsoft.VSTS.Common.Triage | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Microsoft.VSTS.Common.Triage |  | VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_94-53-34-EB-36-B9-44-D0-24-37-A0-62-B2-E1-13-E8-50-A4-DF-57 |  | Review
|  |  |  | LOCAL SERVICE | LOCAL SERVICE |  | LOCAL SERVICE |  | LOCAL SERVICE | LOCAL SERVICE |  | LOCAL SERVICE |  | LOCAL SERVICE | LOCAL SERVICE |  | LOCAL SERVICE |  | LOCAL SERVICE | LOCAL SERVICE |  | LOCAL SERVICE |  | LOCAL SERVICE | LOCAL SERVICE |  | LOCAL SERVICE | LOCAL SERVICE | LOCAL SERVICE |  | LOCAL SERVICE |  | LOCAL SERVICE | LOCAL SERVICE | LOCAL SERVICE | LOCAL SERVICE | LOCAL SERVICE |  | LOCAL SERVICE |  | LOCAL SERVICE |  | LOCAL SERVICE |  | LOCAL SERVICE |  | LOCAL SERVICE |  | LOCAL SERVICE |  | LOCAL SERVICE |  | LOCAL SERVICE |  | LOCAL SERVICE | In progress |  |  | LOCAL SERVICE | LOCAL SERVICE |  | LOCAL SERVICE |  | LOCAL SERVICE | LOCAL SERVICE |  |  | LOCAL SERVICE | LOCAL SERVICE | LOCAL SERVICE | In progress | LOCAL SERVICE |  | \30 Prototype |  | LOCAL SERVICE |  |  |  |  | LOCAL SERVICE | LOCAL SERVICE |  | \30 Prototype | [13 empty] | LOCAL SERVICE | LOCAL SERVICE | LOCAL SERVICE | LOCAL SERVICE | LOCAL SERVICE | LOCAL SERVICE | LOCAL SERVICE | LOCAL SERVICE | [5 empty] | Risk | LOCAL SERVICE | LOCAL SERVICE | LOCAL SERVICE | LOCAL SERVICE | LOCAL SERVICE | LOCAL SERVICE | [7 empty] | Deferred | Investigation Complete | Overtaken by events | Investigation Complete | Minor Changes Complete | Mitigation Action Unsatisfactory (rework) | all_VSTS_d9cdb1c3_3b79_4351_91a7_e256f1cd916d_Shared Steps_System.Reason | Cut | Reactivated | Deferred | [6 empty] | Risk | [8 empty] | Deferred | Investigation Complete | Overtaken by events | Investigation Complete | Minor Changes Complete | Mitigation Action Unsatisfactory (rework) | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Shared Steps_System.Reason | Cut | Reactivated | Deferred | [9 empty] | Risk
|  |  |  | peishan | peishan |  | peishan |  | peishan | peishan |  | peishan |  | peishan | peishan |  | peishan |  | peishan | peishan |  | peishan |  | peishan | peishan |  | peishan | peishan | peishan |  | peishan |  | peishan | peishan | peishan | peishan | peishan |  | peishan |  | peishan |  | peishan |  | peishan |  | peishan |  | peishan |  | peishan |  | peishan |  | peishan | Design |  |  | peishan | peishan |  | peishan |  | peishan | peishan |  |  | peishan | peishan | peishan | Design | peishan |  | \30 Prototype\31 UI Prototype |  | peishan |  |  |  |  | peishan | peishan |  | \30 Prototype\31 UI Prototype | [13 empty] | peishan | peishan | peishan | peishan | peishan | peishan | peishan | peishan | [5 empty] | Shared Steps | peishan | peishan | peishan | peishan | peishan | peishan | [7 empty] | Duplicate | New | Rejected (not an issue) | New | New | Mitigation Triggered |  | Deferred | Update Test Case | Duplicate | [6 empty] | Shared Steps | [8 empty] | Duplicate | New | Rejected (not an issue) | New | New | Mitigation Triggered |  | Deferred | Update Test Case | Duplicate | [9 empty] | Shared Steps
|  |  |  | se18team8s | se18team8s |  | se18team8s |  | se18team8s | se18team8s |  | se18team8s |  | se18team8s | se18team8s |  | se18team8s |  | se18team8s | se18team8s |  | se18team8s |  | se18team8s | se18team8s |  | se18team8s | se18team8s | se18team8s |  | se18team8s |  | se18team8s | se18team8s | se18team8s | se18team8s | se18team8s |  | se18team8s |  | se18team8s |  | se18team8s |  | se18team8s |  | se18team8s |  | se18team8s |  | se18team8s |  | se18team8s |  | se18team8s | Ready |  |  | se18team8s | se18team8s |  | se18team8s |  | se18team8s | se18team8s |  |  | se18team8s | se18team8s | se18team8s | Ready | se18team8s |  | \30 Prototype\32 Architecture Prototye |  | se18team8s |  |  |  |  | se18team8s | se18team8s |  | \30 Prototype\32 Architecture Prototye | [13 empty] | se18team8s | se18team8s | se18team8s | se18team8s | se18team8s | se18team8s | se18team8s | se18team8s | [5 empty] | Task | se18team8s | se18team8s | se18team8s | se18team8s | se18team8s | se18team8s | [7 empty] | Fixed | Out-of-scope | Re-occurred | Out-of-scope | all_VSTS_d9cdb1c3_3b79_4351_91a7_e256f1cd916d_Review_System.Reason | New |  | Investigate | all_VSTS_d9cdb1c3_3b79_4351_91a7_e256f1cd916d_Test Case_System.Reason | Fixed | [6 empty] | Task | [8 empty] | Fixed | Out-of-scope | Re-occurred | Out-of-scope | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Review_System.Reason | New |  | Investigate | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Test Case_System.Reason | Fixed | [9 empty] | Task
|  |  |  | thida | thida |  | thida |  | thida | thida |  | thida |  | thida | thida |  | thida |  | thida | thida |  | thida |  | thida | thida |  | thida | thida | thida |  | thida |  | thida | thida | thida | thida | thida |  | thida |  | thida |  | thida |  | thida |  | thida |  | thida |  | thida |  | thida |  | thida | all_VSTS_d9cdb1c3_3b79_4351_91a7_e256f1cd916d_System.State |  |  | thida | thida |  | thida |  | thida | thida |  |  | thida | thida | thida | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_System.State | thida |  | \30 Prototype\33 Prototype Study Report |  | thida |  |  |  |  | thida | thida |  | \30 Prototype\33 Prototype Study Report | [13 empty] | thida | thida | thida | thida | thida | thida | thida | thida | [5 empty] | Test Case | thida | thida | thida | thida | thida | thida | [7 empty] | Investigate | Rejected | Re-opened | Postponed |  | Overtaken by events |  | Investigation Complete |  | Investigate | [6 empty] | Test Case | [8 empty] | Investigate | Rejected | Re-opened | Postponed |  | Overtaken by events |  | Investigation Complete |  | Investigate | [9 empty] | Test Case
|  |  |  | zaw | zaw |  | zaw |  | zaw | zaw |  | zaw |  | zaw | zaw |  | zaw |  | zaw | zaw |  | zaw |  | zaw | zaw |  | zaw | zaw | zaw |  | zaw |  | zaw | zaw | zaw | zaw | zaw |  | zaw |  | zaw |  | zaw |  | zaw |  | zaw |  | zaw |  | zaw |  | zaw |  | zaw |  |  |  | zaw | zaw |  | zaw |  | zaw | zaw |  |  | zaw | zaw | zaw |  | zaw |  | \40 Design |  | zaw |  |  |  |  | zaw | zaw |  | \40 Design | [13 empty] | zaw | zaw | zaw | zaw | zaw | zaw | zaw | zaw | [5 empty] | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_System.WorkItemType | zaw | zaw | zaw | zaw | zaw | zaw | [7 empty] | Investigation Complete | Validation Test Failed | Resolution Verified and Accepted | Reintroduced in Scope |  | Rejected |  | New |  | Investigation Complete | [6 empty] | all_VSTS_d9cdb1c3_3b79_4351_91a7_e256f1cd916d_System.WorkItemType | [8 empty] | Investigation Complete | Validation Test Failed | Resolution Verified and Accepted | Reintroduced in Scope |  | Rejected |  | New |  | Investigation Complete | [9 empty] | VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_4F-DF-70-5A-5E-58-89-30-F3-EC-F6-04-C2-E7-A9-98-CA-BD-C1-48
|  |  |  | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Bug_System.AssignedTo | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Bug_Microsoft.VSTS.Common.ClosedBy |  | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Bug_Microsoft.VSTS.Common.ResolvedBy |  | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Change Request_System.AssignedTo | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Change Request_Microsoft.VSTS.Common.ClosedBy |  | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Change Request_Microsoft.VSTS.Common.ResolvedBy |  | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Issue_System.AssignedTo | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Issue_Microsoft.VSTS.Common.ClosedBy |  | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Issue_Microsoft.VSTS.Common.ResolvedBy |  | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Requirement_System.AssignedTo | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Requirement_Microsoft.VSTS.Common.ClosedBy |  | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Requirement_Microsoft.VSTS.Common.ResolvedBy |  | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Review_System.AssignedTo | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Review_Microsoft.VSTS.Common.ClosedBy |  | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Review_Microsoft.VSTS.Common.ResolvedBy | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Risk_System.AssignedTo | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Risk_Microsoft.VSTS.Common.ClosedBy |  | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Risk_Microsoft.VSTS.Common.ResolvedBy |  | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Shared Steps_System.AssignedTo | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Shared Steps_Microsoft.VSTS.Common.ClosedBy | all_VSTS_d9cdb1c3_3b79_4351_91a7_e256f1cd916d_Bug_Microsoft.VSTS.Common.ActivatedBy | all_VSTS_d9cdb1c3_3b79_4351_91a7_e256f1cd916d_Change Request_Microsoft.VSTS.Common.ActivatedBy | all_VSTS_d9cdb1c3_3b79_4351_91a7_e256f1cd916d_Bug_System.AssignedTo |  | all_VSTS_d9cdb1c3_3b79_4351_91a7_e256f1cd916d_Change Request_System.AssignedTo |  | all_VSTS_d9cdb1c3_3b79_4351_91a7_e256f1cd916d_Issue_System.AssignedTo |  | all_VSTS_d9cdb1c3_3b79_4351_91a7_e256f1cd916d_Requirement_System.AssignedTo |  | all_VSTS_d9cdb1c3_3b79_4351_91a7_e256f1cd916d_Review_System.AssignedTo |  | all_VSTS_d9cdb1c3_3b79_4351_91a7_e256f1cd916d_Risk_System.AssignedTo |  | all_VSTS_d9cdb1c3_3b79_4351_91a7_e256f1cd916d_Shared Steps_System.AssignedTo |  | all_VSTS_d9cdb1c3_3b79_4351_91a7_e256f1cd916d_Task_System.AssignedTo |  | all_VSTS_d9cdb1c3_3b79_4351_91a7_e256f1cd916d_Test Case_System.AssignedTo |  | all_VSTS_d9cdb1c3_3b79_4351_91a7_e256f1cd916d_System.AssignedTo |  |  |  | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Task_System.AssignedTo | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Task_Microsoft.VSTS.Common.ClosedBy |  | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Task_Microsoft.VSTS.Common.ResolvedBy |  | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Test Case_System.AssignedTo | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Test Case_Microsoft.VSTS.Common.ClosedBy |  |  | all_VSTS_d9cdb1c3_3b79_4351_91a7_e256f1cd916d_Issue_Microsoft.VSTS.Common.ActivatedBy | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_System.AssignedTo | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Microsoft.VSTS.Common.ClosedBy |  | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Microsoft.VSTS.Common.ResolvedBy |  | \40 Design\41 High level architecture |  | VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_63-3D-6E-FD-05-A5-E3-0A-3D-3B-27-25-0E-09-89-A2-24-50-7D-FA |  |  |  |  | all_VSTS_d9cdb1c3_3b79_4351_91a7_e256f1cd916d_Requirement_Microsoft.VSTS.Common.ActivatedBy | VSTS_d9cdb1c3_3b79_4351_91a7_e256f1cd916d_63-3D-6E-FD-05-A5-E3-0A-3D-3B-27-25-0E-09-89-A2-24-50-7D-FA |  | \40 Design\41 High level architecture | [13 empty] | all_VSTS_d9cdb1c3_3b79_4351_91a7_e256f1cd916d_Bug_Microsoft.VSTS.Common.ResolvedBy | all_VSTS_d9cdb1c3_3b79_4351_91a7_e256f1cd916d_Change Request_Microsoft.VSTS.Common.ResolvedBy | all_VSTS_d9cdb1c3_3b79_4351_91a7_e256f1cd916d_Issue_Microsoft.VSTS.Common.ResolvedBy | all_VSTS_d9cdb1c3_3b79_4351_91a7_e256f1cd916d_Requirement_Microsoft.VSTS.Common.ResolvedBy | all_VSTS_d9cdb1c3_3b79_4351_91a7_e256f1cd916d_Review_Microsoft.VSTS.Common.ResolvedBy | all_VSTS_d9cdb1c3_3b79_4351_91a7_e256f1cd916d_Risk_Microsoft.VSTS.Common.ResolvedBy | all_VSTS_d9cdb1c3_3b79_4351_91a7_e256f1cd916d_Task_Microsoft.VSTS.Common.ResolvedBy | all_VSTS_d9cdb1c3_3b79_4351_91a7_e256f1cd916d_Microsoft.VSTS.Common.ResolvedBy | [6 empty] | all_VSTS_d9cdb1c3_3b79_4351_91a7_e256f1cd916d_Review_Microsoft.VSTS.Common.ActivatedBy | all_VSTS_d9cdb1c3_3b79_4351_91a7_e256f1cd916d_Risk_Microsoft.VSTS.Common.ActivatedBy | all_VSTS_d9cdb1c3_3b79_4351_91a7_e256f1cd916d_Shared Steps_Microsoft.VSTS.Common.ActivatedBy | all_VSTS_d9cdb1c3_3b79_4351_91a7_e256f1cd916d_Task_Microsoft.VSTS.Common.ActivatedBy | all_VSTS_d9cdb1c3_3b79_4351_91a7_e256f1cd916d_Test Case_Microsoft.VSTS.Common.ActivatedBy | all_VSTS_d9cdb1c3_3b79_4351_91a7_e256f1cd916d_Microsoft.VSTS.Common.ActivatedBy | [7 empty] | New | Validation Test Passed | Resolved | Rejected |  | all_VSTS_d9cdb1c3_3b79_4351_91a7_e256f1cd916d_Risk_System.Reason |  | Overtaken by events |  | New | [15 empty] | New | Validation Test Passed | Resolved | Rejected |  | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Risk_System.Reason |  | Overtaken by events |  | New
[74 empty] | \40 Design\42 Detailed Design Specficiations | [9 empty] | \40 Design\42 Detailed Design Specficiations | [40 empty] | Not fixed | all_VSTS_d9cdb1c3_3b79_4351_91a7_e256f1cd916d_Change Request_System.Reason | Rework | Split |  |  |  | Reactivated |  | Not fixed | [15 empty] | Not fixed | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Change Request_System.Reason | Rework | Split |  |  |  | Reactivated |  | Not fixed
[74 empty] | \50 Build | [9 empty] | \50 Build | [40 empty] | Obsolete |  | all_VSTS_d9cdb1c3_3b79_4351_91a7_e256f1cd916d_Issue_System.Reason | Validation Test Failed |  |  |  | Rejected |  | Obsolete | [15 empty] | Obsolete |  | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Issue_System.Reason | Validation Test Failed |  |  |  | Rejected |  | Obsolete
[74 empty] | \50 Build\50 UI design | [9 empty] | \50 Build\50 UI design | [40 empty] | Regression |  |  | Validation Test Passed |  |  |  | Review/Test Failed |  | Regression | [15 empty] | Regression |  |  | Validation Test Passed |  |  |  | Review/Test Failed |  | Regression
[74 empty] | \50 Build\51 Security and Admin | [9 empty] | \50 Build\51 Security and Admin | [40 empty] | Rejected |  |  | all_VSTS_d9cdb1c3_3b79_4351_91a7_e256f1cd916d_Requirement_System.Reason |  |  |  | Review/Test Passed |  | Rejected | [15 empty] | Rejected |  |  | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Requirement_System.Reason |  |  |  | Review/Test Passed |  | Rejected
[74 empty] | \50 Build\52 Volunteer Management | [9 empty] | \50 Build\52 Volunteer Management | [40 empty] | Test Failed | [6 empty] | all_VSTS_d9cdb1c3_3b79_4351_91a7_e256f1cd916d_Task_System.Reason |  | Test Failed | [15 empty] | Test Failed | [6 empty] | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Task_System.Reason |  | Test Failed
[74 empty] | \50 Build\53 Staff Management | [9 empty] | \50 Build\53 Staff Management | [40 empty] | Verified | [8 empty] | Verified | [15 empty] | Verified | [8 empty] | Verified
[74 empty] | \50 Build\54 Project Management | [9 empty] | \50 Build\54 Project Management | [40 empty] | all_VSTS_d9cdb1c3_3b79_4351_91a7_e256f1cd916d_Bug_System.Reason | [8 empty] | Abandoned | [15 empty] | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Bug_System.Reason | [8 empty] | Abandoned
[74 empty] | \50 Build\55 Itinerary Management | [9 empty] | \50 Build\55 Itinerary Management | [49 empty] | Accepted | [24 empty] | Accepted
[74 empty] | \50 Build\56 Reporting | [9 empty] | \50 Build\56 Reporting | [49 empty] | Code Complete and System Tested | [24 empty] | Code Complete and System Tested
[74 empty] | \60 Test | [9 empty] | \60 Test | [49 empty] | Out-of-scope | [24 empty] | Out-of-scope
[74 empty] | \60 Test\61 Unit test | [9 empty] | \60 Test\61 Unit test | [49 empty] | Validation Test Failed | [24 empty] | Validation Test Failed
[74 empty] | \60 Test\62 SIT | [9 empty] | \60 Test\62 SIT | [49 empty] | Validation Test Passed | [24 empty] | Validation Test Passed
[74 empty] | \60 Test\63 UAT | [9 empty] | \60 Test\63 UAT | [49 empty] | Overtaken by events | [24 empty] | Overtaken by events
[74 empty] | \70 Report | [9 empty] | \70 Report | [49 empty] | Rejected (not an issue) | [24 empty] | Rejected (not an issue)
[74 empty] | \70 Report\71 Presentation Phase 1 | [9 empty] | \70 Report\71 Presentation Phase 1 | [49 empty] | Re-occurred | [24 empty] | Re-occurred
[74 empty] | \70 Report\72 Presentation Phase 2 | [9 empty] | \70 Report\72 Presentation Phase 2 | [49 empty] | Re-opened | [24 empty] | Re-opened
[74 empty] | \70 Report\73 Presentation Phase 3 | [9 empty] | \70 Report\73 Presentation Phase 3 | [49 empty] | Resolution Verified and Accepted | [24 empty] | Resolution Verified and Accepted
[74 empty] | \70 Report\74 End project report | [9 empty] | \70 Report\74 End project report | [49 empty] | Resolved | [24 empty] | Resolved
[74 empty] | \80 Project Management | [9 empty] | \80 Project Management | [49 empty] | Rework | [24 empty] | Rework
[74 empty] | \90 Quality Management | [9 empty] | \90 Quality Management | [49 empty] | Code Complete and System Test Passed | [24 empty] | Code Complete and System Test Passed
[74 empty] | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_System.AreaPath | [9 empty] | all_VSTS_d9cdb1c3_3b79_4351_91a7_e256f1cd916d_System.AreaPath | [49 empty] | Postponed | [24 empty] | Postponed
[134 empty] | Reintroduced in Scope | [24 empty] | Reintroduced in Scope
[134 empty] | Split | [24 empty] | Split
[134 empty] | Accepted (as is) | [24 empty] | Accepted (as is)
[134 empty] | Accepted with Major Changes | [24 empty] | Accepted with Major Changes
[134 empty] | Accepted with Minor Changes | [24 empty] | Accepted with Minor Changes
[134 empty] | Major Changes Complete | [24 empty] | Major Changes Complete
[134 empty] | Minor Changes Complete | [24 empty] | Minor Changes Complete
[134 empty] | Accepted (won't mitigate) | [24 empty] | Accepted (won't mitigate)
[134 empty] | Eliminated | [24 empty] | Eliminated
[134 empty] | Mitigated | [24 empty] | Mitigated
[134 empty] | Mitigation Action Complete | [24 empty] | Mitigation Action Complete
[134 empty] | Mitigation Action Unsatisfactory (rework) | [24 empty] | Mitigation Action Unsatisfactory (rework)
[134 empty] | Mitigation Triggered | [24 empty] | Mitigation Triggered
[134 empty] | Reactivated | [24 empty] | Reactivated
[134 empty] | Cancelled | [24 empty] | Cancelled
[134 empty] | Complete and Does Not Require Review/Test | [24 empty] | Complete and Does Not Require Review/Test
[134 empty] | Complete and Requires Review/Test | [24 empty] | Complete and Requires Review/Test
[134 empty] | Cut | [24 empty] | Cut
[134 empty] | Review/Test Failed | [24 empty] | Review/Test Failed
[134 empty] | Review/Test Passed | [24 empty] | Review/Test Passed
[134 empty] | Completed | [24 empty] | Completed
[134 empty] | Update Test Case | [24 empty] | Update Test Case
[134 empty] | all_VSTS_d9cdb1c3_3b79_4351_91a7_e256f1cd916d_System.Reason | [24 empty] | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_System.Reason