## Sheet1
Project: MTECH SE18 CMMI Server: diolaptop\MTECH-SE18 CMMI Query: Open Work & Tasks Items List type: Flat
ID | Stack Rank | Priority | Work Item Type | Assigned To | State | Title | Description
4 |  | 2 | Task | Dio | Active | Review WBS to include all members to do UCMS and UCRR | Lecturers are concern that the writing of functional specifications of UCMS and UCRR might take more time. Suggested that all team members to participate in the functional specifications task. WBS to be review by Dio
5 |  | 2 | Task | Dio | Active | Review WBS to add in more congtingency time for tasks | Lecturers are concern that some team members might be overloaded thus suggested that might need to re-estimate the effort. WBS to be reviewed by Dio
1 |  | 3 | Task | Dio | Active | Find formal user for MTECH | Find formal user for MTECH
2 |  | 3 | Task | Dio | Active | Put in the review evidence for QA plan | Has not started on this item. To update the review form with the last review update
16 |  | 1 | Task | Dio | Active | 1st Draft of Use Case Model Survey | 1st Draft of Use Case Model Survey To be done by : Hazel, Thida, Dio, Peishan Due by : 30 May 2011
17 |  | 1 | Task | Dio | Active | Build 1st Draft of UCRR (Analysis) | 1st Draft UCRR (Analysis): Task assignment is done in https://mtech-se18-t08s.googlecode.com/svn/trunk/docs/W-9%20Working%20Document/W-9.1%20Team%20Members/W-9.1.6%20Thida/
8 |  | 2 | Task | FengYan | Active | AJAX components comparison prototyping. (JSON / DWR / Struts2) | AJAX components comparison prototyping. (JSON / DWR / Struts2)
6 |  | 1 | Task | Hazel | Active | Produce UI prototype | User Interface (UI) prototyping task. This will consists of the actual screen flow and design. Intend to use this for the actual implementation. To be done by: Jifa, Hazel, Dio Due by: 22 May 2011
10 |  | 2 | Task | Jifa | Active | Database comparison prototype. (MS SQL / MySQL / Postgres) | Database comparison prototype. (MS SQL / MySQL / Postgres)
19 |  | 2 | Task | Jifa | Active | Explore on App / JTrac / Database Server availability on ISS / NUS | Explore on App / JTrac / Database Server availability on ISS / NUS To be done by: Zaw, Jifa, Due by: 22 May 2011
14 |  | 2 | Task | Peishan | Resolved | A prototyping study report document template is required. Peishan to come up with it. | A prototyping study report document template is required. Peishan to come up with it.
9 |  | 2 | Task | Peishan | Active | UI AJAX components comparison prototyping. (YUI2 / GWT / MyFaces Tomahawk) | UI AJAX components comparison prototyping. (YUI2 / GWT / MyFaces Tomahawk) Notes: Not applicable since these components are different
3 |  | 2 | Task | Peishan | Active | Review project plan and put in review edvidence | Review project plan and put in review edvidence
15 |  | 1 | Task | Thida | Resolved | UCMS and UCRR tasks break down for everyone | For functional specifications of Use Case Model Survey and Use Case Realisation Report, Thida will be performing the task assignment and send to the team as she is familiar with the requirements. To note that, as this is a concurrent task with prototyping, Jifa, Hazel and Zaw should not be handling use case that have difficult business logic.
12 |  | 2 | Task | Thida | Active | Reporting comparison prototype. (JasperReport / Crystal Report) | Reporting comparison prototype. (JasperReport / Crystal Report)
13 |  | 2 | Task | Zaw | Active | End to end use case prototyping using the most complicated use case. (Itinerary Management) | End to end use case prototyping using the most complicated use case. (Itinerary Management)
11 |  | 2 | Task | Zaw | Active | Framework comparison prototype. (Spring / Struts 2) | Framework comparison prototype. (Spring / Struts 2)
18 |  | 1 | Task | Zaw | Active | Explore and setup Team collaboration software | Explore and setup Team collaboration software To be done by : Zaw, Feng Yan Due by: 1 Jul 2011
7 |  | 2 | Task | Zaw | Active | Data access layer comparison prototype task (iBatis / Hibernate / combination of both iBatis and Hibernate) | Produce Data access layer comparison for arch prototype (iBatis / Hibernate / combination of both iBatis and Hibernate)

## VSTS_ValidationWS_1 (hidden)
value doesn't matter | value doesn't matter | value doesn't matter | value doesn't matter | 1 | admin | Active | 1 | admin | Active | 1 | admin | Active | 1 | admin | Active | admin | Active | 1 | admin | Active | 1 | admin | Active | 1 | admin | Active | 1 | admin | Closed | 1 | Bug | admin | Active | \ | \ | 1 | admin | Active | Active
readOnlyTestRange_@ | readOnlyTestRange_0 | readOnlyTestRange_dd-MMM-yyyy h:mm AM/PM | readOnlyTestRange_General | 2 | Administrator (diolaptop\Administrator) | Closed | 2 | Administrator (diolaptop\Administrator) | Closed | 2 | Administrator (diolaptop\Administrator) | Closed | 2 | Administrator (diolaptop\Administrator) | Closed | Administrator (diolaptop\Administrator) | Closed | 2 | Administrator (diolaptop\Administrator) | Closed | 2 | Administrator (diolaptop\Administrator) | Closed | 2 | Administrator (diolaptop\Administrator) | Closed | 2 | Administrator (diolaptop\Administrator) | Design | 2 | Change Request | Administrator (diolaptop\Administrator) | Closed | \10 Requirements | \Phase 1 | 2 | Administrator (diolaptop\Administrator) | Closed | Closed
|  |  |  | 3 | Administrator (JTC\Administrator) | Proposed | 3 | Administrator (JTC\Administrator) | Proposed | 3 | Administrator (JTC\Administrator) | Proposed | 3 | Administrator (JTC\Administrator) | Proposed | Administrator (JTC\Administrator) | Resolved | 3 | Administrator (JTC\Administrator) | Proposed | 3 | Administrator (JTC\Administrator) | all_VSTS_5d8542b3_0885_4b9f_8fe4_a1c968d4d15f_Shared Steps_System.State | 3 | Administrator (JTC\Administrator) | Proposed | 3 | Administrator (JTC\Administrator) | Ready | 3 | Issue | Administrator (JTC\Administrator) | Proposed | \20 Analysis | \Phase 2 | 3 | Administrator (JTC\Administrator) | Proposed | Resolved
|  |  |  | 4 | Dio | Resolved | 4 | Dio | Resolved | 4 | Dio | Resolved | 4 | Dio | Resolved | Dio | all_VSTS_5d8542b3_0885_4b9f_8fe4_a1c968d4d15f_Review_System.State | 4 | Dio | Resolved | 4 | Dio |  | 4 | Dio | Resolved | 4 | Dio | all_VSTS_5d8542b3_0885_4b9f_8fe4_a1c968d4d15f_Test Case_System.State | 4 | Requirement | Dio | Resolved | \20 Analysis\21 UC Survey Model | \Phase 3 | 4 | Dio | Resolved | VSTS_5d8542b3_0885_4b9f_8fe4_a1c968d4d15f_26-FF-DE-08-0D-C9-09-53-1F-05-FD-90-D7-AD-D4-D5-FF-6A-89-45
|  |  |  | all_VSTS_5d8542b3_0885_4b9f_8fe4_a1c968d4d15f_Bug_Microsoft.VSTS.Common.Priority | DIOLAPTOP$ | all_VSTS_5d8542b3_0885_4b9f_8fe4_a1c968d4d15f_Bug_System.State | all_VSTS_5d8542b3_0885_4b9f_8fe4_a1c968d4d15f_Change Request_Microsoft.VSTS.Common.Priority | DIOLAPTOP$ | all_VSTS_5d8542b3_0885_4b9f_8fe4_a1c968d4d15f_Change Request_System.State | all_VSTS_5d8542b3_0885_4b9f_8fe4_a1c968d4d15f_Issue_Microsoft.VSTS.Common.Priority | DIOLAPTOP$ | all_VSTS_5d8542b3_0885_4b9f_8fe4_a1c968d4d15f_Issue_System.State | all_VSTS_5d8542b3_0885_4b9f_8fe4_a1c968d4d15f_Requirement_Microsoft.VSTS.Common.Priority | DIOLAPTOP$ | all_VSTS_5d8542b3_0885_4b9f_8fe4_a1c968d4d15f_Requirement_System.State | DIOLAPTOP$ |  | all_VSTS_5d8542b3_0885_4b9f_8fe4_a1c968d4d15f_Risk_Microsoft.VSTS.Common.Priority | DIOLAPTOP$ | all_VSTS_5d8542b3_0885_4b9f_8fe4_a1c968d4d15f_Risk_System.State | all_VSTS_5d8542b3_0885_4b9f_8fe4_a1c968d4d15f_Shared Steps_Microsoft.VSTS.Common.Priority | DIOLAPTOP$ |  | all_VSTS_5d8542b3_0885_4b9f_8fe4_a1c968d4d15f_Task_Microsoft.VSTS.Common.Priority | DIOLAPTOP$ | all_VSTS_5d8542b3_0885_4b9f_8fe4_a1c968d4d15f_Task_System.State | all_VSTS_5d8542b3_0885_4b9f_8fe4_a1c968d4d15f_Test Case_Microsoft.VSTS.Common.Priority | DIOLAPTOP$ |  | all_VSTS_5d8542b3_0885_4b9f_8fe4_a1c968d4d15f_Microsoft.VSTS.Common.Priority | Review | DIOLAPTOP$ | Design | \20 Analysis\22 UCRR (Analysis) | all_VSTS_5d8542b3_0885_4b9f_8fe4_a1c968d4d15f_System.IterationPath | VSTS_5d8542b3_0885_4b9f_8fe4_a1c968d4d15f_A9-74-3C-60-20-83-BF-D2-70-44-DA-6E-AF-8C-55-96-9A-24-CE-B3 | DIOLAPTOP$ | VSTS_5d8542b3_0885_4b9f_8fe4_a1c968d4d15f_F9-E1-2C-98-86-04-E5-7D-4B-B1-8B-C7-8F-D4-55-95-91-76-6C-DD
[5 empty] | Eng Chuan Yeap |  |  | Eng Chuan Yeap |  |  | Eng Chuan Yeap |  |  | Eng Chuan Yeap |  | Eng Chuan Yeap |  |  | Eng Chuan Yeap |  |  | Eng Chuan Yeap |  |  | Eng Chuan Yeap |  |  | Eng Chuan Yeap |  |  | Risk | Eng Chuan Yeap | Ready | \30 Design |  |  | Eng Chuan Yeap
[5 empty] | FengYan |  |  | FengYan |  |  | FengYan |  |  | FengYan |  | FengYan |  |  | FengYan |  |  | FengYan |  |  | FengYan |  |  | FengYan |  |  | Shared Steps | FengYan | all_VSTS_5d8542b3_0885_4b9f_8fe4_a1c968d4d15f_System.State | \30 Design\31 UCRR (Design) |  |  | FengYan
[5 empty] | Hazel |  |  | Hazel |  |  | Hazel |  |  | Hazel |  | Hazel |  |  | Hazel |  |  | Hazel |  |  | Hazel |  |  | Hazel |  |  | Task | Hazel |  | \40 Prototype |  |  | Hazel
[5 empty] | Jifa |  |  | Jifa |  |  | Jifa |  |  | Jifa |  | Jifa |  |  | Jifa |  |  | Jifa |  |  | Jifa |  |  | Jifa |  |  | Test Case | Jifa |  | \40 Prototype\41 UI prototype |  |  | Jifa
[5 empty] | NETWORK SERVICE |  |  | NETWORK SERVICE |  |  | NETWORK SERVICE |  |  | NETWORK SERVICE |  | NETWORK SERVICE |  |  | NETWORK SERVICE |  |  | NETWORK SERVICE |  |  | NETWORK SERVICE |  |  | NETWORK SERVICE |  |  | all_VSTS_5d8542b3_0885_4b9f_8fe4_a1c968d4d15f_System.WorkItemType | NETWORK SERVICE |  | \40 Prototype\42 Architect prototype |  |  | NETWORK SERVICE
[5 empty] | Peishan |  |  | Peishan |  |  | Peishan |  |  | Peishan |  | Peishan |  |  | Peishan |  |  | Peishan |  |  | Peishan |  |  | Peishan |  |  |  | Peishan |  | \50 Build |  |  | Peishan
[5 empty] | Phung Kim Cuong |  |  | Phung Kim Cuong |  |  | Phung Kim Cuong |  |  | Phung Kim Cuong |  | Phung Kim Cuong |  |  | Phung Kim Cuong |  |  | Phung Kim Cuong |  |  | Phung Kim Cuong |  |  | Phung Kim Cuong |  |  |  | Phung Kim Cuong |  | \60 Testing |  |  | Phung Kim Cuong
[5 empty] | ssmtiu1 |  |  | ssmtiu1 |  |  | ssmtiu1 |  |  | ssmtiu1 |  | ssmtiu1 |  |  | ssmtiu1 |  |  | ssmtiu1 |  |  | ssmtiu1 |  |  | ssmtiu1 |  |  |  | ssmtiu1 |  | \60 Testing\61 Unit test |  |  | ssmtiu1
[5 empty] | Thida |  |  | Thida |  |  | Thida |  |  | Thida |  | Thida |  |  | Thida |  |  | Thida |  |  | Thida |  |  | Thida |  |  |  | Thida |  | \60 Testing\62 SIT |  |  | Thida
[5 empty] | Vern Tay |  |  | Vern Tay |  |  | Vern Tay |  |  | Vern Tay |  | Vern Tay |  |  | Vern Tay |  |  | Vern Tay |  |  | Vern Tay |  |  | Vern Tay |  |  |  | Vern Tay |  | \60 Testing\63 UAT |  |  | Vern Tay
[5 empty] | Zaw |  |  | Zaw |  |  | Zaw |  |  | Zaw |  | Zaw |  |  | Zaw |  |  | Zaw |  |  | Zaw |  |  | Zaw |  |  |  | Zaw |  | \70 Report |  |  | Zaw
[5 empty] | all_VSTS_5d8542b3_0885_4b9f_8fe4_a1c968d4d15f_Bug_System.AssignedTo |  |  | all_VSTS_5d8542b3_0885_4b9f_8fe4_a1c968d4d15f_Change Request_System.AssignedTo |  |  | all_VSTS_5d8542b3_0885_4b9f_8fe4_a1c968d4d15f_Issue_System.AssignedTo |  |  | all_VSTS_5d8542b3_0885_4b9f_8fe4_a1c968d4d15f_Requirement_System.AssignedTo |  | all_VSTS_5d8542b3_0885_4b9f_8fe4_a1c968d4d15f_Review_System.AssignedTo |  |  | all_VSTS_5d8542b3_0885_4b9f_8fe4_a1c968d4d15f_Risk_System.AssignedTo |  |  | all_VSTS_5d8542b3_0885_4b9f_8fe4_a1c968d4d15f_Shared Steps_System.AssignedTo |  |  | all_VSTS_5d8542b3_0885_4b9f_8fe4_a1c968d4d15f_Task_System.AssignedTo |  |  | all_VSTS_5d8542b3_0885_4b9f_8fe4_a1c968d4d15f_Test Case_System.AssignedTo |  |  |  | all_VSTS_5d8542b3_0885_4b9f_8fe4_a1c968d4d15f_System.AssignedTo |  | \80 Project management |  |  | VSTS_5d8542b3_0885_4b9f_8fe4_a1c968d4d15f_1C-B5-F4-54-3B-B1-BF-E1-04-64-5A-0E-72-00-43-D8-EC-E7-75-BF
\90 Quality management
all_VSTS_5d8542b3_0885_4b9f_8fe4_a1c968d4d15f_System.AreaPath