## Slide 1: Volunteer Management System
Presented by Team SE18-08S

## Slide 2: Agenda
Project Revisit
Use Case Modeling
Software Architecture
Demo of Prototype
Transition Strategy
Project Progress
Challenges & Problems
Q & A

## Slide 3: Project Revisit
Volunteer Management
Staff Management
Project Management
Itinerary Management
Administration
Purpose: To build a web-based solution to facilitate the process of volunteer registration, project management till retention.
Requirement overview:

## Slide 4: Agenda
Project Revisit
Use Case Modeling
Software Architecture
Demo of Prototype
Transition Strategy
Project Progress
Development Plan
Challenges & Problems
Q & A

## Slide 5: Use Case Modeling
  Use Case Model Survey:
    23 use cases
    7 actors
  Sample Use Cases:
    Search Project Member
    Assign Role to Project Member
    Generate Certificate

## Slide 7: Use Case Modeling Sample 1: Search Project Member
Description: Let user search and view the member list of a project.
Interaction diagram

## Slide 8: Use Case Modeling Sample 1: Search Project Member
Class diagram

## Slide 9: Use Case Modeling Sample 2: Generate Certificate
Description: Let user search and view the member list of a project.
Interaction diagram

## Slide 10: Use Case Modeling Sample 2: Generate Certificate
Class diagram

## Slide 11: Agenda
Project Revisit
Use Case Modeling
Software Architecture
Demo of Prototype
Transition Strategy
Project Progress
Development Plan
Challenges & Problems
Q & A

## Slide 12: Software Architecture –Overview

## Slide 13: Software Architecture –Architecture Overview
Web Server
  Apache 2.2
  Apache Load Balancer (JK module)
Application Server
  Tomcat 6.0
Database Server (RDBMS)
  MySQL 5
Mail Server
  Any Java-supported mail server (eg. Gmail)

## Slide 14: High Level Architecture – Framework Overview

## Slide 15: High Level Architecture – Overview of Components

## Slide 16: Agenda
Project Revisit
Use Case Modeling
Software Architecture
Demo of Prototype
Transition Strategy
Project Progress
Development Plan
Challenges & Problems
Q & A

## Slide 17: Demo of Prototype
Volunteer Management System

## Slide 18: Demonstration of Prototype
Purpose of Technical Prototype:
  Confirm system components working
  Confirm feasibility and reusability
User Interface Prototype
  Review usability
  Confirm UI design with user

## Slide 19: Agenda
Project Revisit
Use Case Modeling
Software Architecture
Demo of Prototype
Transition Strategy
Project Progress
Development Plan
Challenges & Problems
Q & A

## Slide 20: Transition Strategy
Volunteer Management System

## Slide 21: Transition Strategy – Analysis to Design
Project Planning
Analysis and Design
Prototyping
Use Case Modeling
Use Case Realisation Report
High-level System Design
Software Architecture
Transition Strategy from Analysis to Design
Project Management

## Slide 22: Transition Strategy – Analysis to Design
No | Task | Description | In-Charge
1. | Prototyping | User interface prototyping Technical prototyping | Feng Yan, Jifa Zaw
2. | Use Case Modeling | Use case model survey | Thida, Hazel
3. | Use case realisation report | Use case realisation report | Thida, Hazel
4. | Software Design | High level software architecture design document | Zaw
5. | Transition Strategy from Analysis to Design | Transition Strategy from Analysis to Design | Zaw
6. | Project Management | Transition Strategy from Analysis to Design | Dio

## Slide 23: Transition Strategy
Active member involvement
  Involve all team members by clear and thorough communication
Clearly define roles and responsibilities
  Assign tasks to staff by capability and experience
Active risk management
  Anticipate risk early, accept and mitigate following the risk management techniques
Enforce tracking practices
  Monthly progress update

## Slide 24: Agenda
Project Revisit
Use Case Modeling
Software Architecture
Demo of Prototype
Transition Strategy
Project Progress
Development Plan
Challenges & Problems
Q & A

## Slide 25: PROJECT Progress
Volunteer Management System

## Slide 26: Project Progress
No | Activity | Planned Start Date | Planned End Date | Actual Start Date | Actual End Date | Planned Effort | Actual Effort | Task Status | Comments
1 | Project Planning |  |  |  |  |  |  |  | 
1.1 | Produce Project Plan | 21 Jan 2011 | 02 Apr 2011 | 20 Feb 2011 | 09 Apr 2011 | 7 | 9 | Done | Requirements gathering issues.
1.2 | Produce Quality Plan | 21 Jan 2011 | 02 Apr 2011 | 20 Feb 2011 | 05 Apr 2011 | 6 | 6.025 | Done | Makes changes based on Audit Meeting feedback
1.3 | Prepare First Audit & Presentation | 21 Jan 2011 | 02 Apr 2011 | 03 Apr 2011 | 09 Apr 2011 | 9 | 9 | Done | 
2 | Requirement Analysis |  |  |  |  |  |  |  | 
2.1 | Produce User Requirements Specifications | 22 Jan 2011 | 02 Apr 2011 | 20 Jan 2011 | 02 Apr 2011 | 18 | 13.6875 | Done | 
3 | Analysis Modelling |  |  |  |  |  |  |  | 
3.1 | Produce Functional Specifications : UCMS and UCRR (Analysis) | 10 Apr 2011 | 07 Jul 2011 |  |  | 38 |  | Open | 
3.3 | Produce Prototyping Study Report | 10 Apr 2011 | 12 Jun 2011 |  |  | 17.5 |  | Open | 

## Slide 27: Agenda
Project Revisit
Use Case Modeling
Software Architecture
Demo of Prototype
Transition Strategy
Project Progress
Development Plan
Challenges & Problems
Q & A

## Slide 28: DEVELOPMENT PLAN
Volunteer Management System

## Slide 29: Development plan
No | Activity | Planned Start Date | Planned End Date | Actual Start Date | Actual End Date | Planned Effort | Actual Effort | Task Status | Comments
1 | Project Planning |  |  |  |  |  |  |  | 
1.1 | Produce Project Plan | 21 Jan 2011 | 02 Apr 2011 | 20 Feb 2011 | 09 Apr 2011 | 7 | 9 | Done | Requirements gathering issues.
1.2 | Produce Quality Plan | 21 Jan 2011 | 02 Apr 2011 | 20 Feb 2011 | 05 Apr 2011 | 6 | 6.025 | Done | Makes changes based on Audit Meeting feedback
1.3 | Prepare First Audit & Presentation | 21 Jan 2011 | 02 Apr 2011 | 03 Apr 2011 | 09 Apr 2011 | 9 | 9 | Done | 
2 | Requirement Analysis |  |  |  |  |  |  |  | 
2.1 | Produce User Requirements Specifications | 22 Jan 2011 | 02 Apr 2011 | 20 Jan 2011 | 02 Apr 2011 | 18 | 13.6875 | Done | 
3 | Analysis Modelling |  |  |  |  |  |  |  | 
3.1 | Produce Functional Specifications : UCMS and UCRR (Analysis) | 10 Apr 2011 | 07 Jul 2011 |  |  | 38 |  | Open | 
3.3 | Produce Prototyping Study Report | 10 Apr 2011 | 12 Jun 2011 |  |  | 17.5 |  | Open | 

## Slide 30: Agenda
Project Revisit
Use Case Modeling
Software Architecture
Demo of Prototype
Transition Strategy
Project Progress
Development Plan
Challenges & Problems
Q & A

## Slide 31: Challenges & Problems
Volunteer Management System

## Slide 32: Challenges & Problems
No | Challenge | Description | Solution
1. | Communications | Difficulty to gather all members for discussions. | Online meeting via Skype To fix a weekly meeting time
2. | Requirements Gathering | Client only wants a small set of requirements. | Seek lecturers advice Proposed merging of requirements Appoint team members as putative end users Look for alternative customer
3. | Task Control | Not able to meet deadline on time. | To log time log To hold meetings to track status
4. | Low Quality of Work | Deliverables not up to standard. | Perform reviews Conduct briefing and demo on required items

## Slide 33: Agenda
Project Revisit
Use Case Modeling
Software Architecture
Demo of Prototype
Transition Strategy
Project Progress
Challenges & Problems
Q & A

## Slide 34: Question & Answer