## 1.Task
Project: MTECH SE18 TEAM8S Server: team8s.myvnc.com\DefaultCollection Query: All tasks List type: Flat
ID | Iteration Path | Area Path | Assigned To | Priority | Title | Description | State | History | Start Date | Finish Date | Resolved By | Resolved Date | Original Estimate | Remaining Work | Completed Work | Work Item Type
1 | \Phase 1 | \80 Project Management | admin | 1 | Finish server setup | To finish TFS, (done) MS SQL, (done) MySQL, (done) Java (done) Tomcat (done) Jtrac setup (N/A) | Closed |  | 2011-05-21 08:00 | 2011-06-01 17:00 |  |  | 8 | 64 | 8 | Task
2 | \Phase 2 | \50 Build\50 UI design | admin | 2 | Test out the SQL and TFS server | Please try to test the function of TFS & SQL | Closed |  | 2011-05-21 08:00 | 2011-06-08 17:00 |  |  | 0 | 0 | 112 | Task
3 | \Phase 2 | \80 Project Management | admin | 2 | To check with Zaw for MySQL setup | To check with Zaw for MySQL setup | Closed |  | 2011-05-21 08:00 | 2011-08-26 17:00 |  |  | 0 | 112 | 0 | Task
23 | \Phase 3 | \80 Project Management | dio | 1 | Development tasks break down - to use case level | Development tasks break down - to use case level (done - pending checked in SVN ) To review the draft WBS breakdown from Peishan (checked into SVN) (done) | In progress |  | 2011-08-13 00:41 | 2011-08-19 00:41 |  |  | 12 | 8 | 4 | Task
28 | \Phase 3 | \80 Project Management | dio | 1 | To prepare Implementation Plan - down to use case level , include SIT | Prepare Implementation Plan - in detailed Focus on : - prototype completed solution - integration phases - DWR usage ? OK or not ? | In progress |  | 2011-08-13 00:41 | 2011-08-20 |  |  | 16 | 14 | 2 | Task
49 | \Phase 3 | \80 Project Management | dio | 2 | To configure email sent out for TFS, to notice team member upon changes/new assignment | To configure email sent out for TFS for these items: - Task created - Bug update - Review request | In progress |  | 2011-08-21 16:04 | 2011-08-21 16:04 |  |  | 8 | 8 | 0 | Task
29 | \Phase 3 | \80 Project Management | dio | 1 | To produce tasks assignment for Detailed Design Document - involved all team members | To produce Detailed Design Document - all team members | In progress |  | 2011-08-13 17:53 | 2011-08-25 17:53 |  |  | 8 | 8 | 0 | Task
5 | \Phase 2 | \80 Project Management | dio | 1 | Review WBS to reflect latest change | To review WBS and Project plan to reflect latest status | In progress |  | 2011-06-01 08:00 | 2011-09-01 17:00 |  |  | 8 | 7 | 1 | Task
35 | \ | \80 Project Management | dio | 4 | Looking for User | To continue looking for potential user | Assigned |  | 2011-01-01 00:41 | 2012-01-01 |  |  | 8 | 8 | 0 | Task
10 | \Phase 2 | \30 Prototype\33 Prototype Study Report | dio | 2 | To compare Reporting Tool Prototype | To compare Reporting Tool Prototype | Closed |  | 2011-06-01 08:00 | 2011-08-20 | thida |  | 8 | 0 | 8 | Task
14 | \Phase 2 | \30 Prototype\31 UI Prototype | dio | 2 | To review UI draft 1 from Jifa | To review UI draft 1 from Jifa , in SVN - to suggest integrated view (all page with footer / header) - to suggest navigation - to suggest frame/ button/ layout / CSS usage | Closed |  | 2011-06-01 08:00 | 2011-06-14 17:00 |  |  | 8 | 0 | 8 | Task
15 | \Phase 2 | \80 Project Management | dio | 1 | To start WBS tasks breakdown , split tasks among team | To start WBS tasks breakdown , split tasks among team - Split UCRR tasks for all members - Split High level specs among Zaw, Feng Yan, Peishan and Thida - To get status update before 24 June 2011 | Closed |  | 2011-07-01 18:56 | 2011-08-30 18:56 |  |  | 0 | 0 | 12 | Task
17 | \Phase 2 | \30 Prototype\32 Architecture Prototye | dio | 2 | To review Database system for Prototype study report from Jifa | To review Database system for Prototype study report from Jifa | Closed |  | 2011-06-01 17:47 | 2011-07-07 17:47 | dio | 2011-08-13 17:48 | 4 | 4 | 0 | Task
18 | \Phase 2 | \30 Prototype | dio | 1 | Testing review my report tool | pls check for me | Closed |  | 2011-08-14 00:24 | 2011-08-14 00:24 | thida | 2011-06-11 16:48 | 8 | 0 | 8 | Task
20 | \Phase 2 | \80 Project Management | dio | 2 | To explorer TFS template, modify the project template to match ISS and project context | To customize TFS template with task workflow, item workflow that match the ISS project waterfall model. For e.g: To add more discipline into Tasks | Closed |  | 2011-08-13 00:23 | 2011-08-14 00:23 |  |  | 8 | 0 | 8 | Task
27 | \Phase 2 | \80 Project Management | dio | 2 | For the task tracking, use the TFS to generate the progress report and check in to the SVN | For the task tracking, use the TFS to generate the progress report and check in to the SVN | Closed |  | 2011-08-13 16:31 | 2011-08-20 16:31 |  |  | 8 | 0 | 8 | Task
36 | \Phase 2 | \70 Report\72 Presentation Phase 2 | dio | 2 | Presentation - Project Background (2 Slides) | To prepare slides for presentation (project background) | Closed |  | 2011-08-13 00:41 | 2011-08-20 |  |  | 8 | 0 | 8 | Task
37 | \Phase 2 | \70 Report\72 Presentation Phase 2 | dio | 2 | Presentation - Global Use Case Modelling Picture | To create UCMS for presentation | Closed |  | 2011-08-13 00:41 | 2011-08-20 |  |  | 8 | 0 | 8 | Task
38 | \Phase 2 | \70 Report\72 Presentation Phase 2 | dio | 2 | Select Two use case for Demo Decompose / Explain for chosen use cases | To select 2 use cases for Phase 2 presentation | Closed |  | 2011-08-13 00:41 | 2011-08-20 |  |  | 8 | 8 | 0 | Task
40 | \Phase 2 | \70 Report\72 Presentation Phase 2 | dio | 2 | Progress (Which task takes longer… Implementation Plan (what u r going to finish….) | To show the current progress of Phase 2 | Closed |  | 2011-08-13 00:41 | 2011-08-20 |  |  | 8 | 8 | 0 | Task
42 | \Phase 1 | \80 Project Management | dio | 1 | To modify TFS Template to match MTECH workflow | - Created Phases & Iterations to match MTECH architecture | Closed |  | 2011-08-13 19:01 | 2011-08-14 19:01 |  |  | 4 | 0 | 4 | Task
51 | \Phase 3 | \50 Build\50 UI design | dio | 2 | To produce completed UI design of the whole system (include all pages) - prepare before development start | Requirements: - All UI design for all pages - Design for main page, home screen - Involve navigation and flow | Assigned |  | 2011-08-21 22:30 | 2011-08-28 22:30 |  |  | 30 | 30 | 0 | Task
21 | \Phase 2 | \80 Project Management | fengyan | 2 | To explore how to use SVN Bug tracker, and how to generate project reports from SVN | - To explore how to use SVN Bug tracker, and how to generate project reports from SVN. For e.g: - How to integrate SVN bug tracker into Eclipse - How to generate report on active/closed/pending bugs - Generate report on code coverage during testing stage - Generate report on requirements coverage during testing stage | In progress |  | 2011-08-13 00:41 | 2011-08-20 |  |  | 12 | 11 | 1 | Task
4 | \Phase 2 | \30 Prototype\31 UI Prototype | hazel | 1 | To create User Interface Prototype draft 1 | To prepare User Interface Prototype for putative user to review, by 28th May 2011 | Closed |  | 2011-06-05 08:00 | 2011-06-16 17:00 | hazel | 2011-08-21 22:30 | 16 | 6 | 10 | Task
30 | \Phase 3 | \60 Test | jifa | 2 | Produce Test Plan | To produce detailed Test Plan (maybe based on Unit 7 materials) | In progress |  | 2011-08-13 00:41 | 2011-08-20 |  |  | 8 | 8 | 0 | Task
31 | \Phase 3 | \60 Test | jifa | 2 | To produce Full Test Script for all use cases | To produce Full Test Script for all use cases | In progress |  | 2011-08-13 00:41 | 2011-08-20 |  |  | 8 | 8 | 0 | Task
32 | \Phase 3 | \90 Quality Management | jifa | 2 | Create Review Form for all outstanding deliverables (High level Architecture Design, Prototype Study Report, Transition Strategy) | Create Review Form for all outstanding deliverables (High level Architecture Design, Prototype Study Report, Transition Strategy) | In progress |  | 2011-08-13 00:41 | 2011-08-20 |  |  | 8 | 8 | 0 | Task
11 | \Phase 2 | \30 Prototype\33 Prototype Study Report | jifa | 2 | To compare Database system for Prototype study report | To compare Database system for Prototype study report | Closed |  | 2011-08-13 00:41 | 2011-08-20 | jifa | 2011-06-10 08:59 | 8 | 0 | 8 | Task
39 | \Phase 2 | \70 Report\72 Presentation Phase 2 | peishan | 2 | High level Design (Prepare for technical Question) Prototype (Technical Issue/Risk/learned….) | High level Design (Prepare for technical Question) Prototype (Technical Issue/Risk/learned….) | Resolved |  | 2011-08-13 00:41 | 2011-08-20 | peishan | 2011-08-21 18:26 | 8 | 8 | 0 | Task
25 | \Phase 3 | \90 Quality Management | peishan | 2 | Separate Internal Meeting Minutes and Quality Audit Meeting Minutes | Separate Internal Meeting Minutes and Quality Audit Meeting Minutes | In progress |  | 2011-08-13 00:41 | 2011-08-20 |  |  | 8 | 8 | 0 | Task
34 | \Phase 3 | \90 Quality Management | peishan | 3 | Put the indexing file to some specific required folder(E.g Analysis) | Put the indexing file to some specific required folder(E.g Analysis) | In progress |  | 2011-08-13 00:41 | 2011-08-20 |  |  | 8 | 8 | 0 | Task
7 | \Phase 2 | \30 Prototype\33 Prototype Study Report | peishan | 2 | To compare UI AJAX Prototype | To compare UI AJAX Prototype for Prototype Study Report | Closed |  | 2011-06-01 08:00 | 2011-08-20 |  |  | 8 | 8 |  | Task
13 | \Phase 2 | \30 Prototype\33 Prototype Study Report | peishan | 2 | To consolidate all parts to produce prototype study report | To consolidate all parts to product prototype study report | Closed |  | 2011-06-01 08:00 | 2011-08-20 |  |  | 16 | 0 | 16 | Task
19 | \Phase 2 | \80 Project Management | se18team8s | 2 | Get familiar with Team Foundation Server - know how to manage task/bug/issue status | Get familiar with Team Foundation Server - Know how to create/update/close tasks - Know how to create/update/close requirement / assignment | In progress |  | 2011-08-13 00:41 | 2011-08-20 |  |  | 8 | 8 | 0 | Task
26 | \Phase 3 | \90 Quality Management | se18team8s | 2 | Update the document reference to the document header beside the system name (the coming deliverables) | Update the document reference to the document header beside the system name (the coming deliverables) | In progress |  | 2011-08-13 00:41 | 2011-08-20 |  |  | 8 | 8 | 0 | Task
22 | \Phase 2 | \20 Analysis\22 Use Case Realization Report (Analysis) | se18team8s | 1 | Produce UCRR - Analysis | Complete UCRR (analysis ) for these Use case : 1. Login / Logout 2. Change password 3. Forget password 4. Register User Account 5. Update Profile 7. Raise Project Interest 8. Proposa Project 9. Post Experience 10. Post Feedback 11. Request for Certificate | Closed |  | 2011-08-13 00:41 | 2011-08-20 |  |  | 24 | 0 | 24 | Task
33 | \Phase 3 | \90 Quality Management | thida | 1 | Update and Review all the UCRR (Analysis) | Update and Review all the UCRR (analysis) correctness | In progress |  | 2011-08-13 00:41 | 2011-08-24 |  |  | 8 | 8 | 0 | Task
24 | \Phase 2 | \20 Analysis | thida | 2 | Combine UCMS, UCRR into 1 document | Combine UCMS, UCRR into 1 document | Closed |  | 2011-08-13 00:41 | 2011-08-20 | dio | 2011-08-21 18:14 | 8 | 0 | 8 | Task
50 | \Phase 3 | \30 Prototype | zaw | 2 | To complete prototype - get at least 1 use case working end-to-end (include AJAX-DWR) | To complete prototype - get at least 1 use case working end-to-end (include AJAX-DWR) | Assigned |  | 2011-08-22 | 2011-08-29 |  |  | 50 | 50 | 0 | Task
6 | \Phase 2 | \30 Prototype\33 Prototype Study Report | zaw | 2 | To compare AJAX Framework for Prototype study report | To compare AJAX Framework for Prototype study report To be use in Prototype study report | Closed |  | 2011-08-13 00:41 | 2011-08-20 |  |  | 8 | 0 | 8 | Task
8 | \Phase 2 | \30 Prototype\33 Prototype Study Report | zaw | 2 | To compare Framework Prototype for Prototype Study Report | To compare Framework Prototype for Prototype Study Report | Closed |  | 2011-06-01 08:00 | 2011-08-20 | zaw | 2011-08-21 18:27 | 8 | 8 | 0 | Task
9 | \Phase 2 | \30 Prototype\32 Architecture Prototye | zaw | 2 | To produce Data Access Layer Prototype | To produce Data Access Layer Prototype | Closed |  | 2011-06-01 08:00 | 2011-06-14 17:00 |  |  | 16 | 0 | 16 | Task
12 | \Phase 2 | \30 Prototype | zaw | 1 | to produce End to end Prototype draft 1 | to produce End to end Prototype draft 1 | Closed |  | 2011-06-01 08:00 | 2011-06-14 17:00 |  |  | 16 | 0 | 16 | Task

## VSTS_ValidationWS_1 (hidden)
value doesn't matter | value doesn't matter | 2011-08-22 14:36 | value doesn't matter | admin | Active | admin | Active | admin | Active | admin | Active | admin | Active | admin | admin | Active | admin | 1 | admin | admin | Active | admin | 1 | admin | admin | Active | admin | 1 | admin | admin | Active | admin | 1 | admin | admin | Active | admin | admin | admin | Active | admin | 1 | admin | admin | admin | Active | admin | Active | admin | Assigned | admin | Closed | Bug | admin | Active | \ | \ | admin | Active | Active | admin | Active | admin | Active | admin | Active | admin | Active | admin | Active | admin | Active | admin | Active | admin | Assigned | admin | Closed | Bug | admin | Active | Bug | admin | Design | admin | admin | admin | admin | Active | 1 | admin | admin | Assigned | admin | 1 | admin | admin | Closed | 1 | admin | admin | admin | Active | admin | 1 | \ | \ | admin | Assigned | 1 | Closed | Assigned | admin | admin | admin | admin | admin | \ | \ | Approved | Abandoned | Accepted | Abandoned | Accepted (as is) | Accepted (won't mitigate) | Deferred | Accepted | Completed | Approved | New | Closed | admin | Active | admin | Active | admin | Active | admin | Active | admin | Active | admin | Closed | Bug | Active | admin | Active | admin | Assigned | admin | Closed | Bug | admin | Active | \ | \ | admin | Closed | Assigned | Active | Closed
readOnlyTestRange_@ | readOnlyTestRange_0 | readOnlyTestRange_dd-MMM-yy h:mm AM/PM | readOnlyTestRange_General | dio | Closed | dio | Closed | dio | Closed | dio | Closed | dio | Closed | dio | dio | Closed | dio | 2 | dio | dio | Closed | dio | 2 | dio | dio | Closed | dio | 2 | dio | dio | Closed | dio | 2 | dio | dio | Closed | dio | dio | dio | Closed | dio | 2 | dio | dio | dio | Closed | dio | Closed | dio | Closed | dio | Design | Change Request | dio | Closed | \10 Requirements | \Phase 1 | dio | Closed | Proposed | dio | Closed | dio | Closed | dio | Closed | dio | Closed | dio | Closed | dio | Closed | dio | Closed | dio | Closed | dio | Design | Change Request | dio | Closed | Change Request | dio | VSTS_af75de3b_2602_44c8_b56f_847d84f808bd_13-BF-0E-11-6E-4D-41-8B-C1-69-64-FF-3E-CD-DE-18-56-FF-29-3F | dio | dio | dio | dio | Closed | 2 | dio | dio | Closed | dio | 2 | dio | dio | Design | 2 | dio | dio | dio | Closed | dio | 2 | \10 Requirements | \Phase 1 | dio | Closed | 2 | In progress | Closed | dio | dio | dio | dio | dio | \10 Requirements | \Phase 1 | As Designed | Accepted | Closed in Error | Accepted | Accepted with Major Changes | Closed in Error | Duplicate | Cancelled | Deferred | As Designed | VSTS_af75de3b_2602_44c8_b56f_847d84f808bd_EC-0F-7A-13-B7-B8-F1-00-EB-63-A3-B5-07-10-E1-15-11-B0-2B-46 | Design | dio | Closed | dio | Closed | dio | Closed | dio | Closed | dio | Closed | dio | In progress | Change Request | Closed | dio | Closed | dio | Closed | dio | Design | Change Request | dio | Closed | \10 Requirements | \Phase 1 | dio | In progress | Closed | Proposed | Design
|  |  |  | fengyan | Proposed | fengyan | Proposed | fengyan | Proposed | fengyan | Proposed | fengyan | Resolved | fengyan | fengyan | Proposed | fengyan | 3 | fengyan | fengyan | Proposed | fengyan | 3 | fengyan | fengyan | Proposed | fengyan | 3 | fengyan | fengyan | Proposed | fengyan | 3 | fengyan | fengyan | Resolved | fengyan | fengyan | fengyan | Proposed | fengyan | 3 | fengyan | fengyan | fengyan | Proposed | fengyan | all_VSTS_b27ef33b_290b_440a_ace5_e920054f3c20_Shared Steps_System.State | fengyan | In progress | fengyan | Ready | Issue | fengyan | Proposed | \20 Analysis | \Phase 2 | fengyan | VSTS_b27ef33b_290b_440a_ace5_e920054f3c20_C0-8B-87-81-67-52-71-76-29-2A-B8-4D-FB-D4-D6-6F-1E-E5-D9-2A | Resolved | fengyan | Proposed | fengyan | Proposed | fengyan | Proposed | fengyan | Proposed | fengyan | Resolved | fengyan | Proposed | fengyan | all_VSTS_af75de3b_2602_44c8_b56f_847d84f808bd_Shared Steps_System.State | fengyan | In progress | fengyan | Ready | Issue | fengyan | Proposed | Issue | fengyan |  | fengyan | fengyan | fengyan | fengyan | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Shared Steps_System.State | 3 | fengyan | fengyan | In progress | fengyan | 3 | fengyan | fengyan | Ready | 3 | fengyan | fengyan | fengyan | Proposed | fengyan | 3 | \20 Analysis | \Phase 2 | fengyan | In progress | 3 | VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_50-5B-D0-C6-4D-02-A8-6F-40-65-26-EB-25-5E-77-D6-47-52-6D-6C | In progress | fengyan | fengyan | fengyan | fengyan | fengyan | \20 Analysis | \Phase 2 | Build Failure | Closed in Error | Investigate | Closed in Error | Accepted with Minor Changes | Eliminated | New | Closed in Error | Duplicate | Build Failure |  | Ready | fengyan | Proposed | fengyan | Proposed | fengyan | Proposed | fengyan | Proposed | fengyan | Resolved | fengyan | Resolved | Issue | Proposed | fengyan | all_VSTS_9008c800_2551_458e_9040_a57c55b05a6f_Shared Steps_System.State | fengyan | In progress | fengyan | Ready | Issue | fengyan | Proposed | \20 Analysis | \Phase 2 | fengyan | VSTS_9008c800_2551_458e_9040_a57c55b05a6f_50-5B-D0-C6-4D-02-A8-6F-40-65-26-EB-25-5E-77-D6-47-52-6D-6C | In progress | Resolved | Ready
|  |  |  | hazel | Resolved | hazel | Resolved | hazel | Resolved | hazel | Resolved | hazel | all_VSTS_b27ef33b_290b_440a_ace5_e920054f3c20_Review_System.State | hazel | hazel | Resolved | hazel | 4 | hazel | hazel | Resolved | hazel | 4 | hazel | hazel | Resolved | hazel | 4 | hazel | hazel | Resolved | hazel | 4 | hazel | hazel | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Review_System.State | hazel | hazel | hazel | Resolved | hazel | 4 | hazel | hazel | hazel | Resolved | hazel |  | hazel | Resolved | hazel | all_VSTS_b27ef33b_290b_440a_ace5_e920054f3c20_Test Case_System.State | Requirement | hazel | Resolved | \20 Analysis\21 Use Case Model Survey | \Phase 3 | hazel |  | VSTS_b27ef33b_290b_440a_ace5_e920054f3c20_F6-86-31-A3-47-27-76-CB-57-28-49-17-32-EB-97-93-07-11-CC-4D | hazel | Resolved | hazel | Resolved | hazel | Resolved | hazel | Resolved | hazel | all_VSTS_af75de3b_2602_44c8_b56f_847d84f808bd_Review_System.State | hazel | Resolved | hazel |  | hazel | Resolved | hazel | all_VSTS_af75de3b_2602_44c8_b56f_847d84f808bd_Test Case_System.State | Requirement | hazel | Resolved | Requirement | hazel |  | hazel | hazel | hazel | hazel |  | 4 | hazel | hazel | Resolved | hazel | 4 | hazel | hazel | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Test Case_System.State | 4 | hazel | hazel | hazel | Resolved | hazel | 4 | \20 Analysis\21 Use Case Model Survey | \Phase 3 | hazel | Resolved | 4 |  | VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_8B-D1-53-A2-A6-FB-4F-03-24-65-B4-29-73-CC-D1-C9-B6-3C-6A-90 | hazel | hazel | hazel | hazel | hazel | \20 Analysis\21 Use Case Model Survey | \Phase 3 | Cannot Reproduce | Code Complete and System Tested | Investigation Complete | Code Complete and System Test Passed | Closed in Error | Mitigated | Obsolete | Complete and Does Not Require Review/Test | New | Cannot Reproduce |  | VSTS_af75de3b_2602_44c8_b56f_847d84f808bd_E4-CA-08-0D-C5-01-AB-82-96-6F-B8-39-E9-3E-EA-3F-57-42-86-2A | hazel | Resolved | hazel | Resolved | hazel | Resolved | hazel | Resolved | hazel | all_VSTS_9008c800_2551_458e_9040_a57c55b05a6f_Review_System.State | hazel | VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_6F-C6-D8-EB-43-26-13-F5-A3-D3-8B-09-48-94-22-7A-77-AF-E5-C2 | Requirement | Resolved | hazel |  | hazel | Resolved | hazel | all_VSTS_9008c800_2551_458e_9040_a57c55b05a6f_Test Case_System.State | Requirement | hazel | Resolved | \20 Analysis\21 Use Case Model Survey | \Phase 3 | hazel |  | Resolved | VSTS_9008c800_2551_458e_9040_a57c55b05a6f_F6-86-31-A3-47-27-76-CB-57-28-49-17-32-EB-97-93-07-11-CC-4D | VSTS_9008c800_2551_458e_9040_a57c55b05a6f_E4-CA-08-0D-C5-01-AB-82-96-6F-B8-39-E9-3E-EA-3F-57-42-86-2A
|  |  |  | jifa | all_VSTS_b27ef33b_290b_440a_ace5_e920054f3c20_Bug_System.State | jifa | all_VSTS_b27ef33b_290b_440a_ace5_e920054f3c20_Change Request_System.State | jifa | all_VSTS_b27ef33b_290b_440a_ace5_e920054f3c20_Issue_System.State | jifa | all_VSTS_b27ef33b_290b_440a_ace5_e920054f3c20_Requirement_System.State | jifa |  | jifa | jifa | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Bug_System.State | jifa | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Bug_Microsoft.VSTS.Common.Priority | jifa | jifa | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Change Request_System.State | jifa | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Change Request_Microsoft.VSTS.Common.Priority | jifa | jifa | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Issue_System.State | jifa | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Issue_Microsoft.VSTS.Common.Priority | jifa | jifa | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Requirement_System.State | jifa | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Requirement_Microsoft.VSTS.Common.Priority | jifa | jifa |  | jifa | jifa | jifa | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Risk_System.State | jifa | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Risk_Microsoft.VSTS.Common.Priority | jifa | jifa | jifa | all_VSTS_b27ef33b_290b_440a_ace5_e920054f3c20_Risk_System.State | jifa |  | jifa | all_VSTS_b27ef33b_290b_440a_ace5_e920054f3c20_Task_System.State | jifa |  | Review | jifa | Assigned | \20 Analysis\22 Use Case Realization Report (Analysis) | all_VSTS_b27ef33b_290b_440a_ace5_e920054f3c20_System.IterationPath | jifa |  |  | jifa | all_VSTS_af75de3b_2602_44c8_b56f_847d84f808bd_Bug_System.State | jifa | all_VSTS_af75de3b_2602_44c8_b56f_847d84f808bd_Change Request_System.State | jifa | all_VSTS_af75de3b_2602_44c8_b56f_847d84f808bd_Issue_System.State | jifa | all_VSTS_af75de3b_2602_44c8_b56f_847d84f808bd_Requirement_System.State | jifa |  | jifa | all_VSTS_af75de3b_2602_44c8_b56f_847d84f808bd_Risk_System.State | jifa |  | jifa | all_VSTS_af75de3b_2602_44c8_b56f_847d84f808bd_Task_System.State | jifa |  | Review | jifa | Assigned | Review | jifa |  | jifa | jifa | jifa | jifa |  | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Shared Steps_Microsoft.VSTS.Common.Priority | jifa | jifa | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Task_System.State | jifa | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Task_Microsoft.VSTS.Common.Priority | jifa | jifa |  | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Test Case_Microsoft.VSTS.Common.Priority | jifa | jifa | jifa | Assigned | jifa | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Microsoft.VSTS.Common.Priority | \20 Analysis\22 Use Case Realization Report (Analysis) | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_System.IterationPath | jifa | VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_9F-F6-0F-1C-08-6A-BA-DC-02-F0-E1-1F-9D-C4-DD-F3-E1-46-6F-4A | VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_A9-74-3C-60-20-83-BF-D2-70-44-DA-6E-AF-8C-55-96-9A-24-CE-B3 |  |  | jifa | jifa | jifa | jifa | jifa | \20 Analysis\22 Use Case Realization Report (Analysis) | all_VSTS_af75de3b_2602_44c8_b56f_847d84f808bd_System.IterationPath | Closed in Error | Investigate | New | Investigate | Major Changes Complete | Mitigation Action Complete | Reactivated | Complete and Requires Review/Test | Obsolete | Closed in Error |  |  | jifa | all_VSTS_9008c800_2551_458e_9040_a57c55b05a6f_Bug_System.State | jifa | all_VSTS_9008c800_2551_458e_9040_a57c55b05a6f_Change Request_System.State | jifa | all_VSTS_9008c800_2551_458e_9040_a57c55b05a6f_Issue_System.State | jifa | all_VSTS_9008c800_2551_458e_9040_a57c55b05a6f_Requirement_System.State | jifa |  | jifa |  | Review | all_VSTS_9008c800_2551_458e_9040_a57c55b05a6f_Risk_System.State | jifa |  | jifa | all_VSTS_9008c800_2551_458e_9040_a57c55b05a6f_Task_System.State | jifa |  | Review | jifa | Assigned | \20 Analysis\22 Use Case Realization Report (Analysis) | all_VSTS_9008c800_2551_458e_9040_a57c55b05a6f_System.IterationPath | jifa |  | VSTS_9008c800_2551_458e_9040_a57c55b05a6f_9F-F6-0F-1C-08-6A-BA-DC-02-F0-E1-1F-9D-C4-DD-F3-E1-46-6F-4A
|  |  |  | LOCAL SERVICE |  | LOCAL SERVICE |  | LOCAL SERVICE |  | LOCAL SERVICE |  | LOCAL SERVICE |  | LOCAL SERVICE | LOCAL SERVICE |  | LOCAL SERVICE |  | LOCAL SERVICE | LOCAL SERVICE |  | LOCAL SERVICE |  | LOCAL SERVICE | LOCAL SERVICE |  | LOCAL SERVICE |  | LOCAL SERVICE | LOCAL SERVICE |  | LOCAL SERVICE |  | LOCAL SERVICE | LOCAL SERVICE |  | LOCAL SERVICE | LOCAL SERVICE | LOCAL SERVICE |  | LOCAL SERVICE |  | LOCAL SERVICE | LOCAL SERVICE | LOCAL SERVICE |  | LOCAL SERVICE |  | LOCAL SERVICE |  | LOCAL SERVICE |  | Risk | LOCAL SERVICE | In progress | \30 Prototype |  | LOCAL SERVICE |  |  | LOCAL SERVICE |  | LOCAL SERVICE |  | LOCAL SERVICE |  | LOCAL SERVICE |  | LOCAL SERVICE |  | LOCAL SERVICE |  | LOCAL SERVICE |  | LOCAL SERVICE |  | LOCAL SERVICE |  | Risk | LOCAL SERVICE | In progress | Risk | LOCAL SERVICE |  | LOCAL SERVICE | LOCAL SERVICE | LOCAL SERVICE | LOCAL SERVICE |  |  | LOCAL SERVICE | LOCAL SERVICE |  | LOCAL SERVICE |  | LOCAL SERVICE | LOCAL SERVICE |  |  | LOCAL SERVICE | LOCAL SERVICE | LOCAL SERVICE | In progress | LOCAL SERVICE |  | \30 Prototype |  | LOCAL SERVICE |  |  |  |  | LOCAL SERVICE | LOCAL SERVICE | LOCAL SERVICE | LOCAL SERVICE | LOCAL SERVICE | \30 Prototype |  | Deferred | Investigation Complete | Overtaken by events | Investigation Complete | Minor Changes Complete | Mitigation Action Unsatisfactory (rework) | all_VSTS_af75de3b_2602_44c8_b56f_847d84f808bd_Shared Steps_System.Reason | Cut | Reactivated | Deferred |  |  | LOCAL SERVICE |  | LOCAL SERVICE |  | LOCAL SERVICE |  | LOCAL SERVICE |  | LOCAL SERVICE |  | LOCAL SERVICE |  | Risk |  | LOCAL SERVICE |  | LOCAL SERVICE |  | LOCAL SERVICE |  | Risk | LOCAL SERVICE | In progress | \30 Prototype |  | LOCAL SERVICE
|  |  |  | peishan |  | peishan |  | peishan |  | peishan |  | peishan |  | peishan | peishan |  | peishan |  | peishan | peishan |  | peishan |  | peishan | peishan |  | peishan |  | peishan | peishan |  | peishan |  | peishan | peishan |  | peishan | peishan | peishan |  | peishan |  | peishan | peishan | peishan |  | peishan |  | peishan |  | peishan |  | Shared Steps | peishan | Design | \30 Prototype\31 UI Prototype |  | peishan |  |  | peishan |  | peishan |  | peishan |  | peishan |  | peishan |  | peishan |  | peishan |  | peishan |  | peishan |  | Shared Steps | peishan | Design | Shared Steps | peishan |  | peishan | peishan | peishan | peishan |  |  | peishan | peishan |  | peishan |  | peishan | peishan |  |  | peishan | peishan | peishan | Design | peishan |  | \30 Prototype\31 UI Prototype |  | peishan |  |  |  |  | peishan | peishan | peishan | peishan | peishan | \30 Prototype\31 UI Prototype |  | Duplicate | New | Rejected (not an issue) | New | New | Mitigation Triggered |  | Deferred | Update Test Case | Duplicate |  |  | peishan |  | peishan |  | peishan |  | peishan |  | peishan |  | peishan |  | Shared Steps |  | peishan |  | peishan |  | peishan |  | Shared Steps | peishan | Design | \30 Prototype\31 UI Prototype |  | peishan
|  |  |  | se18team8s |  | se18team8s |  | se18team8s |  | se18team8s |  | se18team8s |  | se18team8s | se18team8s |  | se18team8s |  | se18team8s | se18team8s |  | se18team8s |  | se18team8s | se18team8s |  | se18team8s |  | se18team8s | se18team8s |  | se18team8s |  | se18team8s | se18team8s |  | se18team8s | se18team8s | se18team8s |  | se18team8s |  | se18team8s | se18team8s | se18team8s |  | se18team8s |  | se18team8s |  | se18team8s |  | Task | se18team8s | Ready | \30 Prototype\32 Architecture Prototye |  | se18team8s |  |  | se18team8s |  | se18team8s |  | se18team8s |  | se18team8s |  | se18team8s |  | se18team8s |  | se18team8s |  | se18team8s |  | se18team8s |  | Task | se18team8s | Ready | Task | se18team8s |  | se18team8s | se18team8s | se18team8s | se18team8s |  |  | se18team8s | se18team8s |  | se18team8s |  | se18team8s | se18team8s |  |  | se18team8s | se18team8s | se18team8s | Ready | se18team8s |  | \30 Prototype\32 Architecture Prototye |  | se18team8s |  |  |  |  | se18team8s | se18team8s | se18team8s | se18team8s | se18team8s | \30 Prototype\32 Architecture Prototye |  | Fixed | Out-of-scope | Re-occurred | Out-of-scope | all_VSTS_af75de3b_2602_44c8_b56f_847d84f808bd_Review_System.Reason | New |  | Investigate | all_VSTS_af75de3b_2602_44c8_b56f_847d84f808bd_Test Case_System.Reason | Fixed |  |  | se18team8s |  | se18team8s |  | se18team8s |  | se18team8s |  | se18team8s |  | se18team8s |  | Task |  | se18team8s |  | se18team8s |  | se18team8s |  | Task | se18team8s | Ready | \30 Prototype\32 Architecture Prototye |  | se18team8s
|  |  |  | thida |  | thida |  | thida |  | thida |  | thida |  | thida | thida |  | thida |  | thida | thida |  | thida |  | thida | thida |  | thida |  | thida | thida |  | thida |  | thida | thida |  | thida | thida | thida |  | thida |  | thida | thida | thida |  | thida |  | thida |  | thida |  | Test Case | thida | all_VSTS_b27ef33b_290b_440a_ace5_e920054f3c20_System.State | \30 Prototype\33 Prototype Study Report |  | thida |  |  | thida |  | thida |  | thida |  | thida |  | thida |  | thida |  | thida |  | thida |  | thida |  | Test Case | thida | all_VSTS_af75de3b_2602_44c8_b56f_847d84f808bd_System.State | Test Case | thida |  | thida | thida | thida | thida |  |  | thida | thida |  | thida |  | thida | thida |  |  | thida | thida | thida | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_System.State | thida |  | \30 Prototype\33 Prototype Study Report |  | thida |  |  |  |  | thida | thida | thida | thida | thida | \30 Prototype\33 Prototype Study Report |  | Investigate | Rejected | Re-opened | Postponed |  | Overtaken by events |  | Investigation Complete |  | Investigate |  |  | thida |  | thida |  | thida |  | thida |  | thida |  | thida |  | Test Case |  | thida |  | thida |  | thida |  | Test Case | thida | all_VSTS_9008c800_2551_458e_9040_a57c55b05a6f_System.State | \30 Prototype\33 Prototype Study Report |  | thida
|  |  |  | zaw |  | zaw |  | zaw |  | zaw |  | zaw |  | zaw | zaw |  | zaw |  | zaw | zaw |  | zaw |  | zaw | zaw |  | zaw |  | zaw | zaw |  | zaw |  | zaw | zaw |  | zaw | zaw | zaw |  | zaw |  | zaw | zaw | zaw |  | zaw |  | zaw |  | zaw |  | all_VSTS_b27ef33b_290b_440a_ace5_e920054f3c20_System.WorkItemType | zaw |  | \40 Design |  | zaw |  |  | zaw |  | zaw |  | zaw |  | zaw |  | zaw |  | zaw |  | zaw |  | zaw |  | zaw |  | all_VSTS_af75de3b_2602_44c8_b56f_847d84f808bd_System.WorkItemType | zaw |  | VSTS_af75de3b_2602_44c8_b56f_847d84f808bd_4F-DF-70-5A-5E-58-89-30-F3-EC-F6-04-C2-E7-A9-98-CA-BD-C1-48 | zaw |  | zaw | zaw | zaw | zaw |  |  | zaw | zaw |  | zaw |  | zaw | zaw |  |  | zaw | zaw | zaw |  | zaw |  | \40 Design |  | zaw |  |  |  |  | zaw | zaw | zaw | zaw | zaw | \40 Design |  | Investigation Complete | Validation Test Failed | Resolution Verified and Accepted | Reintroduced in Scope |  | Rejected |  | New |  | Investigation Complete |  |  | zaw |  | zaw |  | zaw |  | zaw |  | zaw |  | zaw |  | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_System.WorkItemType |  | zaw |  | zaw |  | zaw |  | all_VSTS_9008c800_2551_458e_9040_a57c55b05a6f_System.WorkItemType | zaw |  | \40 Design |  | zaw
|  |  |  | all_VSTS_b27ef33b_290b_440a_ace5_e920054f3c20_Bug_System.AssignedTo |  | all_VSTS_b27ef33b_290b_440a_ace5_e920054f3c20_Change Request_System.AssignedTo |  | all_VSTS_b27ef33b_290b_440a_ace5_e920054f3c20_Issue_System.AssignedTo |  | all_VSTS_b27ef33b_290b_440a_ace5_e920054f3c20_Requirement_System.AssignedTo |  | all_VSTS_b27ef33b_290b_440a_ace5_e920054f3c20_Review_System.AssignedTo |  | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Bug_System.AssignedTo | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Bug_Microsoft.VSTS.Common.ClosedBy |  | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Bug_Microsoft.VSTS.Common.ResolvedBy |  | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Change Request_System.AssignedTo | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Change Request_Microsoft.VSTS.Common.ClosedBy |  | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Change Request_Microsoft.VSTS.Common.ResolvedBy |  | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Issue_System.AssignedTo | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Issue_Microsoft.VSTS.Common.ClosedBy |  | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Issue_Microsoft.VSTS.Common.ResolvedBy |  | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Requirement_System.AssignedTo | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Requirement_Microsoft.VSTS.Common.ClosedBy |  | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Requirement_Microsoft.VSTS.Common.ResolvedBy |  | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Review_System.AssignedTo | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Review_Microsoft.VSTS.Common.ClosedBy |  | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Review_Microsoft.VSTS.Common.ResolvedBy | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Risk_System.AssignedTo | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Risk_Microsoft.VSTS.Common.ClosedBy |  | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Risk_Microsoft.VSTS.Common.ResolvedBy |  | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Shared Steps_System.AssignedTo | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Shared Steps_Microsoft.VSTS.Common.ClosedBy | all_VSTS_b27ef33b_290b_440a_ace5_e920054f3c20_Risk_System.AssignedTo |  | all_VSTS_b27ef33b_290b_440a_ace5_e920054f3c20_Shared Steps_System.AssignedTo |  | all_VSTS_b27ef33b_290b_440a_ace5_e920054f3c20_Task_System.AssignedTo |  | all_VSTS_b27ef33b_290b_440a_ace5_e920054f3c20_Test Case_System.AssignedTo |  |  | all_VSTS_b27ef33b_290b_440a_ace5_e920054f3c20_System.AssignedTo |  | \40 Design\41 High level architecture |  | VSTS_b27ef33b_290b_440a_ace5_e920054f3c20_63-3D-6E-FD-05-A5-E3-0A-3D-3B-27-25-0E-09-89-A2-24-50-7D-FA |  |  | all_VSTS_af75de3b_2602_44c8_b56f_847d84f808bd_Bug_System.AssignedTo |  | all_VSTS_af75de3b_2602_44c8_b56f_847d84f808bd_Change Request_System.AssignedTo |  | all_VSTS_af75de3b_2602_44c8_b56f_847d84f808bd_Issue_System.AssignedTo |  | all_VSTS_af75de3b_2602_44c8_b56f_847d84f808bd_Requirement_System.AssignedTo |  | all_VSTS_af75de3b_2602_44c8_b56f_847d84f808bd_Review_System.AssignedTo |  | all_VSTS_af75de3b_2602_44c8_b56f_847d84f808bd_Risk_System.AssignedTo |  | all_VSTS_af75de3b_2602_44c8_b56f_847d84f808bd_Shared Steps_System.AssignedTo |  | all_VSTS_af75de3b_2602_44c8_b56f_847d84f808bd_Task_System.AssignedTo |  | all_VSTS_af75de3b_2602_44c8_b56f_847d84f808bd_Test Case_System.AssignedTo |  |  | all_VSTS_af75de3b_2602_44c8_b56f_847d84f808bd_System.AssignedTo |  |  | VSTS_af75de3b_2602_44c8_b56f_847d84f808bd_63-3D-6E-FD-05-A5-E3-0A-3D-3B-27-25-0E-09-89-A2-24-50-7D-FA |  | all_VSTS_af75de3b_2602_44c8_b56f_847d84f808bd_Bug_Microsoft.VSTS.Common.ActivatedBy | all_VSTS_af75de3b_2602_44c8_b56f_847d84f808bd_Change Request_Microsoft.VSTS.Common.ActivatedBy | all_VSTS_af75de3b_2602_44c8_b56f_847d84f808bd_Issue_Microsoft.VSTS.Common.ActivatedBy | all_VSTS_af75de3b_2602_44c8_b56f_847d84f808bd_Requirement_Microsoft.VSTS.Common.ActivatedBy |  |  | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Task_System.AssignedTo | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Task_Microsoft.VSTS.Common.ClosedBy |  | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Task_Microsoft.VSTS.Common.ResolvedBy |  | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Test Case_System.AssignedTo | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Test Case_Microsoft.VSTS.Common.ClosedBy |  |  | all_VSTS_af75de3b_2602_44c8_b56f_847d84f808bd_Review_Microsoft.VSTS.Common.ActivatedBy | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_System.AssignedTo | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Microsoft.VSTS.Common.ClosedBy |  | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Microsoft.VSTS.Common.ResolvedBy |  | \40 Design\41 High level architecture |  | VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_63-3D-6E-FD-05-A5-E3-0A-3D-3B-27-25-0E-09-89-A2-24-50-7D-FA |  |  |  |  | all_VSTS_af75de3b_2602_44c8_b56f_847d84f808bd_Risk_Microsoft.VSTS.Common.ActivatedBy | all_VSTS_af75de3b_2602_44c8_b56f_847d84f808bd_Shared Steps_Microsoft.VSTS.Common.ActivatedBy | all_VSTS_af75de3b_2602_44c8_b56f_847d84f808bd_Task_Microsoft.VSTS.Common.ActivatedBy | all_VSTS_af75de3b_2602_44c8_b56f_847d84f808bd_Test Case_Microsoft.VSTS.Common.ActivatedBy | all_VSTS_af75de3b_2602_44c8_b56f_847d84f808bd_Microsoft.VSTS.Common.ActivatedBy | \40 Design\41 High level architecture |  | New | Validation Test Passed | Resolved | Rejected |  | all_VSTS_af75de3b_2602_44c8_b56f_847d84f808bd_Risk_System.Reason |  | Overtaken by events |  | New |  |  | all_VSTS_9008c800_2551_458e_9040_a57c55b05a6f_Bug_System.AssignedTo |  | all_VSTS_9008c800_2551_458e_9040_a57c55b05a6f_Change Request_System.AssignedTo |  | all_VSTS_9008c800_2551_458e_9040_a57c55b05a6f_Issue_System.AssignedTo |  | all_VSTS_9008c800_2551_458e_9040_a57c55b05a6f_Requirement_System.AssignedTo |  | all_VSTS_9008c800_2551_458e_9040_a57c55b05a6f_Review_System.AssignedTo |  | all_VSTS_9008c800_2551_458e_9040_a57c55b05a6f_Risk_System.AssignedTo |  |  |  | all_VSTS_9008c800_2551_458e_9040_a57c55b05a6f_Shared Steps_System.AssignedTo |  | all_VSTS_9008c800_2551_458e_9040_a57c55b05a6f_Task_System.AssignedTo |  | all_VSTS_9008c800_2551_458e_9040_a57c55b05a6f_Test Case_System.AssignedTo |  |  | all_VSTS_9008c800_2551_458e_9040_a57c55b05a6f_System.AssignedTo |  | \40 Design\41 High level architecture |  | VSTS_9008c800_2551_458e_9040_a57c55b05a6f_63-3D-6E-FD-05-A5-E3-0A-3D-3B-27-25-0E-09-89-A2-24-50-7D-FA
[56 empty] | \40 Design\42 Detailed Design Specficiations | [49 empty] | \40 Design\42 Detailed Design Specficiations | [11 empty] | \40 Design\42 Detailed Design Specficiations |  | Not fixed | all_VSTS_af75de3b_2602_44c8_b56f_847d84f808bd_Change Request_System.Reason | Rework | Split |  |  |  | Reactivated |  | Not fixed | [25 empty] | \40 Design\42 Detailed Design Specficiations
[56 empty] | \50 Build | [49 empty] | \50 Build | [11 empty] | \50 Build |  | Obsolete |  | all_VSTS_af75de3b_2602_44c8_b56f_847d84f808bd_Issue_System.Reason | Validation Test Failed |  |  |  | Rejected |  | Obsolete | [25 empty] | \50 Build
[56 empty] | \50 Build\50 UI design | [49 empty] | \50 Build\50 UI design | [11 empty] | \50 Build\50 UI design |  | Regression |  |  | Validation Test Passed |  |  |  | Review/Test Failed |  | Regression | [25 empty] | \50 Build\50 UI design
[56 empty] | \50 Build\51 Security and Admin | [49 empty] | \50 Build\51 Security and Admin | [11 empty] | \50 Build\51 Security and Admin |  | Rejected |  |  | all_VSTS_af75de3b_2602_44c8_b56f_847d84f808bd_Requirement_System.Reason |  |  |  | Review/Test Passed |  | Rejected | [25 empty] | \50 Build\51 Security and Admin
[56 empty] | \50 Build\52 Volunteer Management | [49 empty] | \50 Build\52 Volunteer Management | [11 empty] | \50 Build\52 Volunteer Management |  | Test Failed | [6 empty] | all_VSTS_af75de3b_2602_44c8_b56f_847d84f808bd_Task_System.Reason |  | Test Failed | [25 empty] | \50 Build\52 Volunteer Management
[56 empty] | \50 Build\53 Staff Management | [49 empty] | \50 Build\53 Staff Management | [11 empty] | \50 Build\53 Staff Management |  | Verified | [8 empty] | Verified | [25 empty] | \50 Build\53 Staff Management
[56 empty] | \50 Build\54 Project Management | [49 empty] | \50 Build\54 Project Management | [11 empty] | \50 Build\54 Project Management |  | all_VSTS_af75de3b_2602_44c8_b56f_847d84f808bd_Bug_System.Reason | [8 empty] | Abandoned | [25 empty] | \50 Build\54 Project Management
[56 empty] | \50 Build\55 Itinerary Management | [49 empty] | \50 Build\55 Itinerary Management | [11 empty] | \50 Build\55 Itinerary Management | [10 empty] | Accepted | [25 empty] | \50 Build\55 Itinerary Management
[56 empty] | \50 Build\56 Reporting | [49 empty] | \50 Build\56 Reporting | [11 empty] | \50 Build\56 Reporting | [10 empty] | Code Complete and System Tested | [25 empty] | \50 Build\56 Reporting
[56 empty] | \60 Test | [49 empty] | \60 Test | [11 empty] | \60 Test | [10 empty] | Out-of-scope | [25 empty] | \60 Test
[56 empty] | \60 Test\61 Unit test | [49 empty] | \60 Test\61 Unit test | [11 empty] | \60 Test\61 Unit test | [10 empty] | Validation Test Failed | [25 empty] | \60 Test\61 Unit test
[56 empty] | \60 Test\62 SIT | [49 empty] | \60 Test\62 SIT | [11 empty] | \60 Test\62 SIT | [10 empty] | Validation Test Passed | [25 empty] | \60 Test\62 SIT
[56 empty] | \60 Test\63 UAT | [49 empty] | \60 Test\63 UAT | [11 empty] | \60 Test\63 UAT | [10 empty] | Overtaken by events | [25 empty] | \60 Test\63 UAT
[56 empty] | \70 Report | [49 empty] | \70 Report | [11 empty] | \70 Report | [10 empty] | Rejected (not an issue) | [25 empty] | \70 Report
[56 empty] | \70 Report\71 Presentation Phase 1 | [49 empty] | \70 Report\71 Presentation Phase 1 | [11 empty] | \70 Report\71 Presentation Phase 1 | [10 empty] | Re-occurred | [25 empty] | \70 Report\71 Presentation Phase 1
[56 empty] | \70 Report\72 Presentation Phase 2 | [49 empty] | \70 Report\72 Presentation Phase 2 | [11 empty] | \70 Report\72 Presentation Phase 2 | [10 empty] | Re-opened | [25 empty] | \70 Report\72 Presentation Phase 2
[56 empty] | \70 Report\73 Presentation Phase 3 | [49 empty] | \70 Report\73 Presentation Phase 3 | [11 empty] | \70 Report\73 Presentation Phase 3 | [10 empty] | Resolution Verified and Accepted | [25 empty] | \70 Report\73 Presentation Phase 3
[56 empty] | \70 Report\74 End project report | [49 empty] | \70 Report\74 End project report | [11 empty] | \70 Report\74 End project report | [10 empty] | Resolved | [25 empty] | \70 Report\74 End project report
[56 empty] | \80 Project Management | [49 empty] | \80 Project Management | [11 empty] | \80 Project Management | [10 empty] | Rework | [25 empty] | \80 Project Management
[56 empty] | \90 Quality Management | [49 empty] | \90 Quality Management | [11 empty] | \90 Quality Management | [10 empty] | Code Complete and System Test Passed | [25 empty] | \90 Quality Management
[56 empty] | all_VSTS_b27ef33b_290b_440a_ace5_e920054f3c20_System.AreaPath | [49 empty] | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_System.AreaPath | [11 empty] | all_VSTS_af75de3b_2602_44c8_b56f_847d84f808bd_System.AreaPath | [10 empty] | Postponed | [25 empty] | all_VSTS_9008c800_2551_458e_9040_a57c55b05a6f_System.AreaPath
Reintroduced in Scope
Split
Accepted (as is)
Accepted with Major Changes
Accepted with Minor Changes
Major Changes Complete
Minor Changes Complete
Accepted (won't mitigate)
Eliminated
Mitigated
Mitigation Action Complete
Mitigation Action Unsatisfactory (rework)
Mitigation Triggered
Reactivated
Cancelled
Complete and Does Not Require Review/Test
Complete and Requires Review/Test
Cut
Review/Test Failed
Review/Test Passed
Completed
Update Test Case
all_VSTS_af75de3b_2602_44c8_b56f_847d84f808bd_System.Reason

## 2.Bug
Project: MTECH SE18 TEAM8S Server: team8s.myvnc.com\DefaultCollection Query: All bugs List type: Flat
ID | Work Item Type | Title | Assigned To | State
41 | Bug | TST - Not a bug | dio | Closed
43 | Bug | System cannot start | dio | Resolved
52 | Bug | Try creating new bug | jifa | Active

## 3. Test case
Project: MTECH SE18 TEAM8S Server: team8s.myvnc.com\DefaultCollection Query: Test case - All List type: Flat
ID | Work Item Type | Title | Assigned To | State | Activated By | Area Path | Iteration Path | Reason
53 | Test Case | To test the creation of test case | dio | Design | dio | \ | \Phase 3 | New
54 | Test Case | Register Volunteer with invalid name | jifa | Design | jifa | \50 Build\52 Volunteer Management | \Phase 3 | New

## 4. All work items
Project: MTECH SE18 TEAM8S Server: team8s.myvnc.com\DefaultCollection Query: Work items - All List type: Flat
ID | Work Item Type | Title | Assigned To | State
1 | Task | Finish server setup | admin | Closed
2 | Task | Test out the SQL and TFS server | admin | Closed
3 | Task | To check with Zaw for MySQL setup | admin | Closed
4 | Task | To create User Interface Prototype draft 1 | hazel | Closed
5 | Task | Review WBS to reflect latest change | dio | In progress
6 | Task | To compare AJAX Framework for Prototype study report | zaw | Closed
7 | Task | To compare UI AJAX Prototype | peishan | Closed
8 | Task | To compare Framework Prototype for Prototype Study Report | zaw | Closed
9 | Task | To produce Data Access Layer Prototype | zaw | Closed
10 | Task | To compare Reporting Tool Prototype | dio | Closed
11 | Task | To compare Database system for Prototype study report | jifa | Closed
12 | Task | to produce End to end Prototype draft 1 | zaw | Closed
13 | Task | To consolidate all parts to produce prototype study report | peishan | Closed
14 | Task | To review UI draft 1 from Jifa | dio | Closed
15 | Task | To start WBS tasks breakdown , split tasks among team | dio | Closed
16 | Requirement | To learn team site tool and start using it - updating tasks status via web | se18team8s | Active
17 | Task | To review Database system for Prototype study report from Jifa | dio | Closed
18 | Task | Testing review my report tool | dio | Closed
19 | Task | Get familiar with Team Foundation Server - know how to manage task/bug/issue status | se18team8s | In progress
20 | Task | To explorer TFS template, modify the project template to match ISS and project context | dio | Closed
21 | Task | To explore how to use SVN Bug tracker, and how to generate project reports from SVN | fengyan | In progress
22 | Task | Produce UCRR - Analysis | se18team8s | Closed
23 | Task | Development tasks break down - to use case level | dio | In progress
24 | Task | Combine UCMS, UCRR into 1 document | thida | Closed
25 | Task | Separate Internal Meeting Minutes and Quality Audit Meeting Minutes | peishan | In progress
26 | Task | Update the document reference to the document header beside the system name (the coming deliverables) | se18team8s | In progress
27 | Task | For the task tracking, use the TFS to generate the progress report and check in to the SVN | dio | Closed
28 | Task | To prepare Implementation Plan - down to use case level , include SIT | dio | In progress
29 | Task | To produce tasks assignment for Detailed Design Document - involved all team members | dio | In progress
30 | Task | Produce Test Plan | jifa | In progress
31 | Task | To produce Full Test Script for all use cases | jifa | In progress
32 | Task | Create Review Form for all outstanding deliverables (High level Architecture Design, Prototype Study Report, Transition Strategy) | jifa | In progress
33 | Task | Update and Review all the UCRR (Analysis) | thida | In progress
34 | Task | Put the indexing file to some specific required folder(E.g Analysis) | peishan | In progress
35 | Task | Looking for User | dio | Assigned
36 | Task | Presentation - Project Background (2 Slides) | dio | Closed
37 | Task | Presentation - Global Use Case Modelling Picture | dio | Closed
38 | Task | Select Two use case for Demo Decompose / Explain for chosen use cases | dio | Closed
39 | Task | High level Design (Prepare for technical Question) Prototype (Technical Issue/Risk/learned….) | peishan | Resolved
40 | Task | Progress (Which task takes longer… Implementation Plan (what u r going to finish….) | dio | Closed
41 | Bug | TST - Not a bug | dio | Closed
42 | Task | To modify TFS Template to match MTECH workflow | dio | Closed
43 | Bug | System cannot start | dio | Resolved
44 | Review | To Review the correctness of <<Include>> / <<Exclude>> in the UCMS | dio | Active
45 | Review | To Review All UCRR (Analysis) | se18team8s | Active
46 | Review | To remove the clustering option on the High Level Architecture | zaw | Active
47 | Review | To build a Access Control Framework to manage both granular security level | zaw | Active
48 | Review | To Review DWR usage - vs. Dojo | zaw | Active
49 | Task | To configure email sent out for TFS, to notice team member upon changes/new assignment | dio | In progress
50 | Task | To complete prototype - get at least 1 use case working end-to-end (include AJAX-DWR) | zaw | In progress
51 | Task | To produce completed UI design of the whole system (include all pages) - prepare before development start | dio | Assigned
52 | Bug | Try creating new bug | jifa | Active
53 | Test Case | To test the creation of test case | dio | Design
54 | Test Case | Register Volunteer with invalid name | jifa | Design