## Slide 1: Volunteer Management System
Presented by Team SE18-08S

## Slide 2: Agenda
Project Revisit
Use Case Modeling
Software Architecture
Demo of Prototype
Transition Strategy
Project Progress
Challenges & Problems
Q & A

## Slide 3: Project Revisit
Volunteer Management
Staff Management
Project Management
Itinerary Management
Administration
Purpose: To build a web-based solution to facilitate the process of volunteer registration, project management till retention.
Requirement overview:

## Slide 4: Agenda
Project Revisit
Use Case Modeling
Software Architecture
Demo of Prototype
Transition Strategy
Project Progress
Development Plan
Challenges & Problems
Q & A

## Slide 5: Use Case Modeling
  Use Case Model Survey:
    23 use cases
    7 actors
  Sample Use Cases:
    Search Project Member
    Assign Role to Project Member
    Generate Certificate

## Slide 7: Use Case Modeling Sample 1: Search Project Member
Description: Let user search and view the member list of a project.
Interaction diagram

## Slide 8: Use Case Modeling Sample 1: Search Project Member
Class diagram

## Slide 9: Use Case Modeling Sample 2: Generate Certificate
Description: Let user search and view the member list of a project.
Interaction diagram

## Slide 10: Use Case Modeling Sample 2: Generate Certificate
Class diagram

## Slide 11: Agenda
Project Revisit
Use Case Modeling
Software Architecture
Demo of Prototype
Transition Strategy
Project Progress
Development Plan
Challenges & Problems
Q & A

## Slide 12: Software Architecture – Technologies & Components

## Slide 13: Software Architecture – Logical Application Architecture

## Slide 14: Agenda
Project Revisit
Use Case Modeling
Software Architecture
Demo of Prototype
Transition Strategy
Project Progress
Development Plan
Challenges & Problems
Q & A

## Slide 15: Demo of Prototype
Volunteer Management System

## Slide 16: Demo of Prototype
Technical Prototype:
  Purpose:
    Confirm system components working
    Confirm feasibility and reusability
  Result:
    Verified and accepted within team
User Interface Prototype
  Purpose:
    Review usability
    Confirm UI design with user
  Result:
    Verified and accepted by user representative

## Slide 17: Agenda
Project Revisit
Use Case Modeling
Software Architecture
Demo of Prototype
Transition Strategy
Project Progress
Development Plan
Challenges & Problems
Q & A

## Slide 18: Transition Strategy – Analysis to Design
RUP workflows & process
Prototyping
Use Case Modeling
Use Case Realisation Report
High-level System Design
Detailed Design
Implementation
Testing
Project Management

## Slide 19: Transition Strategy – Analysis to Design
No | Task | Description | In-Charge
1 | High level design | Software architecture Prototype | Architect Design team
2 | Detailed Design Specs | Use Case Realisation Report (Designed) Guidelines & standards | Architect Design team
3 | Implementation | Code Unit-test | Development team
4 | Testing | Test script (SIT & UAT) Test plan Test result | Test lead Test team
5 | Project Management | Development plan Project reports | Project Manager QA Manager

## Slide 20: Agenda
Project Revisit
Use Case Modeling
Software Architecture
Demo of Prototype
Transition Strategy
Project Progress
Development Plan
Challenges & Problems
Q & A

## Slide 21: Project Progress
Activity | Planned Start Date | Planned End Date | Actual Start Date | Actual End Date | Task Status
Analysis Modelling |  |  |  |  | 
Produce Functional Specs - UCMS and UCRR (Analysis) | 10 Apr 2011 | 10 Aug 2011 | 12 Apr 2011 | 18 Aug 2011 | 
Produce High-level Design Specifications | 1 Jul 2011 | 10 Aug 2011 | 25 May 2011 | 10 Aug 2011 | 
Produce Prototyping Study Report | 10 Apr 2011 | 12 Jun 2011 | 01 May 2011 | 18 Aug 2011 | 
Prepare Second Audit & Presentation | 01 Aug 2011 | 12 Aug 2011 | 01 Aug 2011 | 12 Aug 2011 | 
Design Modelling |  |  |  |  | 
Produce detailed DS | 18 Aug 2011 | 15 Sep 2011 | - | - | OPEN

## Slide 22: Agenda
Project Revisit
Use Case Modeling
Software Architecture
Demo of Prototype
Transition Strategy
Project Progress
Development Plan
Challenges & Problems
Q & A

## Slide 23: Development plan

## Slide 24: Agenda
Project Revisit
Use Case Modeling
Software Architecture
Demo of Prototype
Transition Strategy
Project Progress
Development Plan
Challenges & Problems
Q & A

## Slide 25: Challenges & Problems
No | Challenge | Description | Solution
1. | Communications | Difficulty to gather all members for discussions. | Online meeting via Skype To fix a weekly meeting time
2. | Requirements Gathering | Client only wants a small set of requirements. | Seek lecturers advice Proposed merging of requirements Appoint team members as putative end users Look for alternative customer
3. | Task Control | Not able to meet deadline on time. | To log time log To hold meetings to track status
4. | Low Quality of Work | Deliverables not up to standard. | Perform reviews Conduct briefing and demo on required items

## Slide 26: Agenda
Project Revisit
Use Case Modeling
Software Architecture
Demo of Prototype
Transition Strategy
Project Progress
Challenges & Problems
Q & A

## Slide 27: Question & Answer