## Checklist
# | Phase | Deliverable items | Due date | Completeness (%) | File reference | Notes
1 | Phase 1 - Project Planning | Project Plan | 2011-04-02 | Completed: 100 (%)
2 | Phase 1 - Project Planning | Quality Plan | 2011-04-02 | Completed: 100 (%)
3 | Phase 1 - Project Planning | User Requirement Specs | 2011-04-02 | Completed: 100 (%) |  | Ready for printing
4 | Phase 1 - Project Planning | Phase 1 Presentation | 2011-04-09 | Completed: 100 (%) |  | Ready for printing
5 | Phase 2 - Analysis & Design | Functional Specs - UCMS | 2011-08-13 | Completed: 100 (%)
6 | Phase 2 - Analysis & Design | Functional Specs - UCRR (Analysis) (one per use case) | 2011-08-13 | Completed: 100 (%)
7 | Phase 2 - Analysis & Design | High level Design Specs | 2011-08-13 | Completed: 100 (%)
8 | Phase 2 - Analysis & Design | Prototyping Study Report | 2011-08-13 | Completed: 100 (%)
9 | Phase 2 - Analysis & Design | Phase 2 Presentation | 2011-08-13 | Completed: 100 (%) |  | Ready for printing
10 | Phase 3- Implementation | Detailed Design Specs (one per use case): - Sequence Diagram + Object Detailed Specs | 2012-01-07 | Starting: 0-33 (%)
11 | Phase 3- Implementation | Source code/ Executables | 2012-01-07 | Starting: 0-33 (%)
12 | Phase 3- Implementation | Test Plan | 2012-01-07 | Finalizing: 66-99 (%)
13 | Phase 3- Implementation | Test Report / Forms | 2012-01-07 | In progress: 33-65 (%)
14 | Phase 3- Implementation | User Guide / Manual in PDF/DOC/CHM/HTML form | 2012-01-07 | Starting: 0-33 (%)
15 | Phase 3- Implementation | End of Project Report | 2012-01-07 | Starting: 0-33 (%)
16 | Phase 3- Implementation | Phase 3 Presentation | 2012-01-07 | Starting: 0-33 (%)

## Legend
# | Category | Value
1 | Completeness (%) | Completed: 100 (%)
2 | Completeness (%) | Finalizing: 66-99 (%)
3 | Completeness (%) | In progress: 33-65 (%)
4 | Completeness (%) | Starting: 0-33 (%)