## Overall
No | Task | Resource | Start Date | End Date
| Detailed Design - Design Model Report |  | 2011-08-21 | 2011-09-18
| Login / Logout | Feng Yan | 2011-08-21 | 2011-09-04
| Change Password | Feng Yan | 2011-08-21 | 2011-09-04
| Forget Password | Feng Yan | 2011-08-21 | 2011-09-04
| Register User Account | Feng Yan | 2011-08-21 | 2011-09-04
| Update Profile | Feng Yan | 2011-08-21 | 2011-09-04
| Review & Finalise | Zaw | 2011-09-05 | 2011-09-10
| Request for Certificate | Hazel | 2011-08-21 | 2011-09-04
| Print Certificate | Hazel | 2011-08-21 | 2011-09-04
| Generate Certificate By Batch | Hazel | 2011-08-21 | 2011-09-04
| Manually Manage Certificate | Hazel | 2011-08-21 | 2011-09-04
| Review & Finalise | Zaw | 2011-09-05 | 2011-09-10
| Browse Project | Jifa | 2011-08-21 | 2011-09-04
| Manage Project | Jifa | 2011-08-21 | 2011-09-04
| Review & Finalise | Dio | 2011-09-05 | 2011-09-10
| Propose Project | Dio | 2011-08-21 | 2011-09-04
| Review Project Proposal | Dio | 2011-08-21 | 2011-09-04
| Assign Project Member | Dio | 2011-08-21 | 2011-09-04
| Search member of project | Dio | 2011-08-21 | 2011-09-04
| Search project proposal | Dio | 2011-08-21 | 2011-09-04
| Review & Finalise | Jifa | 2011-09-05 | 2011-09-10
| Post Experience | Thida | 2011-08-21 | 2011-09-04
| Post Feedback | Thida | 2011-08-21 | 2011-09-04
| Review Feedback | Thida | 2011-08-21 | 2011-09-04
| Search project feedback | Thida | 2011-08-21 | 2011-09-04
| Review & Finalise | Hazel | 2011-09-05 | 2011-09-10
| Raise Interest | Thida | 2011-09-11 | 2011-09-18
| Review Project Interest | Thida | 2011-09-11 | 2011-09-18
| Review & Finalise | Hazel | 2011-09-18 | 2011-09-24
| Manage Itinerary | Peishan | 2011-08-21 | 2011-09-04
| Submit Itinerary Project | Peishan | 2011-08-21 | 2011-09-04
| Review Itinerary | Peishan | 2011-08-21 | 2011-09-04
| Review & Finalise | Thida | 2011-09-05 | 2011-09-10
| Manage Calendar | Peishan | 2011-09-11 | 2011-09-18
| Review & Finalise | Feng Yan | 2011-09-18 | 2011-09-24
| Generate Report | Zaw | 2011-08-21 | 2011-09-04
| Review & Finalise | Feng Yan | 2011-09-05 | 2011-09-10
Development
Access control & Security
Authentication & Authorisation
Report Utlity
Core Use Case Implementation
Test Plan
| Prepare Test Plan | Jifa | 2011-09-11 | 2011-09-24
| Review & Finalise | Dio, Thida | 2011-09-25 | 2011-09-25
Test Scripts
Prepare Test Scripts by module
Review & Finalise
Week
Development
· Solution framework
· User Access Control & Security
· Common functionalities
o Logging
o Constant
o Session handling
· Report Utility
· Use Case Implementation
Administration
Volunteer Management
Staff Management
Project Management
Itinerary Management
Testing
Project Management

## Tasks
No | Module | Item | Type | Priority | Sequence | Status | Planned Start Date | Planned End Date | Action By | Planned Review Date | Review Status | Review By | Remarks
| Volunteer | Finalised ERD | Database | High |  | Done | 2011-12-24 | 2011-12-24 | Zaw, Thida, Peishan | 2011-12-24 | Done | Peishan
| Volunteer | Data Model Specs | Database | High |  | Done | 2011-12-24 | 2011-12-25 | Thida | 2011-12-24 | Done | Peishan
| Volunteer | Database Tables Creation | Database | High |  | Done | 2011-12-24 | 2011-12-24 | Zaw | 2011-12-24 | Done | Peishan
| Database | Populate Code Table Data | Database | High | 1 | Done | 2011-12-24 | 2011-12-24 | Zaw | 2011-12-24 | Done | Peishan
| Volunteer | Perform reverse engineering using Rational Rose | Design | High |  | Done | 2011-12-24 | 2011-12-25 | Feng Yan | 2011-12-24 | Done | Peishan
| Volunteer | Register Volunteer Profile | Code | High | 1 | Done | 2011-12-24 | 2011-12-26 | Zaw | 2011-12-24 | New | Peishan
| Volunteer | Update Volunteer Profile | Code | High | 2 | Done | 2011-12-25 | 2011-12-27 | Zaw | 2011-12-24 | New | Peishan
| Volunteer | Register Volunteer Profile | Unit Test | High | 1 | New | 2011-01-02 | 2012-01-03 |  |  | New
| Volunteer | Update Volunteer Profile | Unit Test | High | 2 | New | 2011-01-02 | 2012-01-03 |  |  | New
| Volunteer | Register Volunteer Profile | Test Case | High | 1 | New | 2011-12-24 | 2011-12-26 | Jifa | 2011-12-25 | New | Peishan
| Volunteer | Update Volunteer Profile | Test Case | High | 2 | New | 2011-12-25 | 2011-12-27 | Jifa | 2011-12-25 | New | Peishan
| Common | A & A | Code | High | 1 | Done | 2011-12-24 | 2011-12-25 | Peishan | 2011-12-25 | New | Zaw
| Login | Login | Code | High | 1 | Done | 2011-12-24 | 2011-12-25 | Peishan | 2011-12-25 | New | Zaw
| Security | ACL | Code | High | 1 | Done | 2011-12-26 | 2011-12-27 | Peishan | 2011-12-28 | New | Zaw
| Volunteer | Send UI Screen Shots | Design | High |  | Done | 2011-12-24 | 2011-12-24 | Thida | 2011-12-24 | Done | Peishan | Peishan is just to confirm if Thida has sent out the design.
| Base | Pagination | Code | Low | 1 | Done | 2011-12-30 | 2011-12-31 | Zaw |  | New
| Volunteer | Browse for Projects | Code | High | 3 | Done | 2011-12-26 | 2011-12-26 | Feng Yan |  | New
| Volunteer | Raise Interest to Project | Code | High | 4 | Done | 2011-12-26 | 2011-12-26 | Feng Yan |  | New
| Volunteer | Review Project Interest by Volunteer and Assign Volunteer to Project | Code | High | 5 | Done | 2011-12-26 | 2011-12-26 | Feng Yan |  | New
| Volunteer | Post Feedback to Project | Code | High | 6 | Done | 2011-12-27 | 2011-12-27 | Feng Yan |  | New
| Volunteer | Post Experience or Inspiration Stories | Code | High | 7 | Done | 2011-12-28 | 2011-12-28 | Feng Yan |  | New
| Volunteer | Review Feedback | Code | High | 8 | Done | 2011-12-29 | 2011-12-29 | Feng Yan |  | New
| Volunteer | Request for Certificate | Code | High | 9 | Done | 2011-12-30 | 2011-12-30 | Feng Yan |  | New
| Administrator | Manage Volunteer Account | Code | Low | 10 | NA | 2011-12-28 | 2011-12-28 | Zaw |  | New
| Volunteer | Forget Password | Code | Medium | 11 | New | 2011-12-29 | 2011-12-29 | Thida |  | New
| Volunteer | Change Password | Code | Medium | 12 | Done | 2011-12-29 | 2011-12-29 | Peishan |  | New
| Volunteer | Browse for Projects | Unit Test | High | 3 | New | 2011-01-02 | 2012-01-03 |  |  | New
| Volunteer | Raise Interest to Project | Unit Test | High | 4 | New | 2011-01-02 | 2012-01-03 |  |  | New
| Volunteer | Review Project Interest by Volunteer and Assign Volunteer to Project | Unit Test | High | 5 | New | 2011-01-02 | 2012-01-03 |  |  | New
| Volunteer | Post Feedback to Project | Unit Test | High | 6 | New | 2011-01-02 | 2012-01-03 |  |  | New
| Volunteer | Post Experience or Inspiration Stories | Unit Test | High | 7 | New | 2011-01-02 | 2012-01-03 |  |  | New
| Volunteer | Review Feedback | Unit Test | High | 8 | New | 2011-01-02 | 2012-01-03 |  |  | New
| Volunteer | Request for Certificate | Unit Test | High | 9 | New | 2011-01-02 | 2012-01-03 |  |  | New
| Volunteer | Manage Volunteer Account | Unit Test | High | 10 | New | 2011-01-02 | 2012-01-03 |  |  | New
| Security | Forget Password | Unit Test | Medium | 11 | New | 2011-01-02 | 2012-01-03 |  |  | New
| Security | Change Password | Unit Test | Medium | 12 | New | 2011-01-02 | 2012-01-03 |  |  | New
| Volunteer | Browse for Projects | Test Case | High | 3 | New | 2011-12-26 | 2011-12-26 | Jifa |  | New | Dio
| Volunteer | Raise Interest to Project | Test Case | High | 4 | New | 2011-12-26 | 2011-12-26 | Jifa |  | New | Dio
| Volunteer | Review Project Interest by Volunteer and Assign Volunteer to Project | Test Case | High | 5 | New | 2011-12-26 | 2011-12-26 | Jifa |  | New | Dio
| Volunteer | Post Feedback to Project | Test Case | High | 6 | New | 2011-12-26 | 2011-12-26 | Jifa |  | New | Dio
| Volunteer | Post Experience or Inspiration Stories | Test Case | High | 7 | New | 2011-12-26 | 2011-12-26 | Jifa |  | New | Dio
| Volunteer | Review Feedback | Test Case | High | 8 | New | 2011-12-26 | 2011-12-26 | Jifa |  | New | Dio
| Volunteer | Request for Certificate | Test Case | High | 9 | New | 2011-12-26 | 2011-12-26 | Jifa |  | New | Dio
| Volunteer | Manage Volunteer Account | Test Case | High | 10 | New | 2011-12-26 | 2011-12-26 | Jifa |  | New | Dio
| Volunteer | Forget Password | Test Case | Medium | 11 | New | 2011-12-26 | 2011-12-26 | Jifa |  | New | Dio
| Volunteer | Change Password | Test Case | Medium | 12 | New | 2011-12-26 | 2011-12-26 | Jifa |  | New | Dio
| Project | Manage Projects | Code | High | 1 | Done | 2011-12-26 | 2011-12-26 | Thida |  | New
| Project | Setup Project Details | Code | High | 2 | Done | 2011-12-26 | 2011-12-26 | Feng Yan |  | New
| Project | Assign Roles to Project Member | Code | High | 3 | Done | 2011-12-27 | 2011-12-27 | Zaw |  | New
| Project | Send Invitation to Volunteer | Code | High | 4 | WIP | 2011-12-28 | 2011-12-28 | Zaw |  | New
| Project | Review Project Interest by Volunteer and Assign Volunteer to Project | Code | High | 5 | WIP | 2011-12-29 | 2011-12-29 | Zaw |  | New
| Project | Propose Project | Code | Medium | 6 | Done | 2012-01-01 | 2012-01-02 | Feng Yan |  | New
| Project | Review and Reply Project Proposal | Code | Medium | 7 | Done | 2012-01-01 | 2012-01-02 | Feng Yan |  | New
| Project | Setup Project Calendar | Code | Low | 8 | NA |  |  | Peishan |  | NA
| Project | Manage Projects | Unit Test | High | 1 | New | 2011-01-02 | 2012-01-03 |  |  | New
| Project | Setup Project Details | Unit Test | High | 2 | New | 2011-01-02 | 2012-01-03 |  |  | New
| Project | Assign Roles to Project Member | Unit Test | High | 3 | New | 2011-01-02 | 2012-01-03 |  |  | New
| Project | Send Invitation to Volunteer | Unit Test | High | 4 | New | 2011-01-02 | 2012-01-03 |  |  | New
| Project | Review Project Interest by Volunteer and Assign Volunteer to Project | Unit Test | High | 5 | New | 2011-01-02 | 2012-01-03 |  |  | New
| Project | Propose Project | Unit Test | Low | 6 | New | 2011-01-02 | 2012-01-03 |  |  | New
| Project | Review and Reply Project Proposal | Unit Test | Low | 7 | New | 2011-01-02 | 2012-01-03 |  |  | New
| Project | Setup Project Calendar | Unit Test | Low | 8 | NA |  |  |  |  | New
| Project | Manage Projects | Test Case | High | 1 | New | 2011-12-26 | 2011-12-26 | Dio |  | New | Jifa
| Project | Setup Project Details | Test Case | High | 2 | New | 2011-12-26 | 2011-12-26 | Dio |  | New | Jifa
| Project | Assign Roles to Project Member | Test Case | High | 3 | New | 2011-12-26 | 2011-12-26 | Dio |  | New | Jifa
| Project | Send Invitation to Volunteer | Test Case | High | 4 | New | 2011-12-26 | 2011-12-26 | Dio |  | New | Jifa
| Project | Review Project Interest by Volunteer and Assign Volunteer to Project | Test Case | High | 5 | New | 2011-12-26 | 2011-12-26 | Dio |  | New | Jifa
| Project | Propose Project | Test Case | Low | 6 | New |  |  | Dio |  | New | Jifa
| Project | Review and Reply Project Proposal | Test Case | Low | 7 | New |  |  | Dio |  | New | Jifa
| Project | Setup Project Calendar | Test Case | Low | 8 | New |  |  | Dio |  | New | Jifa
| Itinerary | Prepare Itinerary Plan | Code | Low | 1 | NA |  |  | Zaw |  | NA
| Itinerary | Submit Itinerary Plan | Code | Low | 2 | NA |  |  | Zaw |  | NA
| Itinerary | Review and Reply Itinerary Plan | Code | Low | 3 | NA |  |  | Zaw |  | NA
| Itinerary | Prepare Itinerary Plan | Unit Test | Low | 1 | NA |  |  | Zaw |  | New
| Itinerary | Submit Itinerary Plan | Unit Test | Low | 2 | NA |  |  | Zaw |  | New
| Itinerary | Review and Reply Itinerary Plan | Unit Test | Low | 3 | NA |  |  | Zaw |  | New
| Itinerary | Prepare Itinerary Plan | Test Case | Low | 1 | New |  |  | Jifa |  | New | Dio
| Itinerary | Submit Itinerary Plan | Test Case | Low | 2 | New |  |  | Jifa |  | New | Dio
| Itinerary | Review and Reply Itinerary Plan | Test Case | Low | 3 | New |  |  | Jifa |  | New | Dio
| Base | Change to use XML for database | Code | Low | 1 | NA |  |  | Peishan |  | NA
| Certificate | Generate Certificate (for Project & Volunteer) | Code | Medium | 1 | Done | 2011-12-26 | 2011-12-26 | Thida |  | New
| Certificate | Print Certificate | Code | Medium | 2 | NA | 2011-12-26 | 2011-12-26 | Thida |  | New
| Certificate | Generate Certificate | Unit Test | Medium | 1 | New | 2011-01-02 | 2012-01-03 |  |  | New
| Certificate | Print Certificate | Unit Test | Medium | 2 | NA |  |  | Hazel |  | New
| Certificate | Generate Certificate | Test Case | Medium | 1 | New | 2011-12-27 | 2011-12-27 | Dio |  | New | Jifa
| Certificate | Print Certificate | Test Case | Medium | 2 | New | 2011-12-27 | 2011-12-27 | Dio |  | New | Jifa
| Staff | Manage Staff Account | Code | Low | 1 | NA |  |  | Hazel |  | NA
| Staff | Register Staff Account | Code | Low | 2 | NA |  |  | Hazel |  | NA
| Staff | Update Profile by Staff | Code | Low | 3 | NA |  |  | Hazel |  | NA
| Staff | Forget Password | Code | Low | 4 | NA | 2012-01-01 | 2012-01-02 | Thida |  | New
| Security | Change Password | Code | Low | 5 | Done | 2012-01-01 | 2012-01-02 | Peishan |  | New
| Staff | Manage Staff Account | Unit Test | Low | 1 | NA |  |  | Hazel |  | New
| Staff | Register Staff Account | Unit Test | Low | 2 | NA |  |  | Hazel |  | New
| Staff | Update Profile by Staff | Unit Test | Low | 3 | NA |  |  | Hazel |  | New
| Staff | Forget Password | Unit Test | Low | 4 | NA |  |  | Hazel |  | New
| Staff | Change Password | Unit Test | Low | 5 | NA |  |  | Hazel |  | New
| Staff | Manage Staff Account | Test Case | Low | 1 | New |  |  | Dio |  | New
| Staff | Register Staff Account | Test Case | Low | 2 | New |  |  | Dio |  | New
| Staff | Update Profile by Staff | Test Case | Low | 3 | New |  |  | Dio |  | New
| Staff | Forget Password | Test Case | Low | 4 | New |  |  | Dio |  | New
| Staff | Change Password | Test Case | Low | 5 | New |  |  | Dio |  | New
| Documentation | User Manual | Documentation | High | 2 | New | 2011-12-26 | 2011-12-26 | Dio |  | New
| Documentation | Installation Guide | Documentation | Low | 6 | New | 2011-12-26 | 2011-12-26 | Dio |  | New
| Documentation | Operations Guide | Documentation | Low | 7 | New | 2011-12-26 | 2011-12-26 | Dio |  | New
| Documentation | End of Project Report | Documentation | High | 4 | New | 2011-12-31 | 2012-01-05 | Dio |  | New
| Documentation | 3rd Project Presentation | Documentation | High | 5 | New | 2011-12-30 | 2012-01-05 | Dio |  | New
| Documentation | 3rd Quality Audit | Documentation | High | 3 | New | 2012-01-04 | 2012-01-06 | Peishan |  | New
| Documentation | Detailed Design Specs | Documentation | High | 1 | New | 2012-01-01 | 2012-01-06 | Dio, Feng Yan, Peishan |  | New
| Certificate | Draw the Jasper Report template for Certificate Management | Code | High | 1 | Done | 2011-12-24 | 2011-12-24 | Thida |  | New
| Base | Code Lookup | Code | High | 1 | Done | 2012-01-01 | 2012-01-02 | Peishan |  | New
| Base | User Lookup | Code | High | 2 | Done | 2011-12-31 | 2012-01-01 | Peishan |  | New
| Base | Email Integration | Code | Medium | 1 | Done | 2011-12-31 | 2012-01-01 | Zaw |  | New
| Base | Upgrade Jasper Library to 4.1.2 | Code | High | 1 | Done | 2011-12-24 | 2011-12-24 | Peishan |  | New
| Database | Data Preparation | Database | High |  | Done | 2011-12-29 | 2011-12-30 | Dio, Jifa |  | New
| Code | Utility Classes | Code | High | 1 | Done | 2011-12-24 | 2011-12-24 | Peishan |  | New
| Code | Find code to do zip utility | Code | Low | 2 | NA | 2012-01-01 | 2012-01-01 | Zaw, Thida |  | New
| Project | Request for Certificate (by Project) | Code | High | 8 | New | 2012-01-01 | 2012-01-01 | Zaw |  | New
| Code | Find code to do upload to table | Code | High | 2 | New | 2012-01-02 | 2012-01-02 | Peishan |  | New
| Code | User password decryption | Code | Medium | 3 | Done | 2012-01-02 | 2012-01-02 | Zaw |  | New
UCRR (Design)

## Misc Tasks yet to assign
No | Item | Status | Remarks
1 | Code Lookup Class | New
2 | User Lookup | New
3 | Meeting Minutes | New
4 | Timelog | New
5 | Audit Log Meeting Minutes | New
6 | Validator | New
7 | Utility Classes | Done | Added DateUtil, StringUtil
8 | Use of messages.properties | New | http://static.springsource.org/spring/docs/2.5.x/reference/view.html#view-jsp-formtaglib-errorstag (14.4.5.2. Simple binding)
9 | How to use DWR | New
10 | Upgrade Jasper Lib | Done
11 | Database Script | New
12 | Data Loading