## 1.Task
Project: MTECH SE18 TEAM8S Server: team8s.myvnc.com\DefaultCollection Query: All tasks List type: Flat
ID | Iteration Path | Area Path | Assigned To | Priority | Title | Description | State | History | Start Date | Finish Date | Resolved By | Resolved Date | Original Estimate | Remaining Work | Completed Work | Work Item Type
1 | \Phase 1 | \80 Project Management | admin | 1 | Finish server setup | To finish TFS, (done) MS SQL, (done) MySQL, (done) Java (done) Tomcat (done) Jtrac setup (N/A) | Closed |  | 2011-05-21 08:00 | 2011-06-01 17:00 |  |  | 8 | 64 | 8 | Task
2 | \Phase 2 | \50 Build\50 UI design | admin | 2 | Test out the SQL and TFS server | Please try to test the function of TFS & SQL | Closed |  | 2011-05-21 08:00 | 2011-06-08 17:00 |  |  | 0 | 0 | 112 | Task
3 | \Phase 2 | \80 Project Management | admin | 2 | To check with Zaw for MySQL setup | To check with Zaw for MySQL setup | Closed |  | 2011-05-21 08:00 | 2011-08-26 17:00 |  |  | 0 | 112 | 0 | Task
23 | \Phase 3 | \80 Project Management | dio | 1 | Development tasks break down - to use case level | Development tasks break down - to use case level (done - pending checked in SVN ) To review the draft WBS breakdown from Peishan (checked into SVN) (done) | In progress |  | 2011-08-13 00:41 | 2011-08-19 00:41 |  |  | 12 | 8 | 4 | Task
28 | \Phase 3 | \80 Project Management | dio | 1 | To prepare Implementation Plan - down to use case level , include SIT | Prepare Implementation Plan - in detailed Focus on : - prototype completed solution - integration phases - DWR usage ? OK or not ? | In progress |  | 2011-08-13 00:41 | 2011-08-20 |  |  | 16 | 14 | 2 | Task
49 | \Phase 3 | \80 Project Management | dio | 2 | To configure email sent out for TFS, to notice team member upon changes/new assignment | To configure email sent out for TFS for these items: - Task created - Bug update - Review request | In progress |  | 2011-08-21 16:04 | 2011-08-21 16:04 |  |  | 8 | 8 | 0 | Task
29 | \Phase 3 | \80 Project Management | dio | 1 | To produce tasks assignment for Detailed Design Document - involved all team members | To produce Detailed Design Document - all team members | In progress |  | 2011-08-13 17:53 | 2011-08-25 17:53 |  |  | 8 | 8 | 0 | Task
5 | \Phase 2 | \80 Project Management | dio | 1 | Review WBS to reflect latest change | To review WBS and Project plan to reflect latest status | In progress |  | 2011-06-01 08:00 | 2011-09-01 17:00 |  |  | 8 | 7 | 1 | Task
35 | \ | \80 Project Management | dio | 4 | Looking for User | To continue looking for potential user | Assigned |  | 2011-01-01 00:41 | 2012-01-01 |  |  | 8 | 8 | 0 | Task
10 | \Phase 2 | \30 Prototype\33 Prototype Study Report | dio | 2 | To compare Reporting Tool Prototype | To compare Reporting Tool Prototype | Closed |  | 2011-06-01 08:00 | 2011-08-20 | thida |  | 8 | 0 | 8 | Task
14 | \Phase 2 | \30 Prototype\31 UI Prototype | dio | 2 | To review UI draft 1 from Jifa | To review UI draft 1 from Jifa , in SVN - to suggest integrated view (all page with footer / header) - to suggest navigation - to suggest frame/ button/ layout / CSS usage | Closed |  | 2011-06-01 08:00 | 2011-06-14 17:00 |  |  | 8 | 0 | 8 | Task
15 | \Phase 2 | \80 Project Management | dio | 1 | To start WBS tasks breakdown , split tasks among team | To start WBS tasks breakdown , split tasks among team - Split UCRR tasks for all members - Split High level specs among Zaw, Feng Yan, Peishan and Thida - To get status update before 24 June 2011 | Closed |  | 2011-07-01 18:56 | 2011-08-30 18:56 |  |  | 0 | 0 | 12 | Task
17 | \Phase 2 | \30 Prototype\32 Architecture Prototye | dio | 2 | To review Database system for Prototype study report from Jifa | To review Database system for Prototype study report from Jifa | Closed |  | 2011-06-01 17:47 | 2011-07-07 17:47 | dio | 2011-08-13 17:48 | 4 | 4 | 0 | Task
18 | \Phase 2 | \30 Prototype | dio | 1 | Testing review my report tool | pls check for me | Closed |  | 2011-08-14 00:24 | 2011-08-14 00:24 | thida | 2011-06-11 16:48 | 8 | 0 | 8 | Task
20 | \Phase 2 | \80 Project Management | dio | 2 | To explorer TFS template, modify the project template to match ISS and project context | To customize TFS template with task workflow, item workflow that match the ISS project waterfall model. For e.g: To add more discipline into Tasks | Closed |  | 2011-08-13 00:23 | 2011-08-14 00:23 |  |  | 8 | 0 | 8 | Task
27 | \Phase 2 | \80 Project Management | dio | 2 | For the task tracking, use the TFS to generate the progress report and check in to the SVN | For the task tracking, use the TFS to generate the progress report and check in to the SVN | Closed |  | 2011-08-13 16:31 | 2011-08-20 16:31 |  |  | 8 | 0 | 8 | Task
36 | \Phase 2 | \70 Report\72 Presentation Phase 2 | dio | 2 | Presentation - Project Background (2 Slides) | To prepare slides for presentation (project background) | Closed |  | 2011-08-13 00:41 | 2011-08-20 |  |  | 8 | 0 | 8 | Task
37 | \Phase 2 | \70 Report\72 Presentation Phase 2 | dio | 2 | Presentation - Global Use Case Modelling Picture | To create UCMS for presentation | Closed |  | 2011-08-13 00:41 | 2011-08-20 |  |  | 8 | 0 | 8 | Task
38 | \Phase 2 | \70 Report\72 Presentation Phase 2 | dio | 2 | Select Two use case for Demo Decompose / Explain for chosen use cases | To select 2 use cases for Phase 2 presentation | Closed |  | 2011-08-13 00:41 | 2011-08-20 |  |  | 8 | 8 | 0 | Task
40 | \Phase 2 | \70 Report\72 Presentation Phase 2 | dio | 2 | Progress (Which task takes longer… Implementation Plan (what u r going to finish….) | To show the current progress of Phase 2 | Closed |  | 2011-08-13 00:41 | 2011-08-20 |  |  | 8 | 8 | 0 | Task
42 | \Phase 1 | \80 Project Management | dio | 1 | To modify TFS Template to match MTECH workflow | - Created Phases & Iterations to match MTECH architecture | Closed |  | 2011-08-13 19:01 | 2011-08-14 19:01 |  |  | 4 | 0 | 4 | Task
51 | \Phase 3 | \50 Build\50 UI design | dio | 2 | To produce completed UI design of the whole system (include all pages) - prepare before development start | Requirements: - All UI design for all pages - Design for main page, home screen - Involve navigation and flow | Assigned |  | 2011-08-21 22:30 | 2011-08-28 22:30 |  |  | 30 | 30 | 0 | Task
21 | \Phase 2 | \80 Project Management | fengyan | 2 | To explore how to use SVN Bug tracker, and how to generate project reports from SVN | - To explore how to use SVN Bug tracker, and how to generate project reports from SVN. For e.g: - How to integrate SVN bug tracker into Eclipse - How to generate report on active/closed/pending bugs - Generate report on code coverage during testing stage - Generate report on requirements coverage during testing stage | In progress |  | 2011-08-13 00:41 | 2011-08-20 |  |  | 12 | 11 | 1 | Task
4 | \Phase 2 | \30 Prototype\31 UI Prototype | hazel | 1 | To create User Interface Prototype draft 1 | To prepare User Interface Prototype for putative user to review, by 28th May 2011 | Closed |  | 2011-06-05 08:00 | 2011-06-16 17:00 | hazel | 2011-08-21 22:30 | 16 | 6 | 10 | Task
30 | \Phase 3 | \60 Test | jifa | 2 | Produce Test Plan | To produce detailed Test Plan (maybe based on Unit 7 materials) | In progress |  | 2011-08-13 00:41 | 2011-08-20 |  |  | 8 | 8 | 0 | Task
31 | \Phase 3 | \60 Test | jifa | 2 | To produce Full Test Script for all use cases | To produce Full Test Script for all use cases | In progress |  | 2011-08-13 00:41 | 2011-08-20 |  |  | 8 | 8 | 0 | Task
32 | \Phase 3 | \90 Quality Management | jifa | 2 | Create Review Form for all outstanding deliverables (High level Architecture Design, Prototype Study Report, Transition Strategy) | Create Review Form for all outstanding deliverables (High level Architecture Design, Prototype Study Report, Transition Strategy) | In progress |  | 2011-08-13 00:41 | 2011-08-20 |  |  | 8 | 8 | 0 | Task
11 | \Phase 2 | \30 Prototype\33 Prototype Study Report | jifa | 2 | To compare Database system for Prototype study report | To compare Database system for Prototype study report | Closed |  | 2011-08-13 00:41 | 2011-08-20 | jifa | 2011-06-10 08:59 | 8 | 0 | 8 | Task
39 | \Phase 2 | \70 Report\72 Presentation Phase 2 | peishan | 2 | High level Design (Prepare for technical Question) Prototype (Technical Issue/Risk/learned….) | High level Design (Prepare for technical Question) Prototype (Technical Issue/Risk/learned….) | Resolved |  | 2011-08-13 00:41 | 2011-08-20 | peishan | 2011-08-21 18:26 | 8 | 8 | 0 | Task
25 | \Phase 3 | \90 Quality Management | peishan | 2 | Separate Internal Meeting Minutes and Quality Audit Meeting Minutes | Separate Internal Meeting Minutes and Quality Audit Meeting Minutes | In progress |  | 2011-08-13 00:41 | 2011-08-20 |  |  | 8 | 8 | 0 | Task
34 | \Phase 3 | \90 Quality Management | peishan | 3 | Put the indexing file to some specific required folder(E.g Analysis) | Put the indexing file to some specific required folder(E.g Analysis) | In progress |  | 2011-08-13 00:41 | 2011-08-20 |  |  | 8 | 8 | 0 | Task
7 | \Phase 2 | \30 Prototype\33 Prototype Study Report | peishan | 2 | To compare UI AJAX Prototype | To compare UI AJAX Prototype for Prototype Study Report | Closed |  | 2011-06-01 08:00 | 2011-08-20 |  |  | 8 | 8 |  | Task
13 | \Phase 2 | \30 Prototype\33 Prototype Study Report | peishan | 2 | To consolidate all parts to produce prototype study report | To consolidate all parts to product prototype study report | Closed |  | 2011-06-01 08:00 | 2011-08-20 |  |  | 16 | 0 | 16 | Task
19 | \Phase 2 | \80 Project Management | se18team8s | 2 | Get familiar with Team Foundation Server - know how to manage task/bug/issue status | Get familiar with Team Foundation Server - Know how to create/update/close tasks - Know how to create/update/close requirement / assignment | In progress |  | 2011-08-13 00:41 | 2011-08-20 |  |  | 8 | 8 | 0 | Task
26 | \Phase 3 | \90 Quality Management | se18team8s | 2 | Update the document reference to the document header beside the system name (the coming deliverables) | Update the document reference to the document header beside the system name (the coming deliverables) | In progress |  | 2011-08-13 00:41 | 2011-08-20 |  |  | 8 | 8 | 0 | Task
22 | \Phase 2 | \20 Analysis\22 Use Case Realization Report (Analysis) | se18team8s | 1 | Produce UCRR - Analysis | Complete UCRR (analysis ) for these Use case : 1. Login / Logout 2. Change password 3. Forget password 4. Register User Account 5. Update Profile 7. Raise Project Interest 8. Proposa Project 9. Post Experience 10. Post Feedback 11. Request for Certificate | Closed |  | 2011-08-13 00:41 | 2011-08-20 |  |  | 24 | 0 | 24 | Task
33 | \Phase 3 | \90 Quality Management | thida | 1 | Update and Review all the UCRR (Analysis) | Update and Review all the UCRR (analysis) correctness | In progress |  | 2011-08-13 00:41 | 2011-08-24 |  |  | 8 | 8 | 0 | Task
24 | \Phase 2 | \20 Analysis | thida | 2 | Combine UCMS, UCRR into 1 document | Combine UCMS, UCRR into 1 document | Closed |  | 2011-08-13 00:41 | 2011-08-20 | dio | 2011-08-21 18:14 | 8 | 0 | 8 | Task
50 | \Phase 3 | \30 Prototype | zaw | 2 | To complete prototype - get at least 1 use case working end-to-end (include AJAX-DWR) | To complete prototype - get at least 1 use case working end-to-end (include AJAX-DWR) | Assigned |  | 2011-08-22 | 2011-08-29 |  |  | 50 | 50 | 0 | Task
6 | \Phase 2 | \30 Prototype\33 Prototype Study Report | zaw | 2 | To compare AJAX Framework for Prototype study report | To compare AJAX Framework for Prototype study report To be use in Prototype study report | Closed |  | 2011-08-13 00:41 | 2011-08-20 |  |  | 8 | 0 | 8 | Task
8 | \Phase 2 | \30 Prototype\33 Prototype Study Report | zaw | 2 | To compare Framework Prototype for Prototype Study Report | To compare Framework Prototype for Prototype Study Report | Closed |  | 2011-06-01 08:00 | 2011-08-20 | zaw | 2011-08-21 18:27 | 8 | 8 | 0 | Task
9 | \Phase 2 | \30 Prototype\32 Architecture Prototye | zaw | 2 | To produce Data Access Layer Prototype | To produce Data Access Layer Prototype | Closed |  | 2011-06-01 08:00 | 2011-06-14 17:00 |  |  | 16 | 0 | 16 | Task
12 | \Phase 2 | \30 Prototype | zaw | 1 | to produce End to end Prototype draft 1 | to produce End to end Prototype draft 1 | Closed |  | 2011-06-01 08:00 | 2011-06-14 17:00 |  |  | 16 | 0 | 16 | Task

## 2.Bug
Project: MTECH SE18 TEAM8S Server: team8s.myvnc.com\DefaultCollection Query: All bugs List type: Flat
ID | Title | Area Path | Assigned To | State | Severity | Priority | Resolved By | Resolved Date
41 | TST - Not a bug | \50 Build | dio | Closed | 4 - Low | 4 | dio | 2011-08-22 14:35
43 | System cannot start | \50 Build | dio | Resolved | 4 - Low | 4 | dio | 2011-08-22 14:36

## VSTS_ValidationWS_1 (hidden)
value doesn't matter | value doesn't matter | 2011-08-22 14:36 | value doesn't matter | admin | Active | admin | Active | admin | Active | admin | Active | admin | Active | admin | admin | Active | admin | 1 | admin | admin | Active | admin | 1 | admin | admin | Active | admin | 1 | admin | admin | Active | admin | 1 | admin | admin | Active | admin | admin | admin | Active | admin | 1 | admin | admin | admin | Active | admin | Active | admin | Assigned | admin | Closed | Bug | admin | Active | admin | Active | \ | \ | admin | admin | admin | admin | admin | admin | admin | admin | admin | Active | admin | Active | admin | Active | admin | Active | admin | Active | admin | Active | admin | Active | admin | Assigned | admin | Closed | Bug | admin | Active | Active | 1 | admin | admin | Assigned | admin | 1 | admin | admin | Closed | 1 | admin | admin | Active | admin | 1 | \ | \ | admin | Assigned | 1 | Closed | Assigned | \ | admin | Active | \ | 1 - Critical | 1 - Critical | 1 - Critical | 1 - Critical | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | admin | admin | admin | admin | admin | admin | admin | admin | 1 - Critical | 1 | Active | Active | Closed | Bug
readOnlyTestRange_@ | readOnlyTestRange_0 | readOnlyTestRange_dd-MMM-yy h:mm AM/PM | readOnlyTestRange_General | dio | Closed | dio | Closed | dio | Closed | dio | Closed | dio | Closed | dio | dio | Closed | dio | 2 | dio | dio | Closed | dio | 2 | dio | dio | Closed | dio | 2 | dio | dio | Closed | dio | 2 | dio | dio | Closed | dio | dio | dio | Closed | dio | 2 | dio | dio | dio | Closed | dio | Closed | dio | Closed | dio | Design | Change Request | dio | Closed | dio | Closed | \10 Requirements | \Phase 1 | dio | dio | dio | dio | dio | dio | dio | dio | dio | Closed | dio | Closed | dio | Closed | dio | Closed | dio | Closed | dio | Closed | dio | Closed | dio | Closed | dio | Design | Change Request | dio | Closed | Closed | 2 | dio | dio | Closed | dio | 2 | dio | dio | Design | 2 | dio | dio | Closed | dio | 2 | \10 Requirements | \Phase 1 | dio | Closed | 2 | In progress | Closed | \Phase 1 | dio | Closed | \10 Requirements | 2 - High | 2 - High | 2 - High | 2 - High | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | dio | dio | dio | dio | dio | dio | dio | dio | 2 - High | 2 | Proposed | Closed | In progress | Change Request
|  |  |  | fengyan | Proposed | fengyan | Proposed | fengyan | Proposed | fengyan | Proposed | fengyan | Resolved | fengyan | fengyan | Proposed | fengyan | 3 | fengyan | fengyan | Proposed | fengyan | 3 | fengyan | fengyan | Proposed | fengyan | 3 | fengyan | fengyan | Proposed | fengyan | 3 | fengyan | fengyan | Resolved | fengyan | fengyan | fengyan | Proposed | fengyan | 3 | fengyan | fengyan | fengyan | Proposed | fengyan | all_VSTS_ab6d703e_6d0c_4d18_abd0_a67eae3ef4d5_Shared Steps_System.State | fengyan | In progress | fengyan | Ready | Issue | fengyan | Proposed | fengyan | Resolved | \20 Analysis | \Phase 2 | fengyan | fengyan | fengyan | fengyan | fengyan | fengyan | fengyan | fengyan | fengyan | Proposed | fengyan | Proposed | fengyan | Proposed | fengyan | Proposed | fengyan | Resolved | fengyan | Proposed | fengyan | all_VSTS_d9cdb1c3_3b79_4351_91a7_e256f1cd916d_Shared Steps_System.State | fengyan | In progress | fengyan | Ready | Issue | fengyan | Proposed | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Shared Steps_System.State | 3 | fengyan | fengyan | In progress | fengyan | 3 | fengyan | fengyan | Ready | 3 | fengyan | fengyan | Proposed | fengyan | 3 | \20 Analysis | \Phase 2 | fengyan | In progress | 3 | VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_50-5B-D0-C6-4D-02-A8-6F-40-65-26-EB-25-5E-77-D6-47-52-6D-6C | In progress | \Phase 2 | fengyan | VSTS_d9cdb1c3_3b79_4351_91a7_e256f1cd916d_C0-8B-87-81-67-52-71-76-29-2A-B8-4D-FB-D4-D6-6F-1E-E5-D9-2A | \20 Analysis | 3 - Medium | 3 - Medium | 3 - Medium | 3 - Medium | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | fengyan | fengyan | fengyan | fengyan | fengyan | fengyan | fengyan | fengyan | 3 - Medium | 3 | Resolved | Resolved | Resolved | Issue
|  |  |  | hazel | Resolved | hazel | Resolved | hazel | Resolved | hazel | Resolved | hazel | all_VSTS_ab6d703e_6d0c_4d18_abd0_a67eae3ef4d5_Review_System.State | hazel | hazel | Resolved | hazel | 4 | hazel | hazel | Resolved | hazel | 4 | hazel | hazel | Resolved | hazel | 4 | hazel | hazel | Resolved | hazel | 4 | hazel | hazel | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Review_System.State | hazel | hazel | hazel | Resolved | hazel | 4 | hazel | hazel | hazel | Resolved | hazel |  | hazel | Resolved | hazel | all_VSTS_ab6d703e_6d0c_4d18_abd0_a67eae3ef4d5_Test Case_System.State | Requirement | hazel | Resolved | hazel | VSTS_ab6d703e_6d0c_4d18_abd0_a67eae3ef4d5_26-FF-DE-08-0D-C9-09-53-1F-05-FD-90-D7-AD-D4-D5-FF-6A-89-45 | \20 Analysis\21 Use Case Model Survey | \Phase 3 | hazel | hazel | hazel | hazel | hazel | hazel | hazel | hazel | hazel | Resolved | hazel | Resolved | hazel | Resolved | hazel | Resolved | hazel | all_VSTS_d9cdb1c3_3b79_4351_91a7_e256f1cd916d_Review_System.State | hazel | Resolved | hazel |  | hazel | Resolved | hazel | all_VSTS_d9cdb1c3_3b79_4351_91a7_e256f1cd916d_Test Case_System.State | Requirement | hazel | Resolved |  | 4 | hazel | hazel | Resolved | hazel | 4 | hazel | hazel | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Test Case_System.State | 4 | hazel | hazel | Resolved | hazel | 4 | \20 Analysis\21 Use Case Model Survey | \Phase 3 | hazel | Resolved | 4 |  | VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_8B-D1-53-A2-A6-FB-4F-03-24-65-B4-29-73-CC-D1-C9-B6-3C-6A-90 | \Phase 3 | hazel |  | \20 Analysis\21 Use Case Model Survey | 4 - Low | 4 - Low | 4 - Low | 4 - Low | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | hazel | hazel | hazel | hazel | hazel | hazel | hazel | hazel | 4 - Low | 4 | VSTS_d9cdb1c3_3b79_4351_91a7_e256f1cd916d_F6-86-31-A3-47-27-76-CB-57-28-49-17-32-EB-97-93-07-11-CC-4D | VSTS_d9cdb1c3_3b79_4351_91a7_e256f1cd916d_26-FF-DE-08-0D-C9-09-53-1F-05-FD-90-D7-AD-D4-D5-FF-6A-89-45 | VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_6F-C6-D8-EB-43-26-13-F5-A3-D3-8B-09-48-94-22-7A-77-AF-E5-C2 | Requirement
|  |  |  | jifa | all_VSTS_ab6d703e_6d0c_4d18_abd0_a67eae3ef4d5_Bug_System.State | jifa | all_VSTS_ab6d703e_6d0c_4d18_abd0_a67eae3ef4d5_Change Request_System.State | jifa | all_VSTS_ab6d703e_6d0c_4d18_abd0_a67eae3ef4d5_Issue_System.State | jifa | all_VSTS_ab6d703e_6d0c_4d18_abd0_a67eae3ef4d5_Requirement_System.State | jifa |  | jifa | jifa | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Bug_System.State | jifa | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Bug_Microsoft.VSTS.Common.Priority | jifa | jifa | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Change Request_System.State | jifa | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Change Request_Microsoft.VSTS.Common.Priority | jifa | jifa | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Issue_System.State | jifa | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Issue_Microsoft.VSTS.Common.Priority | jifa | jifa | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Requirement_System.State | jifa | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Requirement_Microsoft.VSTS.Common.Priority | jifa | jifa |  | jifa | jifa | jifa | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Risk_System.State | jifa | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Risk_Microsoft.VSTS.Common.Priority | jifa | jifa | jifa | all_VSTS_ab6d703e_6d0c_4d18_abd0_a67eae3ef4d5_Risk_System.State | jifa |  | jifa | all_VSTS_ab6d703e_6d0c_4d18_abd0_a67eae3ef4d5_Task_System.State | jifa |  | Review | jifa | Assigned | jifa |  | \20 Analysis\22 Use Case Realization Report (Analysis) | all_VSTS_ab6d703e_6d0c_4d18_abd0_a67eae3ef4d5_System.IterationPath | jifa | jifa | jifa | jifa | jifa | jifa | jifa | jifa | jifa | all_VSTS_d9cdb1c3_3b79_4351_91a7_e256f1cd916d_Bug_System.State | jifa | all_VSTS_d9cdb1c3_3b79_4351_91a7_e256f1cd916d_Change Request_System.State | jifa | all_VSTS_d9cdb1c3_3b79_4351_91a7_e256f1cd916d_Issue_System.State | jifa | all_VSTS_d9cdb1c3_3b79_4351_91a7_e256f1cd916d_Requirement_System.State | jifa |  | jifa | all_VSTS_d9cdb1c3_3b79_4351_91a7_e256f1cd916d_Risk_System.State | jifa |  | jifa | all_VSTS_d9cdb1c3_3b79_4351_91a7_e256f1cd916d_Task_System.State | jifa |  | Review | jifa | Assigned |  | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Shared Steps_Microsoft.VSTS.Common.Priority | jifa | jifa | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Task_System.State | jifa | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Task_Microsoft.VSTS.Common.Priority | jifa | jifa |  | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Test Case_Microsoft.VSTS.Common.Priority | jifa | jifa | Assigned | jifa | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Microsoft.VSTS.Common.Priority | \20 Analysis\22 Use Case Realization Report (Analysis) | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_System.IterationPath | jifa | VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_9F-F6-0F-1C-08-6A-BA-DC-02-F0-E1-1F-9D-C4-DD-F3-E1-46-6F-4A | VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_A9-74-3C-60-20-83-BF-D2-70-44-DA-6E-AF-8C-55-96-9A-24-CE-B3 |  |  | all_VSTS_d9cdb1c3_3b79_4351_91a7_e256f1cd916d_System.IterationPath | jifa |  | \20 Analysis\22 Use Case Realization Report (Analysis) | all_VSTS_d9cdb1c3_3b79_4351_91a7_e256f1cd916d_Bug_Microsoft.VSTS.Common.Severity | all_VSTS_d9cdb1c3_3b79_4351_91a7_e256f1cd916d_Issue_Microsoft.VSTS.Common.Severity | all_VSTS_d9cdb1c3_3b79_4351_91a7_e256f1cd916d_Risk_Microsoft.VSTS.Common.Severity | all_VSTS_d9cdb1c3_3b79_4351_91a7_e256f1cd916d_Microsoft.VSTS.Common.Severity | all_VSTS_d9cdb1c3_3b79_4351_91a7_e256f1cd916d_Bug_Microsoft.VSTS.Common.Priority | all_VSTS_d9cdb1c3_3b79_4351_91a7_e256f1cd916d_Change Request_Microsoft.VSTS.Common.Priority | all_VSTS_d9cdb1c3_3b79_4351_91a7_e256f1cd916d_Issue_Microsoft.VSTS.Common.Priority | all_VSTS_d9cdb1c3_3b79_4351_91a7_e256f1cd916d_Requirement_Microsoft.VSTS.Common.Priority | all_VSTS_d9cdb1c3_3b79_4351_91a7_e256f1cd916d_Risk_Microsoft.VSTS.Common.Priority | all_VSTS_d9cdb1c3_3b79_4351_91a7_e256f1cd916d_Shared Steps_Microsoft.VSTS.Common.Priority | all_VSTS_d9cdb1c3_3b79_4351_91a7_e256f1cd916d_Task_Microsoft.VSTS.Common.Priority | all_VSTS_d9cdb1c3_3b79_4351_91a7_e256f1cd916d_Test Case_Microsoft.VSTS.Common.Priority | all_VSTS_d9cdb1c3_3b79_4351_91a7_e256f1cd916d_Microsoft.VSTS.Common.Priority | jifa | jifa | jifa | jifa | jifa | jifa | jifa | jifa | VSTS_d9cdb1c3_3b79_4351_91a7_e256f1cd916d_45-F5-9C-27-95-2A-7B-65-33-77-4B-A9-8C-81-2F-7D-A7-A1-56-F2 | VSTS_d9cdb1c3_3b79_4351_91a7_e256f1cd916d_A9-74-3C-60-20-83-BF-D2-70-44-DA-6E-AF-8C-55-96-9A-24-CE-B3 |  |  |  | Review
|  |  |  | LOCAL SERVICE |  | LOCAL SERVICE |  | LOCAL SERVICE |  | LOCAL SERVICE |  | LOCAL SERVICE |  | LOCAL SERVICE | LOCAL SERVICE |  | LOCAL SERVICE |  | LOCAL SERVICE | LOCAL SERVICE |  | LOCAL SERVICE |  | LOCAL SERVICE | LOCAL SERVICE |  | LOCAL SERVICE |  | LOCAL SERVICE | LOCAL SERVICE |  | LOCAL SERVICE |  | LOCAL SERVICE | LOCAL SERVICE |  | LOCAL SERVICE | LOCAL SERVICE | LOCAL SERVICE |  | LOCAL SERVICE |  | LOCAL SERVICE | LOCAL SERVICE | LOCAL SERVICE |  | LOCAL SERVICE |  | LOCAL SERVICE |  | LOCAL SERVICE |  | Risk | LOCAL SERVICE | In progress | LOCAL SERVICE |  | \30 Prototype |  | LOCAL SERVICE | LOCAL SERVICE | LOCAL SERVICE | LOCAL SERVICE | LOCAL SERVICE | LOCAL SERVICE | LOCAL SERVICE | LOCAL SERVICE | LOCAL SERVICE |  | LOCAL SERVICE |  | LOCAL SERVICE |  | LOCAL SERVICE |  | LOCAL SERVICE |  | LOCAL SERVICE |  | LOCAL SERVICE |  | LOCAL SERVICE |  | LOCAL SERVICE |  | Risk | LOCAL SERVICE | In progress |  |  | LOCAL SERVICE | LOCAL SERVICE |  | LOCAL SERVICE |  | LOCAL SERVICE | LOCAL SERVICE |  |  | LOCAL SERVICE | LOCAL SERVICE | In progress | LOCAL SERVICE |  | \30 Prototype |  | LOCAL SERVICE | [5 empty] | LOCAL SERVICE |  | \30 Prototype | [13 empty] | LOCAL SERVICE | LOCAL SERVICE | LOCAL SERVICE | LOCAL SERVICE | LOCAL SERVICE | LOCAL SERVICE | LOCAL SERVICE | LOCAL SERVICE | [5 empty] | Risk
|  |  |  | peishan |  | peishan |  | peishan |  | peishan |  | peishan |  | peishan | peishan |  | peishan |  | peishan | peishan |  | peishan |  | peishan | peishan |  | peishan |  | peishan | peishan |  | peishan |  | peishan | peishan |  | peishan | peishan | peishan |  | peishan |  | peishan | peishan | peishan |  | peishan |  | peishan |  | peishan |  | Shared Steps | peishan | Design | peishan |  | \30 Prototype\31 UI Prototype |  | peishan | peishan | peishan | peishan | peishan | peishan | peishan | peishan | peishan |  | peishan |  | peishan |  | peishan |  | peishan |  | peishan |  | peishan |  | peishan |  | peishan |  | Shared Steps | peishan | Design |  |  | peishan | peishan |  | peishan |  | peishan | peishan |  |  | peishan | peishan | Design | peishan |  | \30 Prototype\31 UI Prototype |  | peishan | [5 empty] | peishan |  | \30 Prototype\31 UI Prototype | [13 empty] | peishan | peishan | peishan | peishan | peishan | peishan | peishan | peishan | [5 empty] | Shared Steps
|  |  |  | se18team8s |  | se18team8s |  | se18team8s |  | se18team8s |  | se18team8s |  | se18team8s | se18team8s |  | se18team8s |  | se18team8s | se18team8s |  | se18team8s |  | se18team8s | se18team8s |  | se18team8s |  | se18team8s | se18team8s |  | se18team8s |  | se18team8s | se18team8s |  | se18team8s | se18team8s | se18team8s |  | se18team8s |  | se18team8s | se18team8s | se18team8s |  | se18team8s |  | se18team8s |  | se18team8s |  | Task | se18team8s | Ready | se18team8s |  | \30 Prototype\32 Architecture Prototye |  | se18team8s | se18team8s | se18team8s | se18team8s | se18team8s | se18team8s | se18team8s | se18team8s | se18team8s |  | se18team8s |  | se18team8s |  | se18team8s |  | se18team8s |  | se18team8s |  | se18team8s |  | se18team8s |  | se18team8s |  | Task | se18team8s | Ready |  |  | se18team8s | se18team8s |  | se18team8s |  | se18team8s | se18team8s |  |  | se18team8s | se18team8s | Ready | se18team8s |  | \30 Prototype\32 Architecture Prototye |  | se18team8s | [5 empty] | se18team8s |  | \30 Prototype\32 Architecture Prototye | [13 empty] | se18team8s | se18team8s | se18team8s | se18team8s | se18team8s | se18team8s | se18team8s | se18team8s | [5 empty] | Task
|  |  |  | thida |  | thida |  | thida |  | thida |  | thida |  | thida | thida |  | thida |  | thida | thida |  | thida |  | thida | thida |  | thida |  | thida | thida |  | thida |  | thida | thida |  | thida | thida | thida |  | thida |  | thida | thida | thida |  | thida |  | thida |  | thida |  | Test Case | thida | all_VSTS_ab6d703e_6d0c_4d18_abd0_a67eae3ef4d5_System.State | thida |  | \30 Prototype\33 Prototype Study Report |  | thida | thida | thida | thida | thida | thida | thida | thida | thida |  | thida |  | thida |  | thida |  | thida |  | thida |  | thida |  | thida |  | thida |  | Test Case | thida | all_VSTS_d9cdb1c3_3b79_4351_91a7_e256f1cd916d_System.State |  |  | thida | thida |  | thida |  | thida | thida |  |  | thida | thida | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_System.State | thida |  | \30 Prototype\33 Prototype Study Report |  | thida | [5 empty] | thida |  | \30 Prototype\33 Prototype Study Report | [13 empty] | thida | thida | thida | thida | thida | thida | thida | thida | [5 empty] | Test Case
|  |  |  | zaw |  | zaw |  | zaw |  | zaw |  | zaw |  | zaw | zaw |  | zaw |  | zaw | zaw |  | zaw |  | zaw | zaw |  | zaw |  | zaw | zaw |  | zaw |  | zaw | zaw |  | zaw | zaw | zaw |  | zaw |  | zaw | zaw | zaw |  | zaw |  | zaw |  | zaw |  | all_VSTS_ab6d703e_6d0c_4d18_abd0_a67eae3ef4d5_System.WorkItemType | zaw |  | zaw |  | \40 Design |  | zaw | zaw | zaw | zaw | zaw | zaw | zaw | zaw | zaw |  | zaw |  | zaw |  | zaw |  | zaw |  | zaw |  | zaw |  | zaw |  | zaw |  | all_VSTS_d9cdb1c3_3b79_4351_91a7_e256f1cd916d_System.WorkItemType | zaw |  |  |  | zaw | zaw |  | zaw |  | zaw | zaw |  |  | zaw | zaw |  | zaw |  | \40 Design |  | zaw | [5 empty] | zaw |  | \40 Design | [13 empty] | zaw | zaw | zaw | zaw | zaw | zaw | zaw | zaw | [5 empty] | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_System.WorkItemType
|  |  |  | all_VSTS_ab6d703e_6d0c_4d18_abd0_a67eae3ef4d5_Bug_System.AssignedTo |  | all_VSTS_ab6d703e_6d0c_4d18_abd0_a67eae3ef4d5_Change Request_System.AssignedTo |  | all_VSTS_ab6d703e_6d0c_4d18_abd0_a67eae3ef4d5_Issue_System.AssignedTo |  | all_VSTS_ab6d703e_6d0c_4d18_abd0_a67eae3ef4d5_Requirement_System.AssignedTo |  | all_VSTS_ab6d703e_6d0c_4d18_abd0_a67eae3ef4d5_Review_System.AssignedTo |  | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Bug_System.AssignedTo | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Bug_Microsoft.VSTS.Common.ClosedBy |  | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Bug_Microsoft.VSTS.Common.ResolvedBy |  | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Change Request_System.AssignedTo | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Change Request_Microsoft.VSTS.Common.ClosedBy |  | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Change Request_Microsoft.VSTS.Common.ResolvedBy |  | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Issue_System.AssignedTo | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Issue_Microsoft.VSTS.Common.ClosedBy |  | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Issue_Microsoft.VSTS.Common.ResolvedBy |  | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Requirement_System.AssignedTo | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Requirement_Microsoft.VSTS.Common.ClosedBy |  | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Requirement_Microsoft.VSTS.Common.ResolvedBy |  | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Review_System.AssignedTo | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Review_Microsoft.VSTS.Common.ClosedBy |  | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Review_Microsoft.VSTS.Common.ResolvedBy | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Risk_System.AssignedTo | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Risk_Microsoft.VSTS.Common.ClosedBy |  | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Risk_Microsoft.VSTS.Common.ResolvedBy |  | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Shared Steps_System.AssignedTo | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Shared Steps_Microsoft.VSTS.Common.ClosedBy | all_VSTS_ab6d703e_6d0c_4d18_abd0_a67eae3ef4d5_Risk_System.AssignedTo |  | all_VSTS_ab6d703e_6d0c_4d18_abd0_a67eae3ef4d5_Shared Steps_System.AssignedTo |  | all_VSTS_ab6d703e_6d0c_4d18_abd0_a67eae3ef4d5_Task_System.AssignedTo |  | all_VSTS_ab6d703e_6d0c_4d18_abd0_a67eae3ef4d5_Test Case_System.AssignedTo |  |  | all_VSTS_ab6d703e_6d0c_4d18_abd0_a67eae3ef4d5_System.AssignedTo |  | VSTS_ab6d703e_6d0c_4d18_abd0_a67eae3ef4d5_63-3D-6E-FD-05-A5-E3-0A-3D-3B-27-25-0E-09-89-A2-24-50-7D-FA |  | \40 Design\41 High level architecture |  | all_VSTS_ab6d703e_6d0c_4d18_abd0_a67eae3ef4d5_Bug_Microsoft.VSTS.Common.ResolvedBy | all_VSTS_ab6d703e_6d0c_4d18_abd0_a67eae3ef4d5_Change Request_Microsoft.VSTS.Common.ResolvedBy | all_VSTS_ab6d703e_6d0c_4d18_abd0_a67eae3ef4d5_Issue_Microsoft.VSTS.Common.ResolvedBy | all_VSTS_ab6d703e_6d0c_4d18_abd0_a67eae3ef4d5_Requirement_Microsoft.VSTS.Common.ResolvedBy | all_VSTS_ab6d703e_6d0c_4d18_abd0_a67eae3ef4d5_Review_Microsoft.VSTS.Common.ResolvedBy | all_VSTS_ab6d703e_6d0c_4d18_abd0_a67eae3ef4d5_Risk_Microsoft.VSTS.Common.ResolvedBy | all_VSTS_ab6d703e_6d0c_4d18_abd0_a67eae3ef4d5_Task_Microsoft.VSTS.Common.ResolvedBy | all_VSTS_ab6d703e_6d0c_4d18_abd0_a67eae3ef4d5_Microsoft.VSTS.Common.ResolvedBy | all_VSTS_d9cdb1c3_3b79_4351_91a7_e256f1cd916d_Bug_System.AssignedTo |  | all_VSTS_d9cdb1c3_3b79_4351_91a7_e256f1cd916d_Change Request_System.AssignedTo |  | all_VSTS_d9cdb1c3_3b79_4351_91a7_e256f1cd916d_Issue_System.AssignedTo |  | all_VSTS_d9cdb1c3_3b79_4351_91a7_e256f1cd916d_Requirement_System.AssignedTo |  | all_VSTS_d9cdb1c3_3b79_4351_91a7_e256f1cd916d_Review_System.AssignedTo |  | all_VSTS_d9cdb1c3_3b79_4351_91a7_e256f1cd916d_Risk_System.AssignedTo |  | all_VSTS_d9cdb1c3_3b79_4351_91a7_e256f1cd916d_Shared Steps_System.AssignedTo |  | all_VSTS_d9cdb1c3_3b79_4351_91a7_e256f1cd916d_Task_System.AssignedTo |  | all_VSTS_d9cdb1c3_3b79_4351_91a7_e256f1cd916d_Test Case_System.AssignedTo |  |  | all_VSTS_d9cdb1c3_3b79_4351_91a7_e256f1cd916d_System.AssignedTo |  |  |  | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Task_System.AssignedTo | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Task_Microsoft.VSTS.Common.ClosedBy |  | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Task_Microsoft.VSTS.Common.ResolvedBy |  | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Test Case_System.AssignedTo | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Test Case_Microsoft.VSTS.Common.ClosedBy |  |  | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_System.AssignedTo | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Microsoft.VSTS.Common.ClosedBy |  | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Microsoft.VSTS.Common.ResolvedBy |  | \40 Design\41 High level architecture |  | VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_63-3D-6E-FD-05-A5-E3-0A-3D-3B-27-25-0E-09-89-A2-24-50-7D-FA | [5 empty] | VSTS_d9cdb1c3_3b79_4351_91a7_e256f1cd916d_63-3D-6E-FD-05-A5-E3-0A-3D-3B-27-25-0E-09-89-A2-24-50-7D-FA |  | \40 Design\41 High level architecture | [13 empty] | all_VSTS_d9cdb1c3_3b79_4351_91a7_e256f1cd916d_Bug_Microsoft.VSTS.Common.ResolvedBy | all_VSTS_d9cdb1c3_3b79_4351_91a7_e256f1cd916d_Change Request_Microsoft.VSTS.Common.ResolvedBy | all_VSTS_d9cdb1c3_3b79_4351_91a7_e256f1cd916d_Issue_Microsoft.VSTS.Common.ResolvedBy | all_VSTS_d9cdb1c3_3b79_4351_91a7_e256f1cd916d_Requirement_Microsoft.VSTS.Common.ResolvedBy | all_VSTS_d9cdb1c3_3b79_4351_91a7_e256f1cd916d_Review_Microsoft.VSTS.Common.ResolvedBy | all_VSTS_d9cdb1c3_3b79_4351_91a7_e256f1cd916d_Risk_Microsoft.VSTS.Common.ResolvedBy | all_VSTS_d9cdb1c3_3b79_4351_91a7_e256f1cd916d_Task_Microsoft.VSTS.Common.ResolvedBy | all_VSTS_d9cdb1c3_3b79_4351_91a7_e256f1cd916d_Microsoft.VSTS.Common.ResolvedBy
[58 empty] | \40 Design\42 Detailed Design Specficiations | [46 empty] | \40 Design\42 Detailed Design Specficiations | [9 empty] | \40 Design\42 Detailed Design Specficiations
[58 empty] | \50 Build | [46 empty] | \50 Build | [9 empty] | \50 Build
[58 empty] | \50 Build\50 UI design | [46 empty] | \50 Build\50 UI design | [9 empty] | \50 Build\50 UI design
[58 empty] | \50 Build\51 Security and Admin | [46 empty] | \50 Build\51 Security and Admin | [9 empty] | \50 Build\51 Security and Admin
[58 empty] | \50 Build\52 Volunteer Management | [46 empty] | \50 Build\52 Volunteer Management | [9 empty] | \50 Build\52 Volunteer Management
[58 empty] | \50 Build\53 Staff Management | [46 empty] | \50 Build\53 Staff Management | [9 empty] | \50 Build\53 Staff Management
[58 empty] | \50 Build\54 Project Management | [46 empty] | \50 Build\54 Project Management | [9 empty] | \50 Build\54 Project Management
[58 empty] | \50 Build\55 Itinerary Management | [46 empty] | \50 Build\55 Itinerary Management | [9 empty] | \50 Build\55 Itinerary Management
[58 empty] | \50 Build\56 Reporting | [46 empty] | \50 Build\56 Reporting | [9 empty] | \50 Build\56 Reporting
[58 empty] | \60 Test | [46 empty] | \60 Test | [9 empty] | \60 Test
[58 empty] | \60 Test\61 Unit test | [46 empty] | \60 Test\61 Unit test | [9 empty] | \60 Test\61 Unit test
[58 empty] | \60 Test\62 SIT | [46 empty] | \60 Test\62 SIT | [9 empty] | \60 Test\62 SIT
[58 empty] | \60 Test\63 UAT | [46 empty] | \60 Test\63 UAT | [9 empty] | \60 Test\63 UAT
[58 empty] | \70 Report | [46 empty] | \70 Report | [9 empty] | \70 Report
[58 empty] | \70 Report\71 Presentation Phase 1 | [46 empty] | \70 Report\71 Presentation Phase 1 | [9 empty] | \70 Report\71 Presentation Phase 1
[58 empty] | \70 Report\72 Presentation Phase 2 | [46 empty] | \70 Report\72 Presentation Phase 2 | [9 empty] | \70 Report\72 Presentation Phase 2
[58 empty] | \70 Report\73 Presentation Phase 3 | [46 empty] | \70 Report\73 Presentation Phase 3 | [9 empty] | \70 Report\73 Presentation Phase 3
[58 empty] | \70 Report\74 End project report | [46 empty] | \70 Report\74 End project report | [9 empty] | \70 Report\74 End project report
[58 empty] | \80 Project Management | [46 empty] | \80 Project Management | [9 empty] | \80 Project Management
[58 empty] | \90 Quality Management | [46 empty] | \90 Quality Management | [9 empty] | \90 Quality Management
[58 empty] | all_VSTS_ab6d703e_6d0c_4d18_abd0_a67eae3ef4d5_System.AreaPath | [46 empty] | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_System.AreaPath | [9 empty] | all_VSTS_d9cdb1c3_3b79_4351_91a7_e256f1cd916d_System.AreaPath