## Slide 1: Volunteer Management System
Presented by Team SE18-08S

## Slide 2: Agenda
Project revisit
Use Case Modeling
Software Architecture
Demonstration of Prototype
Transition Strategy
Project Progress
Management Problems
Challenges
Q & A

## Slide 3: Introduction
Volunteer Management System

## Slide 4: Introduction – Recap of Project Requirements
Volunteer Management
Staff Management
Project Management
Itinerary Management
Administration

## Slide 5: Use Case Modeling
Volunteer Management System

## Slide 6: Use Case Modeling – Overview of Use Cases
In total: 28 Use cases – spread across 4 major components

## Slide 7: Use Case Modeling – Analysis of Use Case 1 – Assign Role to Member
This use case allows:
  Project Manager to assign different role to the project members
  Require interaction across Project Management, Volunteer Management modules

## Slide 8: Use Case Modeling – Analysis of Use Case 2 – Generate Report
This use case allows:
  Project Manager / Coordinator to generate Project Report / Volunteer Report
  Demonstrated the use of JasperReport components

## Slide 9: Software Architecture
Volunteer Management System

## Slide 10: High Level Architecture –Architecture Overview

## Slide 11: High Level Architecture –Architecture Overview
Web Server
  Apache 2.2
  Apache Load Balancer (JK module)
Application Server
  Tomcat 6.0
Database Server (RDBMS)
  Microsoft SQL Server 2008
Mail Server
  POP Mail server (eg. Gmail)

## Slide 12: High Level Architecture – Framework Overview

## Slide 13: High Level Architecture – Overview of Components

## Slide 14: Demonstration of Prototype
Volunteer Management System

## Slide 15: Demonstration of Prototype
Technical Prototype
User Interface Prototype

## Slide 16: Transition Strategy
Volunteer Management System

## Slide 17: Transition Strategy – Analysis to Design
Project Planning
Analysis and Design
Prototyping
Use Case Modeling
Use Case Realisation Report
High-level System Design
Software Architecture
Transition Strategy from Analysis to Design
Project Management

## Slide 18: Transition Strategy – Analysis to Design
No | Task | Description | In-Charge
1. | Prototyping | User interface prototyping Technical prototyping | Feng Yan, Jifa Zaw
2. | Use Case Modeling | Use case model survey | Thida, Hazel
3. | Use case realisation report | Use case realisation report | Thida, Hazel
4. | Software Design | High level software architecture design document | Zaw
5. | Transition Strategy from Analysis to Design | Transition Strategy from Analysis to Design | Zaw
6. | Project Management | Transition Strategy from Analysis to Design | Dio

## Slide 19: Transition Strategy
Active member involvement
  Involve all team members by clear and thorough communication
Clearly define roles and responsibilities
  Assign tasks to staff by capability and experience
Active risk management
  Anticipate risk early, accept and mitigate following the risk management techniques
Enforce tracking practices
  Monthly progress update

## Slide 20: PROJECT Progress
Volunteer Management System

## Slide 21: Project Progress
No | Activity | Planned Start Date | Planned End Date | Actual Start Date | Actual End Date | Planned Effort | Actual Effort | Task Status | Comments
1 | Project Planning |  |  |  |  |  |  |  | 
1.1 | Produce Project Plan | 21 Jan 2011 | 02 Apr 2011 | 20 Feb 2011 | 09 Apr 2011 | 7 | 9 | Done | Requirements gathering issues.
1.2 | Produce Quality Plan | 21 Jan 2011 | 02 Apr 2011 | 20 Feb 2011 | 05 Apr 2011 | 6 | 6.025 | Done | Makes changes based on Audit Meeting feedback
1.3 | Prepare First Audit & Presentation | 21 Jan 2011 | 02 Apr 2011 | 03 Apr 2011 | 09 Apr 2011 | 9 | 9 | Done | 
2 | Requirement Analysis |  |  |  |  |  |  |  | 
2.1 | Produce User Requirements Specifications | 22 Jan 2011 | 02 Apr 2011 | 20 Jan 2011 | 02 Apr 2011 | 18 | 13.6875 | Done | 
3 | Analysis Modelling |  |  |  |  |  |  |  | 
3.1 | Produce Functional Specifications : UCMS and UCRR (Analysis) | 10 Apr 2011 | 07 Jul 2011 |  |  | 38 |  | Open | 
3.3 | Produce Prototyping Study Report | 10 Apr 2011 | 12 Jun 2011 |  |  | 17.5 |  | Open | 

## Slide 22: Management Problems
Volunteer Management System

## Slide 23: Management Problems
No | Challenge | Description | Solution
1. | Communications | Difficulty to gather all members for discussions. | Online meeting via Skype To fix a weekly meeting time
2. | Requirements Gathering | Client only wants a small set of requirements. | Seek lecturers advice Proposed merging of requirements Appoint team members as putative end users Look for alternative customer
3. | Task Control | Not able to meet deadline on time. | To log time log To hold meetings to track status
4. | Low Quality of Work | Deliverables not up to standard. | Perform reviews Conduct briefing and demo on required items

## Slide 24: Challenges
Volunteer Management System

## Slide 25: Challenges
No | Challenge | Strategies
1. | Phung Kim Cuong, Dio | Project Manager
2. | Zaw Htet | Technical Lead
3. | Thida Khin Myo Thaung | Business Analyst
4. | Hnin Nu Aye | Business Analyst
5. | Feng Yan | Development Lead
6. | Jiang Jifa | Test Lead
7. | Liu Peishan | Quality Manager
Note: All team members will be programmer as well.

## Slide 26: Question & Answer