## Pending Tasks
Project: MTECH SE18 TEAM8S Server: team8s.myvnc.com\DefaultCollection Query: All unclosed tasks List type: Flat
ID | Work Item Type | Iteration Path | Area Path | Title | Assigned To | Start Date | Finish Date | State | Resolved By | Priority | Original Estimate | Remaining Work | Completed Work
35 | Task | \ | \80 Project Management | Looking for User | dio | 2011-01-01 00:41 | 2012-01-01 | Assigned |  | 4 | 8 | 8 | 0
5 | Task | \Phase 2 | \80 Project Management | Review WBS to reflect latest change | dio | 2011-06-01 08:00 | 2011-09-01 17:00 | In progress |  | 1 | 8 | 7 | 1
23 | Task | \Phase 3 | \80 Project Management | Development tasks break down - to use case level | dio | 2011-08-13 00:41 | 2011-08-19 00:41 | In progress |  | 1 | 12 | 8 | 4
28 | Task | \Phase 3 | \80 Project Management | To prepare Implementation Plan - down to use case level , include SIT | dio | 2011-08-13 00:41 | 2011-08-20 | In progress |  | 2 | 16 | 14 | 2
29 | Task | \Phase 3 | \80 Project Management | To produce tasks assignment for Detailed Design Document - involved all team members | dio | 2011-08-13 17:53 | 2011-08-25 17:53 | In progress |  | 1 | 8 | 8 | 0
49 | Task | \Phase 3 | \80 Project Management | To configure email sent out for TFS, to notice team member upon changes/new assignment | dio | 2011-08-21 16:04 | 2011-08-21 16:04 | In progress |  | 2 | 8 | 8 | 0
21 | Task | \Phase 2 | \80 Project Management | To explore how to use SVN Bug tracker, and how to generate project reports from SVN | fengyan | 2011-08-13 00:41 | 2011-08-20 | In progress |  | 2 | 12 | 12
4 | Task | \Phase 2 | \30 Prototype\31 UI Prototype | To create User Interface Prototype draft 1 | hazel | 2011-06-05 08:00 | 2011-06-16 17:00 | In progress |  | 1 | 16 | 6 | 10
30 | Task | \Phase 3 | \60 Test | Produce Test Plan | jifa | 2011-08-13 00:41 | 2011-08-20 | In progress |  | 2 | 8 | 8 | 0
31 | Task | \Phase 3 | \60 Test | Produce Test Script | jifa | 2011-08-13 00:41 | 2011-08-20 | In progress |  | 2 | 8 | 8 | 0
32 | Task | \Phase 3 | \90 Quality Management | Create Review Form for all outstanding deliverables (High level Architecture Design, Prototype Study Report, Transition Strategy) | jifa | 2011-08-13 00:41 | 2011-08-20 | In progress |  | 2 | 8 | 8 | 0
39 | Task | \Phase 2 | \70 Report\72 Presentation Phase 2 | High level Design (Prepare for technical Question) Prototype (Technical Issue/Risk/learned….) | peishan | 2011-08-13 00:41 | 2011-08-20 | Resolved | peishan | 2 | 8 | 8 | 0
25 | Task | \Phase 3 | \90 Quality Management | Separate Internal Meeting Minutes and Quality Audit Meeting Minutes | peishan | 2011-08-13 00:41 | 2011-08-20 | In progress |  | 2 | 8 | 8 | 0
34 | Task | \Phase 3 | \90 Quality Management | Put the indexing file to some specific required folder(E.g Analysis) | peishan | 2011-08-13 00:41 | 2011-08-20 | In progress |  | 2 | 8 | 8 | 0
19 | Task | \Phase 2 | \80 Project Management | Get familiar with Team Foundation Server | se18team8s | 2011-08-13 00:41 | 2011-08-20 | In progress |  | 2 | 8 | 8 | 0
26 | Task | \Phase 3 | \90 Quality Management | Update the document reference to the document header beside the system name (the coming deliverables) | se18team8s | 2011-08-13 00:41 | 2011-08-20 | In progress |  | 2 | 8 | 8 | 0
33 | Task | \Phase 3 | \90 Quality Management | Update and Review all the UCRR | thida | 2011-08-13 00:41 | 2011-08-20 | In progress |  | 2 | 8 | 8 | 0
50 | Task | \Phase 3 | \30 Prototype | To complete prototype - get at least 1 use case working end-to-end (include AJAX-DWR) | zaw | 2011-08-21 | 2011-08-28 | Assigned |  | 2 | 50 | 50 | 0

## VSTS_ValidationWS_1 (hidden)
value doesn't matter | value doesn't matter | value doesn't matter | value doesn't matter | admin | Active | 1 | admin | Active | 1 | admin | Active | 1 | admin | Active | 1 | admin | Active | admin | Active | 1 | admin | Active | 1 | admin | Assigned | 1 | admin | Closed | 1 | Bug | admin | Active | 1 | \ | \ | admin | Assigned | 1 | admin | admin | admin | admin | admin | admin | admin | admin | Closed | Closed | Assigned
readOnlyTestRange_@ | readOnlyTestRange_0 | readOnlyTestRange_dd-MMM-yy h:mm AM/PM | readOnlyTestRange_General | dio | Closed | 2 | dio | Closed | 2 | dio | Closed | 2 | dio | Closed | 2 | dio | Closed | dio | Closed | 2 | dio | Closed | 2 | dio | Closed | 2 | dio | Design | 2 | Change Request | dio | Closed | 2 | \10 Requirements | \Phase 1 | dio | Closed | 2 | dio | dio | dio | dio | dio | dio | dio | dio | In progress | In progress | Closed
|  |  |  | fengyan | Proposed | 3 | fengyan | Proposed | 3 | fengyan | Proposed | 3 | fengyan | Proposed | 3 | fengyan | Resolved | fengyan | Proposed | 3 | fengyan | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Shared Steps_System.State | 3 | fengyan | In progress | 3 | fengyan | Ready | 3 | Issue | fengyan | Proposed | 3 | \20 Analysis | \Phase 2 | fengyan | In progress | 3 | fengyan | fengyan | fengyan | fengyan | fengyan | fengyan | fengyan | fengyan | Resolved | VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_50-5B-D0-C6-4D-02-A8-6F-40-65-26-EB-25-5E-77-D6-47-52-6D-6C | In progress
|  |  |  | hazel | Resolved | 4 | hazel | Resolved | 4 | hazel | Resolved | 4 | hazel | Resolved | 4 | hazel | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Review_System.State | hazel | Resolved | 4 | hazel |  | 4 | hazel | Resolved | 4 | hazel | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Test Case_System.State | 4 | Requirement | hazel | Resolved | 4 | \20 Analysis\21 Use Case Model Survey | \Phase 3 | hazel | Resolved | 4 | hazel | hazel | hazel | hazel | hazel | hazel | hazel | hazel | VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_6F-C6-D8-EB-43-26-13-F5-A3-D3-8B-09-48-94-22-7A-77-AF-E5-C2 |  | VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_8B-D1-53-A2-A6-FB-4F-03-24-65-B4-29-73-CC-D1-C9-B6-3C-6A-90
|  |  |  | jifa | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Bug_System.State | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Bug_Microsoft.VSTS.Common.Priority | jifa | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Change Request_System.State | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Change Request_Microsoft.VSTS.Common.Priority | jifa | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Issue_System.State | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Issue_Microsoft.VSTS.Common.Priority | jifa | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Requirement_System.State | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Requirement_Microsoft.VSTS.Common.Priority | jifa |  | jifa | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Risk_System.State | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Risk_Microsoft.VSTS.Common.Priority | jifa |  | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Shared Steps_Microsoft.VSTS.Common.Priority | jifa | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Task_System.State | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Task_Microsoft.VSTS.Common.Priority | jifa |  | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Test Case_Microsoft.VSTS.Common.Priority | Review | jifa | Assigned | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Microsoft.VSTS.Common.Priority | \20 Analysis\22 Use Case Realization Report (Analysis) | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_System.IterationPath | jifa | VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_9F-F6-0F-1C-08-6A-BA-DC-02-F0-E1-1F-9D-C4-DD-F3-E1-46-6F-4A | VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_A9-74-3C-60-20-83-BF-D2-70-44-DA-6E-AF-8C-55-96-9A-24-CE-B3 | jifa | jifa | jifa | jifa | jifa | jifa | jifa | jifa
|  |  |  | LOCAL SERVICE |  |  | LOCAL SERVICE |  |  | LOCAL SERVICE |  |  | LOCAL SERVICE |  |  | LOCAL SERVICE |  | LOCAL SERVICE |  |  | LOCAL SERVICE |  |  | LOCAL SERVICE |  |  | LOCAL SERVICE |  |  | Risk | LOCAL SERVICE | In progress |  | \30 Prototype |  | LOCAL SERVICE |  |  | LOCAL SERVICE | LOCAL SERVICE | LOCAL SERVICE | LOCAL SERVICE | LOCAL SERVICE | LOCAL SERVICE | LOCAL SERVICE | LOCAL SERVICE
|  |  |  | peishan |  |  | peishan |  |  | peishan |  |  | peishan |  |  | peishan |  | peishan |  |  | peishan |  |  | peishan |  |  | peishan |  |  | Shared Steps | peishan | Design |  | \30 Prototype\31 UI Prototype |  | peishan |  |  | peishan | peishan | peishan | peishan | peishan | peishan | peishan | peishan
|  |  |  | se18team8s |  |  | se18team8s |  |  | se18team8s |  |  | se18team8s |  |  | se18team8s |  | se18team8s |  |  | se18team8s |  |  | se18team8s |  |  | se18team8s |  |  | Task | se18team8s | Ready |  | \30 Prototype\32 Architecture Prototye |  | se18team8s |  |  | se18team8s | se18team8s | se18team8s | se18team8s | se18team8s | se18team8s | se18team8s | se18team8s
|  |  |  | thida |  |  | thida |  |  | thida |  |  | thida |  |  | thida |  | thida |  |  | thida |  |  | thida |  |  | thida |  |  | Test Case | thida | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_System.State |  | \30 Prototype\33 Prototype Study Report |  | thida |  |  | thida | thida | thida | thida | thida | thida | thida | thida
|  |  |  | zaw |  |  | zaw |  |  | zaw |  |  | zaw |  |  | zaw |  | zaw |  |  | zaw |  |  | zaw |  |  | zaw |  |  | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_System.WorkItemType | zaw |  |  | \40 Design |  | zaw |  |  | zaw | zaw | zaw | zaw | zaw | zaw | zaw | zaw
|  |  |  | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Bug_System.AssignedTo |  |  | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Change Request_System.AssignedTo |  |  | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Issue_System.AssignedTo |  |  | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Requirement_System.AssignedTo |  |  | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Review_System.AssignedTo |  | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Risk_System.AssignedTo |  |  | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Shared Steps_System.AssignedTo |  |  | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Task_System.AssignedTo |  |  | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Test Case_System.AssignedTo |  |  |  | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_System.AssignedTo |  |  | \40 Design\41 High level architecture |  | VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_63-3D-6E-FD-05-A5-E3-0A-3D-3B-27-25-0E-09-89-A2-24-50-7D-FA |  |  | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Bug_Microsoft.VSTS.Common.ResolvedBy | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Change Request_Microsoft.VSTS.Common.ResolvedBy | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Issue_Microsoft.VSTS.Common.ResolvedBy | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Requirement_Microsoft.VSTS.Common.ResolvedBy | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Review_Microsoft.VSTS.Common.ResolvedBy | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Risk_Microsoft.VSTS.Common.ResolvedBy | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Task_Microsoft.VSTS.Common.ResolvedBy | all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_Microsoft.VSTS.Common.ResolvedBy
\40 Design\42 Detailed Design Specficiations
\50 Build
\50 Build\51 Security and Admin
\50 Build\52 Volunteer Management
\50 Build\53 Staff Management
\50 Build\54 Project Management
\50 Build\55 Itinerary Management
\50 Build\56 Reporting
\60 Test
\60 Test\61 Unit test
\60 Test\62 SIT
\60 Test\63 UAT
\70 Report
\70 Report\71 Presentation Phase 1
\70 Report\72 Presentation Phase 2
\70 Report\73 Presentation Phase 3
\70 Report\74 End project report
\80 Project Management
\90 Quality Management
all_VSTS_b53978b7_d470_4f54_b4ad_8f6a9c5092d9_System.AreaPath