## Sheet1
| Activitiy | Start | End
Design Modelling
1.1. | Produce detailed DS | 2011-08-12 | 2011-10-08
Software Implementation
2.1. | Produce System Code | 2011-10-09 | 2011-12-10
2.2. | Integrate System Code | 2011-10-09 | 2011-12-10
System Integration Testing
3.1. | Produce SIT plan, test script and test data | 2011-10-10 | 2011-10-20
3.2. | Perform System Integration Test and corrective actions | 2011-12-10 | 2011-12-30
4. | Project Report and Closure
4.1. | Produce Final Project report | 2011-12-20 | 2012-01-07
4.2. | Produce User Guide | 2011-08-13 | 2012-01-07
4.3. | Produce Project Presentation & Audit | 2011-12-30 | 2012-01-07
ACTIVITY | Aug |  | Sep | Oct | Nov | Dec | Jan
Produce detailed DS
Produce System Code
Common / Utility / Infrastructure
Volunteer Management
Project Management
Other Business Use Cases
Integrate System Code
Prepare SIT plan, test script & data
Perform SIT and corrective actions
Produce Final Project report
Produce User Guide
Produce Project Presentation & Audit